## Sheet2
Master Tracker Statuses
Yet to Start
In Progress
Complete
On Hold
Column Wise Update
Sprint Planning | Indicates Sprint N-1 planning, Backlog Grooming, sprint planning, prioritizing, etc
Dev + UT | Indicates Analysis, Dev, UT, Code Review, Peer Review, Dry Run in QA
QA Recon | Indicates testing and Recon on QA env by dev team, with PBC data
QA Validation | Indicates Test case creation, test case execution/Testing, capture results in PT, etc on QA env
Stage | Indicates Deployment on Stage env, test
Prod | Indicates deployment on prod env, validate (fix) deliverables on prod env by Datanutts
prod sign off | Indicates Testing by Virtusa QA Team includes 3 rounds of recon, testing, etc
Hypercare | Indicates defect fixing in prod by Datanutts
UAT | Indicates UAT Defect fixing by Datanutts
Others | All other necessary Documentation and prod readiness by Datanutts

## Business_Project_POC
Business_Project | POC Member's | Email Id
edm_processed_agency-E-Money | Suraj Sharma | suraj_sharma@newyorklife.com
edm_processed_agency-LAR | Habeebur Rahmana | habeebur_rahmana@newyorklife.com
edm_processed_agency-EmailCampaign | Suraj Sharma | suraj_sharma@newyorklife.com
edm_processed_agency-DataObjectives | Siddarth Doon | siddarth_doon@newyorklife.com
edm_processed_agency-Amp | Vinayakkaparatti Basavanneppa | vinayakkaparatti_basavanneppa@newyorklife.com
edm_processed_agency-FamilyBusiness | Siddarth Doon | siddarth_doon@newyorklife.com
edm_processed_agency-ADM-Qualtrics | Pavithra Velayutham | pavithra_velayutham@newyorklife.com
edm_processed_agency-Producer2.0-CandidateDaily | Navin kumar kurapati | navinkumar_kurapati@newyorklife.com
edm_processed_agency-FINRA | Navin kumar kurapati | navinkumar_kurapati@newyorklife.com
edm_processed_agency-AMS EPM feeds | Navin kumar kurapati | navinkumar_kurapati@newyorklife.com
edm_processed_agency-AMS LDAP feeds | Navin kumar kurapati | navinkumar_kurapati@newyorklife.com
edm_processed_party-PDMParty | Manoj (Onsite): (Virtusa employee) | manojjh@virtusa.com
edm_processed_party-PDMParty | Manoj (Onsite): (Virtusa employee) | Manoj_juttu_Hariharan1@newyorklife.com
edm_processed_party-PDMParty | Shobhikala (Offshore): (Virtusa employee) | shobikalap@virtusa.com
edm_processed_party-PDMParty | Shobhikala (Offshore): (Virtusa employee) | Shobikala_Palanivelu1@newyorklife.com
edm_processed_party-PDMParty | Chandra (Onsite): (He is a NYL employee) | chandrashekharreddy_siddireddygari@newyorklife.com
edm_proccessed_nb-Proj_nb | Partha Pratim Mandal | pamandal@virtusa.com

## NYL Sprint Plan 15
Squad | Team | NAME | Current assignment | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 | 2024-06-28 | 2024-07-01 | Number of leaves | Capacity | Number of jobs planned | Completed Jobs | Spill over | Stretch goals | Story Point Available | Bandwidth | Completed without Recon | Completed with Recon | In-Progress | Total Assigned | Committed
Squad11 | Project | Monika Joshi | Wave 3 & 4 | 2024-06-18: Technical calls + Code Review+Sprint Test planning+Prod roll out |  | 10 | 10
Squad11 | QA | Ashwin Kumar | Wave 3 & 4 | 2024-06-18: Prod Recon support , Data objectives seqDataObjAum seqDataObjBrinkerInitialfeed seqDataObjClientfeed seqInvAum529; 2024-06-20: Prod support Data objectives seqInvAumAGENT seqInvAumDST seqInvAumIWS seqInvAumNFS seqInvHouseHoldLdap SeqInvNewInvestorDonnelly; 2024-06-24: QA recon Policy PzFactContractLTC PzFactContractPrimaryProducer |  | 10 | 13
Squad12 | QA | Muni Sankar | Wave 3 & 4 | 2024-06-18: Prod suppot Family business, emoney seqMasterPzEmoney PzAnnuityFamilyBusinessExtract PzFamilyBusinessLoad PzLifeFamilyBusinessExtract seqFamilyBusiness; 2024-06-20: Prod support Producer 2.0 PzCandidateDailyView seqCandidateDailyView; 2024-06-24: QA Recon Policy PzFactCntProducerSalesAnnuity PzFactContractMoodyBondYield |  | 10 | 10
Squad11 | QA | Yogeshwar Kudal | Wave 3 & 4 | 2024-06-18: Prod recon support - AMP PzAmpCntClientMktrIns PzAmpCntClientMktrReportBusinessGrp PzAmpCntClientMktrReportCompensationGrp PzAmpFamilyBusinessNB21Extract PzAmpFamilyBusinessRPYExtract PzAmpMentorMenteeExtract PzTraditionalAmpFullExtract seqAmpGenerateBusinessReport seqAmpGenerateCompensationReport; 2024-06-20: Prod support - AMP,LAR PzEbossFinraAddress_lar1 PzEbossFinraAddress_lar2 PzEbossFinraAddress_lar3 seqMasterFinraAddressEboss_lar SseqFinraAddressEboss_lar; 2024-06-24: QA recon Policy PzFactFinInstitutionAcct PzFactContractCmpntInsuredDerv |  | 10 | 17
Squad12 | QA | Harsh Panchal | Wave 3 & 4 | 2024-06-18: Prod recon support Email campaign, FINRA Agency PzAmsFinraInfoLoad seqAmsFinraInfoLoad PzEmailCampaignInsUpdDel PzEmailCampaignOutbound PzEmailCampaignSrcExtrct1 PzEmailCampaignSrcExtrct2 PzEmailCampaignSrcExtrct3 PzEmailCampaignSrcExtrct4 PzEmailCampaignSrcExtrct5 seqEmailCampaign; 2024-06-20: Prod support ADM Qualtrics PzAgentContactFeeds_IncreLoad PzAgentContactFeeds_Initial PzRecruiterContactFeeds_IncreLoad PzRecruiterContactFeeds_Initial seqPzMasterADMQualtricsFeed_Incr seqPzMasterADMQualtricsFeed_Initial; 2024-06-24: QA recon Policy PzFactInvestmentBaseShareValue PzFactRelatedContracts |  | 10 | 19
Squad11 | QA | Mayank Kurkerja | Wave 3 & 4 | 2024-06-18: QA recon PzFactContractPolicyNotes; 2024-06-24: QA recon Policy PzFactContractPayeeContact |  | 10 | 2
Squad11 | Dev | Kiruthika Rajamohan | Wave 3 & 4 | 2024-06-18: Dev PzFactNbContractActivity; 2024-06-21: Dev PzBrgNbAgentStAddlDtlTp; 2024-06-26: Dev PzFactNbAgentStatementDimGeo7 |  | 10 | 3
Squad11 | Dev(n-1) | Sourabh Sharma | Wave 3 & 4 | 2024-06-18: Pre-req Sprint - 11/12 PzFactNbPrescrDrugFill3 PzFactNbPrescrDrugFill4 PzFactNbPrescrDrugFillCDC PzFactNbPrescrDrugFillSrc PzFactNbPrescriptionIcd1 PzFactNbPrescriptionIcd2 PzFactNbPrescriptionIcdCDC PzFactNbScheduledWork1 PzFactNbScheduledWork2 |  | 10 | 9
Squad11 | Dev(n-1) | Nisha Pursani | Wave 3 & 4 | 2024-06-18: Pre -req Sprint 11/12 PzBrgNbCntDclnReason PzBrgNbCntExtraPremRate PzBrgNbCntInsuredBnft PzBrgNbCntOriginalOffer PzBrgNbCntReinOffer PzBrgNbCntUwRiskClass PzBrgNbContractAmendment PzBrgNbContractBeneficiary PzBrgNbContractCorr PzBrgNbContractEventSts PzBrgNbContractExclusion PzBrgNbContractimpairment PzBrgNbInsuredOtherPolicy PzBrgNbUwCntInsRating PzFactNbCaseRemark1 PzFactNbCaseRemark2 PzFactNbCaseRemark2Src PzFactNbCaseRemark2Union1Src PzFactNbCaseRemark2Union2Src |  | 10 | 19
Squad11 | Dev(n-1) | Shreya Jain | Wave 3 & 4 | 2024-06-18: Pre-req Sprint 11/12 PzFactNbCaseRemark2Union3Src PzFactNbCaseRemark3 PzFactNbCaseRemarkcdc PzFactNbContractPart1 PzFactNbContractPart1cdc PzFactNbContractPart2 PzFactNbContractQcReply1 PzFactNbContractQcReply2 PzFactNbContractQcReplyCDC PzFactNbMedication_1 PzFactNbMedication_2 PzFactNbMedication_3 |  | 10 | 13
Squad11 | Dev-QA | Farajiya Khan | Wave 3 & 4 | 2024-06-18: QA recon Policy PzFactContractLowestPackage |  | 10 | 1
Squad11 | Dev-QA | Kamlendu Sarkar | Wave 3 & 4 | 2024-06-18: QA recon policy - PzFactCtcpCpiSkip |  | 10 | 1
Squad12 | Dev-QA | Rajat Singh | Wave 3 & 4 | 2024-06-18: QA recon Policy - PzFactContractPartyRoleDerv |  | 10 | 1
Squad11 | Dev-QA | Nikhil | Wave 3 & 4 | 2024-06-18: QA recon Policy - PzFactContractReinsurance |  | 10 | 1
Squad12 | QA | Ankit Singh | Wave 3 & 4 | 2024-06-18: Prod recon support - LDAP PzLdapVueFieldOfficeSpecInsUpdDel PzLdapVueFieldOfficeTeamFileCsv Prod recon support - EPM feeds PzLdapEPMFieldOfficeSpecInsUpdDel PzLdapEPMFieldOfficeTeamFileUnqorkCsv PzLdapEPMFieldOfficeTeamInsUpdDel; 2024-06-20: Prod recon support - LDAP feeds PzLdapVueFieldOfficeTeamInsUpdDel PzLdapVueStandardUserInsUpdDel seqLdapVueFileFeed; 2024-06-24: QA recon Policy PzFactContractTax | 1 | 9 | 6
Squad12 | Dev | Kamakshi | Wave 3 & 4 | 2024-06-18: Dev PzFactNbAgentStatementDimGeo3; 2024-06-21: Dev PzFactNbCntInsuredReqrSrcCntr2; 2024-06-26: Dev SeqPzNbSubAreaSet1Master |  | 10 | 3
Squad12 | Dev | Wasi | Wave 3 & 4 | 2024-06-18: Dev PzFactNbAgentStatementDimGeo4; 2024-06-21: Dev PzFactNbCntInsuredReqrSrcCntr3; 2024-06-26: Dev SSeqPzNbAgentStmt | 1 | 9 | 3
Squad12 | Dev | Krishna K | Wave 3 & 4 | 2024-06-18: Dev PzFactNbAgentStatementTrans2; 2024-06-21: Dev PzBrgNbAgentStmntOldCnt; 2024-06-26: Dev PzBrgNbAgentStmntOldCnt |  | 10 | 3
Squad12 | Dev | Sakshi T | Wave 3 & 4 | 2024-06-18: Dev PzBrgNbCntPartyRoleRelship; 2024-06-21: Dev PzFactNbCntInsuredPegaTrans; 2024-06-26: PzFactNbUwContractAlertcdc |  | 10 | 3
Squad12 | Dev | Kuldeep Sharma | Wave 3 & 4 | 2024-06-18: Dev PzBrgNbAgentStmntDpndnt; 2024-06-21: Dev PzFactNbAgentStatementDimGeo9; 2024-06-26: PzFactNbContractChange |  | 10 | 3
Squad12 | Dev | Govind Gaurav | Wave 3 & 4 | 2024-06-18: Dev PzBrgNbAgntStmntInsPrps; 2024-06-20: Leave; 2024-06-21: Leave; 2024-06-24: PzFactNbAgentStatementTrans3; 2024-06-26: PzFactNbUwContractAlert | 2 | 8 | 3
Squad12 | Dev | Smita Rasal | Wave 3 & 4 | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | 10 | 0 | 0
Squad12 | Dev | Sridevi Kommera | Wave 3 & 4 | 2024-06-18: Dev PzFactNbAgentStatementDimGeo5; 2024-06-21: Dev PzFactNbCntPartyRelshp1; 2024-06-26: Dev PzBrgNbAgentStmntAgent |  | 10 | 3
Squad12 | Dev | Rushil Patel | Wave 3 & 4 | 2024-06-18: Dev PzFactNbAgentStatementDimGeo6; 2024-06-21: Dev PzFactNbCntPartyRelshp2; 2024-06-26: Dev PzBrgNbCntPartyInsStmnt |  | 10 | 3
Squad11 | Dev | Subakartika | Wave 3 & 4 | [10 empty] | 10 | 0 | 0 | bar: 2024-06-18 to 2024-07-01
Total: | [13 empty] | 24 | 226 | 149 |  | 0
Leave
Spill Over Tasks
Completed Tasks
Blocker/Dependent Tasks
Ready for Deployment
OnHold

## Sprint_5
S No | Project | Business Project | Job | Mapping/Tf | Assigned To | Sprint Planning | Dev + UT | QA Recon | QA Validation | Stage | Prod | Prod Sign Off | UAT Sign Off | Remarks | Peer-Review Owner
1 | edm_processed_agency | DataObjectives | PzClientBrinkerAddr | m_RsClientBrinkerAddr | Muni | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  | Mocked up the data in source and UAT Done. | Kuldeep
2 | edm_processed_agency | DataObjectives | PzClientBrinkerAgent | m_RsClientBrinkerAgent | Smita | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  | Mocked up the data in source and UAT Done. | Rajat
3 | edm_processed_agency | DataObjectives | PzClientBrinkerInitial | m_RsClientBrinkerInitial | Sridevi | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  | Mocked up the data in source and UAT Done,documentation in progress. Rachit needs to give confirmation for two extra columns in target table | Farajiya
4 | edm_processed_agency | DataObjectives | PzClientInitialL10 | m_RsClientInitialL10 | Harsh | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  | Mocked up the data in source data and UAT Done. | Govind
5 | edm_processed_agency | DataObjectives | PzClientInvLkpRoleTranslation | m_RsClientInvLkpRoleTranslation | Sridevi | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  | Mocked up the data in source and UAT Done. | Sakshi
6 | edm_processed_agency | DataObjectives | PzClientL10Addr | m_RsClientL10Addr | Farajiya | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  | Mocked up the data in source and UAT Done. | Krishna
7 | edm_processed_agency | DataObjectives | PzClientL10Agent | m_RsClientL10Agent | Kamlendu | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  | Mocked up the data in source and UAT Done. | Kuldeep
8 | edm_processed_agency | DataObjectives | PzClientL10BrinkerLoad | m_RsClientL10BrinkerLoad | Kuldeep | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  | Mocked up the data in source and UAT Done. | Rajat
9 | edm_processed_agency | DataObjectives | PzClientOutboundFeed | m_RsClientOutboundFeed | Krishna | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  | Mocked up the data in source and UAT Done. | Farajiya
10 | edm_processed_agency | DataObjectives | PzInvAum529 | m_RsInvAum529 | Yogeshwar | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  |  | Govind
11 | edm_processed_agency | DataObjectives | PzInvAumAGENT | m_RsInvAumAGENT | Rajat | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  | Mocked up the data in source and UAT Done. | Sakshi
12 | edm_processed_agency | DataObjectives | PzInvAumDST | m_RsInvAumDST | Kiruthika | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  |  | Krishna
13 | edm_processed_agency | DataObjectives | PzInvAumIWS | m_RsInvAumIWS | Sourabh | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  | UT pending and has no data for testing | Harsh
14 | edm_processed_agency | DataObjectives | PzInvAumNFS | m_RsInvAumNFS | Shreya / Farajiya | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  | Mocked up the data in source and UAT Done. | Rajat
15 | edm_processed_agency | DataObjectives | PzInvHouseholdLdap | m_RsInvHouseholdLdap | Nisha | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  |  | Farajiya
16 | edm_processed_agency | DataObjectives | PzInvNewInvestorDonnelly | m_RsInvNewInvestorDonnelly | Govind | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  |  | Harsh
17 | edm_processed_agency | DataObjectives | seqDataObjAum | tf_seqDataObjAum | Muni | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start
18 | edm_processed_agency | DataObjectives | seqDataObjBrinkerInitialfeed | tf_seqDataObjBrinkerInitialfeed | Muni | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start
19 | edm_processed_agency | DataObjectives | seqDataObjClientfeed | tf_seqDataObjClientfeed | Muni | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  | Validated , need to run with default values if no data in the tables
20 | edm_processed_agency | DataObjectives | seqInvAum529 | tf_seqInvAum529 | Muni | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  | failed with Permisson issue - Operation failed: error [error [An error occured while executing the custom query: [select COALESCE(max(max(edm_file_last_received_date)::varchar),'19000101')::VARCHAR(2000) jpoutValue from ext_lake_int_agency_lookup.inv_aum where edm_src_cd='529plans'] due to: [[Amazon](500310) Invalid operation: AwsClientException: AccessDeniedException from glue - Resource does not exist or requester is not authorized to access requested permissions.;]. Please check the custom query ]].
21 | edm_processed_agency | DataObjectives | seqInvAumAGENT | tf_seqInvAumAGENT | Muni | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start
22 | edm_processed_agency | DataObjectives | seqInvAumDST | tf_seqInvAumDST | Muni | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start
23 | edm_processed_agency | DataObjectives | seqInvAumIWS | tf_seqInvAumIWS | Muni | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start
24 | edm_processed_agency | DataObjectives | seqInvAumNFS | tf_seqInvAumNFS | Muni | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start
25 | edm_processed_agency | DataObjectives | seqInvHouseHoldLdap | tf_seqInvHouseHoldLdap | Muni | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start
26 | edm_processed_agency | DataObjectives | SeqInvNewInvestorDonnelly | tf_seqInvNewInvestorDonnelly | Muni | Complete | Complete | Complete | In Progress | Yet to Start | Yet to Start |  |  | MCT Query issue

## Sprint_6
S No | Project | BusinessProject | Job Name(OnPrem) | Mapping/Tf | Assigned To | Sprint Planning | Dev + UT | QA Recon | QA Validation | Stage | Prod | Prod Sign Off | UAT Sign Off | Remarks | Peer-Review Owner | Status | DS Target Load
1 | edm_processed_agency | eMoney | OpsEmBatchJobRunDetailsLoad | m_RsEmBatchJobRunDetailsLoad | Krishna | Complete | on hold | [6 empty] | Conversion not pulled all sources, need to check with DataSwitch team/xml parser Need to check rachit on logic for Heirachy parser 03/05 - need a sample XML file name and directory - file need be available on agent
2 | edm_processed_agency | eMoney | OpsEmBatchSeqRunDetailsLoad | m_RsOpsEmBatchSeqRunDetailsLoad | Harsh | Complete | on hold | [6 empty] | Source and Target is Aurora need confirmation from suraj
3 | edm_processed_agency | eMoney | PzEmContractProductSplit | m_RsEmContractProductSplit | Sridevi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Dry Run Completed, UT complete,document in progress | Krishna | Done
4 | edm_processed_agency | eMoney | PzEmExtractKeyColumns | m_RsEmExtractKeyColumns | Harsh | Complete | Complete | Complete | Complete | Complete | Complete |  |  | acc_id column is not available in ACCOUNT table | Rajat | Done
5 | edm_processed_agency | eMoney | PzEMoneyCalcExtractData | m_RsEMoneyCalcExtractData | Sakshi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with data UT Complete | Yogeshwar | Done
6 | edm_processed_agency | eMoney | PzEMoneyEmd01AnnuitiesDataPrep1 | m_RsEMoneyEmd01AnnuitiesDataPrep1 | Farajiya | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with Data, need to prepare UT doc - Rushil - UT Completed | Rajat | Done
7 | edm_processed_agency | eMoney | PzEMoneyEmd01AnnuitiesDataPrep2 | m_RsEMoneyEmd01AnnuitiesDataPrep2 | Kamlendu | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked up the data in source and UAT Done. | Farajiya | Done
8 | edm_processed_agency | eMoney | PzEMoneyEmd01AnnuitiesPayoutFinal | m_RsEMoneyEmd01AnnuitiesPayoutFinal | Kuldeep | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked up the data in source and UAT Done. | Krishna | Done
9 | edm_processed_agency | eMoney | PzEMoneyEmd01AnnuPayoutSeqEQ00 | m_RsEMoneyEmd01AnnuPayoutSeqEQ00 | Krishna | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Dry run completed need to tested with data | Sridevi | Done
10 | edm_processed_agency | eMoney | PzEMoneyEmd01AnnuPayoutSeqNE00 | m_RsEMoneyEmd01AnnuPayoutSeqNE00 | Harsh | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Ran with dummy data enterd using hardcoded select query | Smita | Done
11 | edm_processed_agency | eMoney | PzEMoneyEmd01DataLoad | m_RsEMoneyEmd01DataLoad | Rajat | Complete | Complete | Complete | Complete | Complete | Complete |  |  | UT Done | Rushil | Done
12 | edm_processed_agency | eMoney | PzEMoneyEmd01HistTblLoad | m_RsEMoneyEmd01HistTblLoad | Smita | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success without data, UT completed | Govind | Done
13 | edm_processed_agency | eMoney | PzEMoneyEmd01InvestmentDataPrep | m_RsEMoneyEmd01InvestmentDataPrep | Harsh | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Ran with dummy data enterd using hardcoded select query | Sakshi | Done
14 | edm_processed_agency | eMoney | PzEMoneyEmd01LifeDataPrep1 | m_RsEMoneyEmd01LifeDataPrep1 | Sakshi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with Data UT Completed with Mocked up Data | Rajat | Done
15 | edm_processed_agency | eMoney | PzEMoneyEmd01LifeDataPrep2 | m_RsEMoneyEmd01LifeDataPrep2 | Yogeshwar | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Dry run completed - Rushil - UT Completed | Krishna | Done
16 | edm_processed_agency | eMoney | PzEMoneyEmd01LifeDataPrep3 | m_RsEMoneyEmd01LifeDataPrep3 | Govind | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with data, UT Complete | Yogeshwar | Done
17 | edm_processed_agency | eMoney | PzEMoneyEmd01LifeDataPrep4 | m_RsEMoneyEmd01LifeDataPrep4 |  | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | Rajat | Done
18 | edm_processed_agency | eMoney | PzEMoneyEmd01LtcDataPrep | m_RsEMoneyEmd01LtcDataPrep | Rushil | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with data, UT Complete | Farajiya | Done
19 | edm_processed_agency | eMoney | PzEMoneyEmd01OtherDataPrep | m_RsEMoneyEmd01OtherDataPrep | Smita | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with data, UT completed | Krishna | Done
20 | edm_processed_agency | eMoney | PzEMoneyEmd02HistTblLoad | m_RsEMoneyEmd02HistTblLoad | Kamlendu | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked up the data in source and UAT Done. | Sridevi | Done
21 | edm_processed_agency | eMoney | PzEMoneyEmd02Marketersdataload | m_RsEMoneyEmd02Marketersdataload | Kamlendu | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked up the data in source and UAT Done. | Smita | Done
22 | edm_processed_agency | eMoney | PzEMoneyEmd03AnnuitiesDataPrep | m_RsEMoneyEmd03AnnuitiesDataPrep | Sakshi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success Without Data UT Completed with Mocked up Data | Rushil | Done
23 | edm_processed_agency | eMoney | PzEMoneyEmd03DataLoad | m_RsEMoneyEmd03DataLoad | Farajiya | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked up the data in source and UAT Done. | Govind | Done
24 | edm_processed_agency | eMoney | PzEMoneyEmd03HistTblLoad | m_RsEMoneyEmd03HistTblLoad | Kamlendu | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked up the data in source and UAT Done. | Sakshi | Done
25 | edm_processed_agency | eMoney | PzEMoneyEmd03InvestmentDataPrep | m_RsEMoneyEmd03InvestmentDataPrep | Kuldeep | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with Data | Sridevi
26 | edm_processed_agency | eMoney | PzEMoneyEmd03LifeDataPrep | m_RsEMoneyEmd03LifeDataPrep | Krishna | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Dry run completed need to tested with data | Kamlendu | Done
27 | edm_processed_agency | eMoney | PzEMoneyEmd04ClientDataLoad | m_RsEMoneyEmd04ClientDataLoad | Yogeshwar | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Completed with Data, UT completed | Kamlendu | Done
28 | edm_processed_agency | eMoney | PzEMoneyEmd04HistTblLoad | m_RsEMoneyEmd04HistTblLoad | Rajat | Complete | Complete | Complete | Complete | Complete | Complete |  |  | UT Done | Farajiya | Done
29 | edm_processed_agency | eMoney | PzEMoneyEmd05ClientOwnerDataLoad | m_RsEMoneyEmd05ClientOwnerDataLoad | Sridevi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Dry Run Completed, UT complete,document done | Yogeshwar | Done
30 | edm_processed_agency | eMoney | PzEMoneyEmd05HistTblLoad | m_RsEMoneyEmd05HistTblLoad | Farajiya | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked up the data in source and UT Completed. | Kamlendu | Done
31 | m_RsEbossFinraAddress_lar1 | eMoney | PzEMoneyEmd07ClientInsuredrDataLoad | m_RsEMoneyEmd07ClientInsuredrDataLoad | Krishna | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Dry run completed need to tested with data | Sridevi | Done
32 | edm_processed_agency | eMoney | PzEMoneyEmd07HistTblLoad | m_RsEMoneyEmd07HistTblLoad | Kuldeep | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked up the data in source and UAT Done. | Smita | Done
33 | edm_processed_agency | eMoney | PzEMoneyEmd08BeneficiaryDataload | m_RsEMoneyEmd08BeneficiaryDataload | Govind | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with data, UT Complete | Rushil | Done
34 | edm_processed_agency | eMoney | PzEMoneyEmd08HistTblLoad | m_RsEMoneyEmd08HistTblLoad |  | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | Rushil | Done
35 | edm_processed_agency | eMoney | PzEMoneyEmd09HistTblLoad | m_RsEMoneyEmd09HistTblLoad | Rajat | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked Up the data/UT Done | Yogeshwar | Done
36 | edm_processed_agency | eMoney | seqMasterPzEmoney | tf_seqMasterPzEmoney | Harsh | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mapping on hold dependency
37 | Compliance | LAR | PzEbossFinraAddress_lar1 | m_RsEbossFinraAddress_lar1 | Ashwin | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | Smita | Done
38 | Compliance | LAR | PzEbossFinraAddress_lar2 | m_RsEbossFinraAddress_lar2 | Yogeshwar | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | Harsh/Krishna | Done
39 | Compliance | LAR | PzEbossFinraAddress_lar3 | m_RsEbossFinraAddress_lar3 | Harsh | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | Sridevi | Done
40 | Compliance | LAR | seqMasterFinraAddressEboss_lar | tf_seqMasterFinraAddressEboss_lar | Yogeshwar | Complete | Complete | Complete | Complete | Complete | Complete
41 | Compliance | LAR | SseqFinraAddressEboss_lar | tf_SseqFinraAddressEboss_lar | Yogeshwar | Complete | Complete | Complete | Complete | Complete | Complete

## Sprint_7
S No | Project | Business Project | Job | Mapping | Assigned To | Sprint Planning | Dev + UT | QA Recon | QA Validation | Stage | Prod | Prod Sign Off | UAT Sign Off | Remarks | Peer Review | Status
1 | edm_processed_agency | Family Business | PzAnnuityFamilyBusinessExtract | m_RsAnnuityFamilyBusinessExtract | Kamlendu | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success without Data and UT complete | Govind | Done
2 | edm_processed_agency | Family Business | PzFamilyBusinessLoad | m_RsFamilyBusinessLoad | Sakshi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success Without Data and UT completed (Target Table Schema provided By Rachit On 8/3/2024 ) (asked to ignore that Peek target so took Oracle as Target) | Kamlendu | Done
3 | edm_processed_agency | Family Business | PzLifeFamilyBusinessExtract | m_RsLifeFamilyBusinessExtract | Rajat | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Fixed and Modified query on own/UT DOC uploaded | Smita | Done
4 | edm_processed_agency | Family Business | seqFamilyBusiness | tf_seqFamilyBusiness | Kamlendu | Complete | Complete | Complete | Complete | Complete | Complete
5 | adm | ADM-Qualtrics | PzAgentContactFeeds_IncreLoad | m_AgentContactFeeds_IncreLoad | Govind | Complete | Complete | Complete | [5 empty] | Success without Data and UT complete | Kuldeep | Done
6 | adm | ADM-Qualtrics | PzAgentContactFeeds_Initial | m_AgentContactFeeds_Initial | Rushil | Complete | Complete | Complete | [6 empty] | Muni
7 | adm | ADM-Qualtrics | PzRecruiterContactFeeds_IncreLoad | m_RecruiterContactFeeds_IncreLoad | Farajiya | Complete | Complete | Complete | [5 empty] | CDC-logic ,need to confirm with Saranya ( to confirm if Dataswitch will fix it)--15/03- manually fixed Another issue is with src query-subquery is causing issue-Waiting for project team confirmation 22/03- Mapping ran without data, UT is done 26/03-Data is not loading to target because change code is not generated. It is coming as 0 and record is getting loaded into router default output group. Which is causing issue to load the data into target, Hence data is not loading to target in this scenario. | Rajat | Done
8 | adm | ADM-Qualtrics | PzRecruiterContactFeeds_Initial | m_RecruiterContactFeeds_Initial | Govind | Complete | Complete | Complete | [5 empty] | Success with Data, UT Done | Farajiya | Done
9 | adm | ADM-Qualtrics | seqPzMasterADMQualtricsFeed_Incr | tf_seqPzMasterADMQualtricsFeed_Incr | Govind | Complete | Complete | Complete | [5 empty] | CMD regarding confirmation needed by project team | Sakshi
10 | adm | ADM-Qualtrics | seqPzMasterADMQualtricsFeed_Initial | tf_seqPzMasterADMQualtricsFeed_Initial | Sakshi | Complete | Complete | Complete | [5 empty] | CMD regarding confirmation needed by project team
11 | edm_processed_agency | AMP | PzAmpCntClientMktrIns | m_RsAmpCntClientMktrIns | Farajiya | Complete | Complete | Complete | [5 empty] | Mct success with Data, UT document done. | Rajat | Done
12 | edm_processed_agency | AMP | PzAmpCntClientMktrReportBusinessGrp | m_RsAmpCntClientMktrReportBusinessGrp | Kuldeep | Complete | Complete | Complete | [6 empty] | Krishna | Done
13 | edm_processed_agency | AMP | PzAmpCntClientMktrReportCompensationGrp | m_AmpCntClientMktrReportCompensationGrp | Sridevi | Complete | Complete | Complete | [5 empty] | Mapping and mct success without data. UT document done. Target preSQL provided. | Smita | Done
14 | edm_processed_agency | AMP | PzAmpFamilyBusinessNB21Extract | m_RsAmpFamilyBusinessNB21Extract | Smita | Complete | Complete | Complete | [5 empty] | UT document complete with mock data. Session success without data | Sridevi | Done
15 | edm_processed_agency | AMP | PzAmpFamilyBusinessRPYExtract | m_RsAmpFamilyBusinessRPYExtract | Smita | Complete | Complete | Complete | [5 empty] | UT document complete Session success with data | Sridevi | Done
16 | edm_processed_agency | AMP | PzAmpMentorMenteeExtract | m_RsAmpMentorMenteeExtract | Sridevi | Complete | Complete | Complete | [5 empty] | Peer review - EXP_XfmDerived_OpsOutputStage - constraint logic seen in DS but not in IDMC / verify with offshore UT document done. Datastage has this target 'idms_mentor_mentee_dtls.txt' and load is overwrite file . mapping and mct got success with data. Datastage, IDMC target fields have datatype mismatch. idms_mentor_mentee_dtls: recrtr_agt_relatnsp_eff_dt: IDMC:str 10 but DS bigint, recrtr_agt_relatnsp_exprtn_dt: IDMC:str 10 but DS bigint, recrtr_shr_pct:IDMC:bigint but DS decimal 7,2 | Smita | Done
17 | edm_processed_agency | AMP | PzTraditionalAmpFullExtract | m_RsTraditionalAmpFullExtract | Rushil | Complete | Complete | Complete | [5 empty] | UT document completed TGT_hdfsValidMentor>>>ValidMentors table created | Muni/ Smita | Done
18 | edm_processed_agency | AMP | seqAmpGenerateBusinessReport | tf_seqAmpGenerateBusinessReport | Farajiya | Complete | Complete | Complete
19 | edm_processed_agency | AMP | seqAmpGenerateCompensationReport | tf_seqAmpGenerateCompensationReport | Kamlendu | Complete | Complete | Complete
20 | edm_processed_agency | Email Campaign | PzEmailCampaignInsUpdDel | m_RsEmailCampaignInsUpdDel | Harsh/Krishna | Complete | Complete | Complete | [6 empty] | Krishna
21 | edm_processed_agency | Email Campaign | PzEmailCampaignOutbound | m_EmailCampaignOutbound | Krishna | Complete | Complete | Complete | [6 empty] | Kuldeep | Done
22 | edm_processed_agency | Email Campaign | PzEmailCampaignSrcExtrct1 | m_RsEmailCampaignSrcExtrct1 | Sakshi | Complete | Complete | Complete | [5 empty] | UT document complete. Session success with data | Kamlendu | Done
23 | edm_processed_agency | Email Campaign | PzEmailCampaignSrcExtrct2 | m_RsEmailCampaignSrcExtrct2 | Smita | Complete | Complete | Complete | [5 empty] | UT document complete. Session success with data 1 Source and 1 Target table were created on 3/7/24. Other source table was created on 3/8/2024. Issue / concern - table 'rcr_cp_smy ' available in schema insurance_agency as created by Client on 03/08/2024. As of now, have defined an InOut parameter 'jpSchemaName_agency' with default value as 'insurance_agency ' schema in mapping but we need verify that this InOut paramter will be included in the updated parameter file as well. | Sridevi | Done
24 | edm_processed_agency | Email Campaign | PzEmailCampaignSrcExtrct3 | m_RsEmailCampaignSrcExtrct3 | Rajat | Complete | Complete | Complete | [5 empty] | UT Document uploaded | Farajiya | Done
25 | edm_processed_agency | Email Campaign | PzEmailCampaignSrcExtrct4 | m_RsEmailCampaignSrcExtrct4 | Rushil | Complete | Complete | Complete | [5 empty] | UT document completed SRC_fchdfsEmailCampaignSrcExtract2>>>EmailCampaignSrcExtract2 (table available in 3/7/24) | Muni/Sridevi | Done
26 | edm_processed_agency | Email Campaign | PzEmailCampaignSrcExtrct5 | m_RSEmailCampaignSrcExtrct5 | Sridevi | Complete | Complete | Complete | [5 empty] | Mapping and mct success with data. UT document done. Target preSQL provided. | Smita | Done
27 | edm_processed_agency | Email Campaign | seqEmailCampaign | tf_seqEmailCampaign | Krishna | Complete | Complete | Complete

## Sprint_8
S No | Project | Business Project | Job | Mapping | Assigned To | Sprint Planning | Dev + UT | QA Recon | QA Validation | Stage | Prod | Prod Sign Off | UAT Sign Off | Remarks | Peer Review | Status
1 | edm_processed_agency | Producer2.0-CandidateDaily | PzCandidateDailyView | m_RsCandidateDailyView | Kuldeep | Complete | Complete | Complete | [5 empty] | Success without Data,source table does not have any Data | Sridevi | Done
2 | edm_processed_agency | Producer2.0-CandidateDaily | seqCandidateDailyView | TF_seqCandidateDailyView | Kuldeep | Complete | Complete | Complete | [5 empty] | Complated without Ops job confirmation is pending.
3 | edm_processed_agency | FINRA | PzAmsFinraInfoLoad | m_RsAmsFinraInfoLoad | Kamlendu | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Completed with Data & UT done | Smita | Done
4 | edm_processed_agency | FINRA | seqAmsFinraInfoLoad | TF_seqAmsFinraInfoLoad | Kamlendu/Kuldeep | Complete | Complete | Complete | Complete | Complete | Complete
5 | edm_processed_agency | AMS EPM feeds | PzLdapEPMFieldOfficeSpecInsUpdDel | m_RsLdapEPMFieldOfficeSpecInsUpdDel | Sakshi | Complete | Complete | Complete | [5 empty] | Completed with Data UT done ,CDC-logic | Kuldeep
6 | edm_processed_agency | AMS EPM feeds | PzLdapEPMFieldOfficeTeamFileUnqorkCsv | m_RsLdapEPMFieldOfficeTeamFileUnqorkCsv | Govind | Complete | Complete | Complete | [5 empty] | Success without Data, UT Done | Rajat | Done
7 | edm_processed_agency | AMS EPM feeds | PzLdapEPMFieldOfficeTeamInsUpdDel | m_RsLdapEPMFieldOfficeTeamInsUpdDel | Krishna | Complete | Complete | Complete | [5 empty] | Mapping is validated and CDC-logic ,need to confirm with Saranya | Kamlendu
8 | edm_processed_agency | AMS EPM feeds | PzLdapEPMStandardUserInsUpdDel | m_RSLdapEPMStandardUserInsUpdDel | Rajat | Complete | Complete | Complete | [6 empty] | Farajiya | Done
9 | edm_processed_agency | AMS EPM feeds | seqLdapVueFileUnqorkFeed | tf_seqLdapVueFileUnqorkFeed | Krishna | Complete | Complete | Complete | [5 empty] | Tf is completed.Need confirmation one cmd which mct we need to use in idmc Ds CMD Task : "select max(edh_updated_batch_key) from #LdapHierarchyHiveDBConnectionString.$EDM_HUB_PZ_AGENCY_SCHEMA#.ldap_epm_field_office_team union select max(edh_created_batch_key) from #LdapHierarchyHiveDBConnectionString.$EDM_HUB_PZ_AGENCY_SCHEMA#.ldap_epm_field_office_team";
10 | edm_processed_agency | AMS LDAP feeds | PzLdapVueFieldOfficeSpecInsUpdDel | m_RsLdapVueFieldOfficeSpecInsUpdDel | Smita | Complete | Complete | Complete | [5 empty] | CDC logic. MCT run success. UT Complete | Krishna | Done | 5/2/2024 - Cleaned up and revalidated as per revised validation document
11 | edm_processed_agency | AMS LDAP feeds | PzLdapVueFieldOfficeTeamFileCsv | m_RsLdapVueFieldOfficeTeamFileCsv | Sridevi | Complete | Complete | Complete | [5 empty] | Source SRC_hiveLdapStandardUserSpec: has'Is_external' field datatype as integer but IDMC conversion pulled as string 100. Added Exp before tgt and fixed the logic. MCT success with no data. UT doc provided with no data in targets. Source tables does not have any data. 3/27/2024 MCT success with data. updated the UT document with data screen shots. | Harsh
12 | edm_processed_agency | AMS LDAP feeds | PzLdapVueFieldOfficeTeamFileUnqorkCsv | m_RsLdapVueFieldOfficeTeamFileUnqorkCsv |  | Complete |  | Descoped
13 | edm_processed_agency | AMS LDAP feeds | PzLdapVueFieldOfficeTeamInsUpdDel | m_RsLdapVueFieldOfficeTeamInsUpdDel | Smita | Complete | Complete | Complete | [5 empty] | CDC logic. MCT run success.UT Complete | Sakshi | Done | 5/2/2024 - Cleaned up and revalidated as per revised validation document
14 | edm_processed_agency | AMS LDAP feeds | PzLdapVueStandardUserInsUpdDel | m_RsLdapVueStandardUserInsUpdDel | Sridevi | Complete | Complete | Complete | [5 empty] | CDC job. MCT success. Needto check with Harsh.UT done. | Govind | Done | 5/2/2024 - Cleaned up mapping revalidated as per the validation document.
15 | edm_processed_agency | AMS LDAP feeds | seqLdapVueFileFeed | tf_seqLdapVueFileFeed | Sakshi | Complete | Complete | Complete | [5 empty] | Depends on mct_RsLdapVueFieldOfficeSpecInsUpdDel, mct_RsLdapVueFieldOfficeTeamInsUpdDel, mct_RsLdapVueStandardUserInsUpdDel, mct_RsLdapVueFieldOfficeTeamFileCsv

## EDM_Policy
Datastage2IDMC | [7 empty] | Standard Mappings |  |  |  | Advanced Mappings
Priority | Folder | Job | Mapping | Target Table | Mentor | Owner | Conversion status | Mapping Validation | MCT Run Status | Review Status | Unit Testing / All Flows | Switched to Advance | MCT Status | UT Documentation Status | DN Recon status | QA Deployment | MCT Status ( QA ) | Development Status | ETA | Peer Review
1.1 | Proj_policy | PzFactCntProducerSalesAnnuity | m_RsFactCntProducerSalesAnnuity m_RsFactCntProducerSalesAnnuity_adv | fact_cnt_producer_sales_annuity | Muni | Rushil | Yes | Validated | Success | Need to be peer reviewed Long running ,tuned as much as possible DS run time is 1hr 23 min in PROD ADV mapping runs for 1hr 5min pdm_conv.fact_cnt_producer_sales_annuity_max_prevtransdt need confirmation if this is truncate and load as no dates in table | UT Completed | Yes | Success |  |  |  |  | original mapping validation is done - need to be optimized tuned as much as possible, converted to adv standard mct ran with filter in source. Adv mct ran with full load |  | Smita | Paused, Muni will get back on optimization that was done using Union to replace all Joiners
1.1 | Proj_policy | PzFactContractMoodyBondYield | m_RsFactContractMoodyBondYield | Fact_Contract_Moody_Bond_Yield | Muni | Sridevi | Yes | Validated | Dry Run Completed | MCT success with no data. Completed | UT Completed | Yes | Success-old status Success |  |  |  |  | Advanced : success but standard mapping is not optimized |  | Rushil
1.1 | Proj_policy | PzFactContractOrgUnitRelation | m_RsFactContractOrgUnitRelation | fact_contract_org_unit_relation | Monika | Govind | Yes | Validated | Success | MCT Completed, UT Completed | UT Completed | [8 empty] | Sakshi | done
1.1 | Proj_policy | PzFactContractPayeeContact | m_RsFactContractPayeeContact | fact_contract_payee_contact | Muni | Smita | Yes | Validated | Success | MCT success. Standard mode session run completed in 2min 14sec.Hence as confirmed by Muni, did not switch to Advanced mode | UT Completed | No | [7 empty] | Sridevi | Sridevi completed peer reviewing of Adv asset and uploaded the document on 4/9/2024. Shailja assigned this to Sridevi. | done
1.1 | Proj_policy | PzFactContractPolicyNotes | m_RsFactContractPolicyNotes | fact_contract_policy_notes | Ashwin | Kamlendu | Yes | Validated | Success | MCT success with data and UT Completed | UT Completed | Yes | Success |  |  |  |  | Changes are not done suggested by Subu |  | Sakshi | done
1.1 | Proj_policy | PzFactContractReinsurance | m_RsFactContractReinsurance | fact_contract_reinsurance | Monika | Rajat | Yes | Validated | Success | Success, UT Completed | UT Completed | [8 empty] | Govind
1.1 | Proj_policy | PzFactContractTax | m_RsFactContractTax | fact_contract_tax | Yogeshwar | Rajat | Yes | Validated | Success | Success, UT Completed | UT Completed | Yes | Success | [6 empty] | Krishna
1.1 | Proj_policy | PzFactCtcpCpiSkip | m_RsFactCtcpCpiSkip | fact_ctcp_cpi_skip | Ashwin | Kuldeep | Yes | Validated | Success | Completed.UT Completed | UT Completed | [8 empty] | Govind
1.1 | Proj_policy | PzFactCtcpOppFinActivityHist | m_RsFactCtcpOppFinActivityHist | fact_ctcp_opp_fin_activty_hist | Ashwin | Farajiya | Yes | Validated | Dry Run Completed | Completed Advance mapping is failing , looking into the issue. 17 apr: Standard/Advanced mapping completed and UT completed. | UT Completed | Yes | Success | [6 empty] | Sridevi
1.1 | Proj_policy | PzFactFinInstitutionAcct | m_RsFactFinInstitutionAcct | fact_fin_institution_acct | Ashwin | Farajiya | Yes | Validated | Success | Completed.UT Completed | UT Completed | Yes | Success | [6 empty] | Rushil
1.1 | Proj_policy | PzFactInvestmentBaseShareValue | m_RsFactInvestmentBaseShareValue | fact_investment_base_share_value | Monika | Krishna | Yes | Validated | Success | Completed.UT Completed | UT Completed | Yes | [5 empty] | Advanced mapping is failed |  | Farajiya | 22 april: review completed
1.1 | Proj_policy | PzFactRelatedContracts | m_RsFactRelatedContracts | fact_related_contracts | Yogeshwar | Kamlendu | Yes | Validated | Success | MCT success with data and UT Completed | UT Completed | [8 empty] | Kuldeep
1.1 | Proj_policy | PzFactContractCmpntInsuredDerv | m_RsFactContractCmpntInsuredDerv | fact_contract_cmpnt_insured_derv | Yogeshwar | Krishna | Yes | Validated | old - Success/On Hold | 1.MCT ran Successfully.All UT scenario tested, except Full load taking time. Fullload is stopped because running continous more than 1 hrs(As suggest by mam) so i have tested 51000 records inserted for full load . Other UT scenrios working fine. 2.Switich to ad. but it will take 1 hour to complete the mct | UT Completed | Yes | Success | [6 empty] | Rajat
1.1 | Proj_policy | PzFactContractLowestPackage | m_RsFactContractLowestPackage | fact_contract_lowest_package | Harsh | Kuldeep | Yes | Validated | Success | Success, UT Completed | UT Completed | Yes | Success | [6 empty] | Rajat
1.1 | Proj_policy | PzFactContractLTC | m_RsFactContractLTC | fact_contract_ltc | Harsh | Smita | Yes | Validated | Success | Optimised 4 sources in to one combined query. Removed one JoinerKeyCols and RTR logic and optimized mapping. Session success - 17 min(Prod run is 14 min, hence as confirmed by Muni since delta is 3, hence no need to switch to Advance mode) | UT Completed | No | [7 empty] | Sridevi | Shailja has assigned this asset for peer review to Sridevi. Started on 4/9/2024.
1.1 - High | Proj_policy | PzFactContractPrimaryProducer | m_RsFactContractPrimaryProducer | fact_contract_primary_producer | Monika | Sridevi/Kamlendu | Yes | Validated | Success-old status | MCT success with data. Limited rows in source. Long running(47 minutes without limit) Assigned to Kamlendu after tuninig,good candidate for ADV mapping | UT Completed | [6 empty] | In standard mapping limited data in source query MCT got success.Long running(47 minutes) Note: SRT_sortproduceridnk ---- DS: producer_id_nk is also in sort keys under partition tab. Ascending ,Nulls last. But IDMC not. need to veriywith someone. EXP_xfmproduceridnk ----verify DS has a constraint keychange = 1 but IDMC not. ----- but it is not going forward. |  | Rushil
1.1 - High | Proj_policy | PzFactCtcpInvestmentBaseActvt | m_RsFactCtcpInvestmentBaseActvt | fact_ctcp_investment_base_actvt | Ashwin | Rushil | Yes | Validated | Success | Success | UT Completed | Yes | Success | [6 empty] | Smita | Completed on 04/30/2024 after mapping was revalidated as per Validation doc and suggestions from offshore
1.1 | Proj_policy | PzFactInvestAccountPrimaryProducer | m_RsFactInvestAccountPrimaryProducer | fact_invest_account_primary_producer | Harsh | Sakshi | Yes | Validated | Success | Success with data , STM Checked,UT completed | UT Completed | Yes | Success |  |  |  |  | Changes are not done suggested by Subu |  | Krishna
1.1 - High | Proj_policy | PzFactContractPartyRoleDerv | m_RsFactContractPartyRoleDerv | fact_contract_party_role_derv | Muni | Kamlendu | Yes | Validated | Success | Success with data , STM Checked,UT completed | UT Completed | Yes | Success | [6 empty] | Sridevi
`

## Sprint _9
| Project | BusinessProject | Job | Mapping | IDMC Job Type | Owner | Sprint Planning | Dev + UT | QA Recon | QA Validation | Stage | Prod | Prod Sign Off | UAT Sign Off | ETA | Remarks | Peer Review | Status
1 | edm_processed_party | PDMParty | SeqPzPartyDimMaster | tf_RsPartyDimMaster | Taskflow | Kamlendu | Complete | [8 empty] | This is master sequence, depends on 5 sub sequences and need to check for cmd,how to handle it.
2 | edm_processed_party | PDMParty | SSeqPzPartyDim1 | tf_RsPartyDim1 | Taskflow | Kamlendu | Complete | In Progress | [6 empty] | 2024-05-31 | Only Editing ETA because In this seq, having 10+ cmd's, need to check for cmd.
3 | edm_processed_party | PDMParty | PzDimBeneficiary | m_RsDimBeneficiary | Advanced | Kamlendu | Complete | Success | [7 empty] | Considered bene_id_nk as Varchar and Completed the Mapping with UT Complete |  |  | 2024-08-05
4 | edm_processed_party | PDMParty | PzDimContractPartyRole | m_RsDimContractPartyRole | StandardPDO | Kuldeep | Complete | Success | [7 empty] | UT Completed
5 | edm_processed_party | PDMParty | PzDimAgentCandRecrtmtStg | m_RsDimAgentCandRecrtmtStg | StandardPDO | Krishna | Complete | Success | [7 empty] | UT Completed
6 | edm_processed_party | PDMParty | PzLkpAgentCandRecrtmtStg | m_RsLkpAgentCandRecrtmtStg | StandardPDO | Sakshi | Complete | Success | [7 empty] | Mapping Success with data , UT Complete
7 | edm_processed_party | PDMParty | SSeqPzPartyDim2 | tf_Rs_PartyDim2 | Taskflow | Farajiya | Complete | On Hold | [7 empty] | In this seq, having 14 cmd's, need to check for cmd.
8 | edm_processed_party | PDMParty | PzDimClient | m_RsDimClient | Advanced | Farajiya/Sridevi | Complete | In Progress | [7 empty] | Ashwin is working on query optimization.Mapping is complex. 03/06: Waiting for Ashwin to complete query optimization. 6/20/2024 Sridevi is validating,will tune once complete
9 | edm_processed_party | PDMParty | PzDimFund | m_RsDimFund | Advanced | Rushil | Complete | success | [7 empty] | Mapping Success with data , UT Complete
10 | edm_processed_party | PDMParty | SSeqPzPartyDim3 | tf_RsPartyDim3 | Taskflow | Kamlendu | Complete | [7 empty] | 2024-06-05 | Only Editing ETA because In this seq, having 10+ cmd's, need to check for cmd.
11 | edm_processed_party | PDMParty | PzDimName | m_RsDimName | Advanced | Rajat | Complete | Success | [7 empty] | UT Complete
12 | edm_processed_party | PDMParty | PzDimAgentCandidateLead | m_RsDimAgentCandidateLead | StandardPDO | Govind | Complete | Success | [7 empty] | MCT & UT completed.
13 | edm_processed_party | PDMParty | PzDimProducerLicenseLOB | m_RsDimProducerLicenseLOB | Advanced | Smita | Complete | Success | [7 empty] | MCT & UT complete.
14 | edm_processed_party | PDMParty | PzLkpProducerLicenseLob | m_RsLkpProducerLicenseLob | Advanced | Sridevi | Complete | Success | [7 empty] | MCT success. UT Completed. validated as per revised validation document.
15 | edm_processed_party | PDMParty | SSeqPzPartyDim4 | tf_RsPartyDim4 | Taskflow | Kamlendu | Complete | [7 empty] | 2024-06-06 | Only Editing ETA because In this seq, having 10+ cmd's, need to check for cmd.
16 | edm_processed_party | PDMParty | PzLkpProducerType | m_RsLkpProducerType | Advanced | Farajiya | Complete | Success | [7 empty] | Mapping is success, UT completed
17 | edm_processed_party | PDMParty | PzDimProducerType | m_RsDimProducerType | Advanced | Rajat | Complete | Success | [7 empty] | UT Complete
18 | edm_processed_party | PDMParty | PzDimProducerCompensation | m_RsDimProducerCompensation | Advanced | Krishna | Complete | Success | [7 empty] | UT Completed
19 | edm_processed_party | PDMParty | PzLkpProducerCompensation | m_RsLkpProducerCompensation | Advanced | Sakshi | Complete | Success | [6 empty] | 21-05 | MCT & UT completed. DS having 4 src while in IDMC 3 src are present , Conversion Issue
20 | edm_processed_party | PDMParty | SSeqPzPartyDim5 | tf_RsPartyDim5 | Taskflow | Kamlendu | Complete | [7 empty] | 2024-06-07 | Only Editing ETA because In this seq, having 10+ cmd's, need to check for cmd.
21 | edm_processed_party | PDMParty | DimIncomeExpense | m_RsDimIncomeExpense | StandardPDO | Kuldeep | Complete | Success | [7 empty] | UT Completed
22 | edm_processed_party | PDMParty | PzLkpIncomeExpense | m_RsLkpIncomeExpense | Advanced | Govind | Complete | Success | [7 empty] | MCT & UT completed.
23 | edm_processed_party | PDMParty | PzDimProducerContractType | m_RsDimProducerContractType | Advanced | Nisha | Complete | Success | [7 empty] | Mapping Success with data , UT Complete
24 | edm_processed_party | PDMParty | PzLkpProducerContractType | m_RsLkpProducerContractType | Advanced | Shreya | Complete | Success | [7 empty] | Mapping Success with data , UT Complete
25 | edm_processed_party | PDMParty | SeqPzDimClientCombClientRel2 | tf_Rs_DimClientCombClientRel2 | Taskflow | Farajiya | Complete | Edited | [7 empty] | 15 May-Working on cmd,once mct will complete,will test seq
27 | edm_processed_party | PDMParty | SeqPzPartyDimClientCombRelMaster | tf_SeqPzPartyDimClientCombRelMaster | Taskflow | Kamlendu | Complete | [7 empty] | 2024-06-07 | Only Editing ETA because In this seq, having 10+ cmd's, need to check for cmd.
28 | edm_processed_party | PDMParty | SSeqPzPartyDimClientCombRel | tf_SSeqPzPartyDimClientCombRel | Taskflow | Kamlendu | Complete | [7 empty] | 2024-06-07 | Only Editing ETA because In this seq, having 10+ cmd's, need to check for cmd.
29 | edm_processed_party | PDMParty | PzDimClientCombClientRel1 | m_RsDimClientCombClientRel1 | StandardPDO | Sridevi | Complete | In Progress | [7 empty] | Source: ext_lake_oracle_orap03_co0101.client Targets: pdm_conv.dim_client_comb_client_rel_full pdm_conv.dim_client_comb_client_rel_matched pdm_conv.dim_client_comb_client_rel_Nonmatched Please followup with Sana on pdm_conv.dim_client_comb_client_rel_Nonmatched MCT Success. UT on hold. Waiting on confirmation from client. Smita has fixed joiners and was missing one joiner also. Same source table and 3 target for Fulll,NotMultipleMatch and Match records,email sent to client Still waiting on client. Issue is escalated. last follow up with Sana/Farajiya is : 6/12/2024
26 | edm_processed_party | PDMParty | PzDimClientCombClientRel2 | m_RsDimClientCombClientRel2 | StandardPDO | Smita | Complete | In Progress | [6 empty] | 18-05 | This dependent on Rel1 Source : pdm_conv.dim_client_comb_client_rel_matched pdm_conv.dim_client_comb_client_rel_full Target : pdm_conv.dim_client_comb_client_rel_matched_trg pdm_conv.dim_client_comb_client_rel_Nonmatched_inbatch_key Please followup with Sana on pdm_conv.dim_client_comb_client_rel_Nonmatched_inbatch_key --- 05/20 - provided src and tgt table connections. Mapping is valid. Session is running > 30 min. Need to review / run with limit - WIP. Shailja asked to hold until Client confirms. UT pending. 05/10-Need confirmation from Client on source and target tables - both are same in pre req document. 05/20 - Client asked to provide table names as per DataStage, all 4 table connections are provided in mapping Still waiting on client. Issue is escalated. last follow up with Sana/Farajiya is : 6/12/2024
30 | edm_processed_party | PDMParty | PzDimClientCombClientRel3 | m_RsDimClientCombClientRel3 | Advanced | Rushil | Complete | success | [7 empty] | Dependency on Rel1 Mapping Success with data , UT Complete rel3: Source pdm_conv.dim_client_comb_client_rel_Nonmatched ext_lake_oracle_orap03_co0101.client pdm_conv.dim_client_comb_client_rel Target pdm_conv.etl_party_reject_table pdm_conv.ops_etl_config_batch_key pdm_conv.dim_client_comb_client_rel pdm_conv.dim_client_comb_client_rel Please followup with Sana on pdm_conv.dim_client_comb_client_rel_Nonmatched -- need to ask sana about fields not match ds--fixed
31 | edm_processed_party | PDMParty | SeqPzPartyFactAgentCandRecrtmtFunnelMaster | tf_Rs_PartyFactAgentCandRecrtmtFunnelMaster | Taskflow | Farajiya | Complete | Edited | [7 empty] | This is master sequence, depends on two sub sequences and need to check for cmd,how to handle it.
32 | edm_processed_party | PDMParty | SSeqPzPartyFactAgentCandRecrtmtFunnel | tf_Rs_SPzPartyFactAgentCandRecrtmtFunnel | Taskflow | Kuldeep | Complete | [8 empty] | Dependent MCt is on hold due to Conversion Issue
33 | edm_processed_party | PDMParty | PzFactAgentCandRecrtmtFunnel | m_RsFactAgentCandRecrtmtFunnel | Advanced | Kuldeep | Complete | On Hold | [7 empty] | 1. Optimization is done and validation was in WIP But project team made some changes in flow now it become complex need new converted code to re-optimize with new flow. 2. Now it have new 5 duplicate logic,2 router,2 aggergator,2 lookup, 2 peek targets.
34 | edm_processed_party | PDMParty | PzFactAgentAvisoryCouncil | m_RsFactAgentAvisoryCouncil | StandardPDO | Govind | Complete | Success | [6 empty] | 2024-06-06 | MCT & UT completed.
35 | edm_processed_party | PDMParty | PzFactBookOfBusiness | m_RsFactBookOfBusiness | Advanced | Rajat | Complete | Success | [7 empty] | UT Complete/ Mapping is running 42 Min
36 | edm_processed_party | PDMParty | PzFactClientCommunication | m_RsFactClientCommunication | StandardPDO | Krishna | Complete | Success | [7 empty] | UT Completed
37 | edm_processed_party | PDMParty | PzFactClientSubscription | m_RsFactClientSubscription | StandardPDO | Sakshi | Complete | Success | [7 empty] | Mapping Success with data , UT Complete , update flow is not working because chksum key is included in main joiner 20/06 - As per discussion with Manoj proceeding as per datastage , ignoring update ,it will only insert data¦ deleted inactive target
38 | edm_processed_party | PDMParty | PzFactFatca | m_RsFactFatca | Advanced | Govind | Complete | Success | [6 empty] | 21-05 | MCT & UT completed.
39 | edm_processed_party | PDMParty | PzFactProducerAddtionalExpense | m_RsFactProducerAddtionalExpense | StandardPDO | Smita | Complete | Success | [7 empty] | MCT Successwith data. UT Complete
40 | edm_processed_party | PDMParty | PzFactProducerAdvisoryBoardDirector | m_RsFactProducerAdvisoryBoardDirector | Advanced | Sridevi | Complete | Success | [7 empty] | MCT Success, UT completed
41 | edm_processed_party | PDMParty | PzFactProducerCertification | m_RsFactProducerCertification | Advanced | Rushil | Complete | success | [7 empty] | Mapping Success with data , UT Complete
42 | edm_processed_party | PDMParty | PzFactProducerCompensation | m_RsFactProducerCompensation | Advanced | Farajiya | Complete | Success | [7 empty] | Got confirmation with project team as it is SCD-1 but in the DS description, mentioned as SCD-2. 30 April: Proceeding with SCD-1 as confirmed by poc, working for scd1 flow. Mapping success with Data and UT Completed
43 | edm_processed_party | PDMParty | PzFactProducerDebitArrangement | m_RsFactProducerDebitArrangement | StandardPDO | Kamlendu | Complete | Success | [7 empty] | MCT success with data and UT completed
44 | edm_processed_party | PDMParty | PzFactProducerEdLicCmplnc | m_RsFactProducerEdLicCmplnc | Advanced | Sakshi | Complete | Success | [7 empty] | Mapping Success with data , UT Complete
45 | edm_processed_party | PDMParty | PzFactProducerFinancialInstitution | m_RsFactProducerFinancialInstitution | StandardPDO | Govind | Complete | Success | [7 empty] | MCT & UT completed.
46 | edm_processed_party | PDMParty | PzFactProducerFinra | m_RsFactProducerFinra | Advanced | Farajiya | Complete | Success | [6 empty] | 15-05 | MCT & UT Completed
47 | edm_processed_party | PDMParty | PzFactProducerGeneralOfficeComp | m_RsFactProducerGeneralOfficeComp | StandardPDO | Sridevi | Complete | Success | [6 empty] | 16-05 | MCT success. UT Completed.
48 | edm_processed_party | PDMParty | PzFactProducerGroupMembership | m_RsFactProducerGroupMembership | Advanced | Rushil | Complete | In Progress | [7 empty] | Mapping success. Need to start UT Data switch team will reconvert mapping - 5/13 Sent message on 6/17 to sana to follow up on it again
49 | edm_processed_party | PDMParty | PzFactProducerIncomeExpense | m_RsFactProducerIncomeExpense | Advanced | Krishna | Complete | Success | [6 empty] | 23-05 | Clubbed query getting error out of memory issue checking with harsh & mam so i have tested all scercnio expect full load bcz of long running so i have tested 100 record it working fine Filter :- producer_id_nk='0351106' and src_sk='92477364' Revised ETA - 29/05
50 | edm_processed_party | PDMParty | PzFactProducerLedger | m_RsFactProducerLedger | Advanced | Rajat | Complete | Success | [7 empty] | UT Complete
51 | edm_processed_party | PDMParty | PzFactProducerLtcTraining | m_RsFactProducerLtcTraining | Advanced | Rajat | Complete | Success | [7 empty] | UT Complete
52 | edm_processed_party | PDMParty | PzFactProducerMdrtMembership | m_RsFactProducerMdrtMembership | Advanced | Krishna | Complete | Success | [7 empty] | UT Completed
53 | edm_processed_party | PDMParty | PzFactProducerPartnerCompensation | m_RsFactProducerPartnerCompensation | StandardPDO | Kiruthika | Complete | Success | [7 empty] | UT Completed
54 | edm_processed_party | PDMParty | PzFactProducerPartnerRole | m_RsFactProducerPartnerRole | StandardPDO | Sakshi | Complete | success | [6 empty] | 29-05 | Mapping Success with data , UT Complete
55 | edm_processed_party | PDMParty | PzFactProducerProducerRel | m_RsFactProducerProducerRel | Advanced | Kuldeep | Complete | Success | [7 empty] | UT Completed
56 | edm_processed_party | PDMParty | PzFactProducerStCntyReqr | m_RsFactProducerStCntyReqr | Advanced | Nisha | Complete | Success | [7 empty] | Mapping Success with data,UT Completed
57 | edm_processed_party | PDMParty | PzFactProducerSubsidiaryCnt | m_RsFactProducerSubsidiaryCnt | Advanced | Govind | Complete | Success | [7 empty] | MCT & UT completed.
58 | edm_processed_party | PDMParty | PzFactAgentCandidateEducation | m_RsFactAgentCandidateEducation | Advanced | Kamlendu | Complete | success | [6 empty] | 16-05 | UT -WIP
59 | edm_processed_party | PDMParty | PzFactAgentCandidateEmployment | m_RsFactAgentCandidateEmployment | StandardPDO | Smita | Complete | Success | [6 empty] | 16-05 | UT Complete MCT success.
60 | edm_processed_party | PDMParty | PzFactAgentCandidateExperience | m_RsFactAgentCandidateExperience | StandardPDO | Sourabh | Complete | Success | [7 empty] | Mapping is success with data, UT Complete
61 | edm_processed_party | PDMParty | PzFactAgentCandidateLead | m_RsFactAgentCandidateLead | Advanced | Shreya | Complete | Success | [7 empty] | Mapping is success with data, UT Complete
62 | edm_processed_party | PDMParty | PzFactAgentCandidateRecrtmt | m_RsFactAgentCandidateRecrtmt | Advanced | Shreya | Complete | Success | [6 empty] | 16-05 | Mapping is success with data, UT Complete
63 | edm_processed_party | PDMParty | PzFactProducerActivity | m_RsFactProducerActivity | Advanced | Nisha | Complete | Success | [7 empty] | Mapping is success with data, UT Complete,Converted in Advance mode
64 | edm_processed_party | PDMParty | PzFactProducerLicense | m_RsFactProducerLicense | Advanced | Rushil | Complete | success | [6 empty] | 2024-05-29 | Mapping Success with data , UT Complete runs longer than production time is DS --- converted to adv mapping after truncating target and running adv mapping it finished in 5 min and when reran it took 12 min
Note on Q14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Converted DataSwitch mapping - few expressions were incorrect in Expression tab. Fixed as per DataStage
Note on Q60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 05/10 - Awaiting confirmation from Client for - Issue : SRC_hiveTableSrc - Query has missing field - DataSwitch original mapping has hardcoded the field vs DataStage it is not . 'a.addl_rmrk_txt' addl_rmrk_free_txt . Without single quotes, query error : error [error [Provided Custom query is invalid due to:[[Amazon](500310) Invalid operation: column a.addl_rmrk_txt does not exist;]]]

## Sprint 10
S No | Project | BusinessProject | Job | Mapping | IDMC Job type | Assigned To | Sprint Planning | Dev + UT | QA Recon | QA Validation | Stage | Prod | Prod Sign Off | UAT Sign Off | ETA | Remarks | Peer Review | Status
1 | edm_processed_party | PDMParty | PzFactAgentCandidateLeadScore | m_RsFactAgentCandidateLeadScore | Advanced | Rajat | Complete | Success | [6 empty] | 17-05 |  |  | UT Complete
2 | edm_processed_party | PDMParty | PzFactAgentCandidateLeadScreen | m_RsFactAgentCandidateLeadScreen | Advanced | Sourabh | Complete | Success | [6 empty] | 17-05 |  |  | MCT success with data and UT completed
3 | edm_processed_party | PDMParty | PzFactProducer | m_RsFactProducer | Advanced | Smita/Rushil | Complete | Blocked | [7 empty] | working on STM of other assets |  | Julian day/date logic is there in expression is not supported in Informatica EXP_xfmActiveRecs --Datastage ----JulianDayFromDate(lnkActiveRecs.rec_exp_dt) integer EXP_XfmMaxDate--Datastage logic DateFromJulianDay(lnkMaxDate.max_date_aggr+1) datetime Mapping is tuned by combining queries where ever applicable :15 min runtime Waiting for confirmation from project team
4 | edm_processed_party | PDMParty | PzFactProducerAddlDtls | m_RSFactProducerAddlDtls | Advanced | Shivangi | Complete | Success | [9 empty] | MCT success with data and UT completed
5 | edm_processed_party | PDMParty | PzFactProducerCouncil | m_RsFactProducerCouncil | Advanced | Shivangi | Complete | Success | [6 empty] | 16-05 |  |  | MCT success with data and UT completed
6 | edm_processed_party | PDMParty | PzFactProducerDerv | m_RsFactProducerDerv | Advanced | Sonveer | Complete | Success | [6 empty] | 20-05 |  |  | MCT success with data and UT completed
7 | edm_processed_party | PDMParty | PzFactProducerFldSuprtEnroll | m_RSFactProducerFldSuprtEnroll | Advanced | Krishna | Complete | Success | [6 empty] | 22-05 |  |  | Working on docu ETA by :22/05/
8 | edm_processed_party | PDMParty | PzFactProducerRecruitment | m_RSFactProducerRecruitment | Advanced | Farajiya | Complete | Success | [6 empty] | 2024-06-12 |  |  | Half query part optimization completed , need help in other part Informed to Thomas. Proceeding with half part query optimization, verified query with harsh, working on mapping optimization. 07/06: Still in progress bcz code is not proper in sync with DS. 10/06: validation is complete, mapping is failing on preview. working on it. 12/06: MCT success with data and UT completed
9 | edm_processed_party | PDMParty | PzFactProducerStSolicElg | m_RsFactProducerStSolicElg | Advanced | Kuldeep/Nikhil | Complete | In Progress | [9 empty] | 1.Node count: 180 ,Source 13,Sorter 52,Joiner 27 2. 95% optimization done, need help to clubbed one of the Exp inside source Query. 3. Mapping flows is complex. but it can be redesign but first need to discuss STM with Harsh and than need confimation with project team.
10 | edm_processed_party | PDMParty | PxFactAgentStaffRelation |  |  | Rajat | Complete | Unpublished
11 | edm_processed_party | PDMParty | SeqPzPartyFactFmisMaster | tf_RsPartyFactFmisMaster | Taskflow | Kamlendu | Complete | On Hold | [6 empty] | 2024-06-11 | It's Master Tasflow were to 2 Subtasflow is used tf_RsSSeqPzPartyFactFmis and tf_SubSeqPzParty_Recon. tf_SubSeqPzParty_Recon is not in our Tracker need to confirm who will provide the validated Subtaskflow.
12 | edm_processed_party | PDMParty | SSeqPzPartyFactFmis | tf_RsSSeqPzPartyFactFmis | Taskflow | Govind | Complete | On Hold | [6 empty] | 2024-06-11 |  |  | For this TF, MCT mct_RsFactFmisCntProducerPremShare Full Load is taking too much time for running.(TF not edited yet)
13 | edm_processed_party | PDMParty | PzFactFmisCntProducerPremShare | m_RsFactFmisCntProducerPremShare | Advanced | Nikhil | Complete | Success | [6 empty] | 17-05 |  |  | 1.MCT ran Successfully.All UT scenario tested, except Full load taking time. Fullload is stopped because running continous more than 2 hrs(As suggest by mam) . Other UT scenrios working fine. This condition 'where A.cnt_id_nk=39710540 and A.mkshr_totcpn_prmam=402 and F.ent_plan_cd='UNK' ' used for testing UT scenarios.(QA team will take care of this job for Full Load). 2. in HiveLkpProduct src duplicate records is present. With this condition 'edh_record_end_ts='9999-12-31'' duplicate can be removed. But this need to be confirm from project team.
14 | edm_processed_party | PDMParty | PzFactProducerNasdExam |  | Advanced | Sridevi | Complete | Unpublished
15 | edm_processed_party | PDMParty | SeqPzPartyFactMaster | tf_RsPartyFactMaster | Taskflow | Sakshi | Complete | On Hold | [9 empty] | Dependent on SSeqPzPartyFact
16 | edm_processed_party | PDMParty | SSeqPzPartyFact |  | Taskflow |  | Complete | [10 empty] | It's Master Tasflow were to 2 Subtasflow is used tf_RsSSeqPzPartyFact and tf_SubSeqPzParty_Recon. tf_SubSeqPzParty_Recon is not in our Tracker .
Note on S4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6/6/2024 - MCT success , EXP_xfmIndFldUpd and EXP_xfmReject - IDMC mapping DataSwitch code for expression fields does not match DataStge code for many fields RTR_fltrCult_Mktr_cd - DataSwitch conversion has incorrect FIELD RENAME and 1 other field renaming is missed, 2 more discrepancies fixed. Sources - 18, Targets - 4, Joiners -37, Sorters - 74 approx

## Sprint 11
S No | Project | Subject Area | BusinessProject | Job | Mapping | IDMCJobType | Assigned | Sprint Planning | Dev + UT | QA Recon | QA Validation | Stage | Prod | Prod Sign Off | UAT Sign Off | ETA | Remarks | Peer Review | Status
1 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzBrgNbAgentStAddlDtlTp | m_RsBrgNbAgentStAddlDtlTp | Advanced | Sakshi | [9 empty] | Optimization done
2 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzBrgNbAgentStmntAgent | m_RsBrgNbAgentStmntAgent | Advanced | Kamakshi |  | InProgress
3 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzBrgNbAgentStmntDpndnt | m_RsBrgNbAgentStmntDpndnt | StandardPDO | Kuldeep |  | InProgress
4 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzBrgNbAgentStmntFundSrc | m_RsBrgNbAgentStmntFundSrc | StandardPDO | Kuldeep |  | InProgress
5 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzBrgNbAgentStmntOldCnt | m_RsBrgNbAgentStmntOldCnt | StandardPDO | Krishna |  | InProgress | [7 empty] | src's are clubbed and working on validation
6 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzBrgNbAgntStmntInsPrps | m_RsBrgNbAgntStmntInsPrps | Advanced | Govind |  | InProgress
7 | edm_processed_nb | NB - Contract Party Relationship | Proj_nb | PzBrgNbCntPartyRoleRelship | m_RsBrgNbCntPartyRoleRelship | Advanced | Sakshi |  | InProgress
8 | edm_processed_nb | NB - Contract Party Relationship | Proj_nb | PzBrgNbContractOldCnt | m_RsBrgNbContractOldCnt | Advanced | Shreya
9 | edm_processed_nb | NB - Contract Alert | Proj_nb | PzBrgNbUwContractAlert | PzFactNbCntInsuredReqr | StandardPDO | Nisha
10 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementCdc | PzFactNbUwMIB | Advanced | Sourabh
11 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo1 | m_RsFactNbAgentStatementDimGeo1 | StandardPDO | Govind
12 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo2 | m_RsFactNbAgentStatementDimGeo2 | StandardPDO | Wasi
13 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo3 | m_RsFactNbAgentStatementDimGeo3 | StandardPDO | Kamakshi |  | InProgress | [6 empty] | 24/7/24 | Target Table fact_nb_agent_statement_GeoTrans3 is not found in pdm_conv schema
14 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo4 | m_RsFactNbAgentStatementDimGeo4 | StandardPDO | Wasi |  | InProgress | [7 empty] | Mapping is validated before Target. TGT Table pdm_conv/fact_nb_agent_statement_GeoTrans4 is missing. |  |  | Waiting on client on target table name
15 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo5 | m_RsFactNbAgentStatementDimGeo5 | StandardPDO | Sridevi |  | In progress | [6 empty] | 2024-05-30 | target table fact_nb_agent_statement doesn't match one of the fileld iagstmid_ref. Datastage target is a ff and it has 4 fields, IDMC target has 127 fields 3 fields are matching one field is not matching. This target table is used in other mappings also. Mapping validated before target. provided /data/EDM_Agency/Cache for CachePath. |  |  | Waiting on client on target table name
16 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo6 | m_RsFactNbAgentStatementDimGeo6 | StandardPDO | Rushil |  | In progress | [10 empty] | Waiting on client on target table name
17 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo7 | m_RsFactNbAgentStatementDimGeo7 | StandardPDO | Govind
18 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo8 | m_RsFactNbAgentStatementDimGeo8 | StandardPDO | Krishna
19 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo9 | m_RsFactNbAgentStatementDimGeo9 | StandardPDO | Kuldeep
20 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementTrans1 | m_RsFactNbAgentStatementTrans1 | StandardPDO | Rushil
21 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementTrans2 | m_RsFactNbAgentStatementTrans2 | StandardPDO | Krishna
22 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementTrans3 | m_RsFactNbAgentStatementTrans3 | Advanced | Govind
23 | edm_processed_nb | NB - Contract Insured Pega Transaction | Proj_nb | PzFactNbCntInsuredPegaTrans | m_RsFactNbCntInsuredPegaTrans | Advanced | Sakshi
24 | edm_processed_nb | NB - Contract Insured Requirement | Proj_nb | PzFactNbCntInsuredReqr | m_RsFactNbCntInsuredReqr | StandardPDO | Shreya
25 | edm_processed_nb | NB - Contract Insured Requirement | Proj_nb | PzFactNbCntInsuredReqr1 |  | Advanced | Nisha
26 | edm_processed_nb | NB - Contract Insured Requirement | Proj_nb | PzFactNbCntInsuredReqrCDC |  | StandardPDO | Sourabh
27 | edm_processed_nb | NB - Contract Insured Requirement | Proj_nb | PzFactNbCntInsuredReqrSrc | m_RsFactNbCntInsuredReqrSrc | StandardPDO | Sakshi
28 | edm_processed_nb | NB - Contract Insured Requirement | Proj_nb | PzFactNbCntInsuredReqrSrcCntr1 | m_RsFactNbCntInsuredReqrSrcCntr1 | StandardPDO | Wasi
29 | edm_processed_nb | NB - Contract Insured Requirement | Proj_nb | PzFactNbCntInsuredReqrSrcCntr2 | m_RsFactNbCntInsuredReqrSrcCntr2 | StandardPDO | Kamakshi |  | inProgress | [7 empty] | Target Table missing fact_nb_cnt_insured_reqr_src_Contract2
30 | edm_processed_nb | NB - Contract Insured Requirement | Proj_nb | PzFactNbCntInsuredReqrSrcCntr3 | m_RsFactNbCntInsuredReqrSrcCntr3 | StandardPDO | Wasi |  | InProgress | [7 empty] | Mapping is validated and Optimised before Target. TGT Table pdm_conv/fact_nb_cnt_insured_reqr_src_Contract3 is missing. |  |  | Waiting on client on target table name
31 | edm_processed_nb | NB - Contract Party Relationship | Proj_nb | PzFactNbCntPartyRelshp1 | m_RsFactNbCntPartyRelshp1 | Advanced | Sridevi
32 | edm_processed_nb | NB - Contract Party Relationship | Proj_nb | PzFactNbCntPartyRelshp2 | m_RsFactNbCntPartyRelshp2 | Advanced | Rushil
33 | edm_processed_nb | NB - Contract Party Relationship | Proj_nb | PzFactNbCntPartyRelshpCDC | m_RsFactNbCntPartyRelshpCDC | StandardPDO | Sridevi
34 | edm_processed_nb | NB - Contract Activity | Proj_nb | PzFactNbContractActivity | m_RsFactNbContractActivity | Advanced | Sridevi
35 | edm_processed_nb | NB - Contract Change | Proj_nb | PzFactNbContractChange | m_RsFactNbContractChange | Advanced | Kuldeep
36 | edm_processed_nb | NB - MIB | Proj_nb | PzFactNbMIB_1 | m_RsFactNbMIB_1 | Advanced | Krishna
37 | edm_processed_nb | NB - MIB | Proj_nb | PzFactNbMIB_2 | m_RsFactNbMIB_2 | Advanced | Krishna
38 | edm_processed_nb | NB - Contract Alert | Proj_nb | PzFactNbUwContractAlert | m_RsFactNbUwContractAlert | StandardPDO | Govind
39 | edm_processed_nb | NB - Contract Alert | Proj_nb | PzFactNbUwContractAlertcdc | m_RsFactNbUwContractAlertcdc | StandardPDO | Sakshi
40 | edm_processed_nb | NB - MIB Underwriting | Proj_nb | PzFactNbUwMIB | m_RsFactNbUwMIB | Advanced | Shreya
41 | edm_processed_nb | NB - Agent Statement | Proj_nb | SeqPzNbAgentStmt_Master |  | Taskflow
42 | edm_processed_nb | NB - Contract Activity | Proj_nb | SeqPzNbCaseRemarkPvtMaster |  | Taskflow
43 | edm_processed_nb | NB - Contract Party Relationship | Proj_nb | SeqPzNbPart1Master |  | Taskflow
44 | edm_processed_nb | NB - Contract Alert | Proj_nb | SeqPzNbSubAreaPvtSet1Master |  | Taskflow
45 | edm_processed_nb | NB - Contract Change | Proj_nb | SeqPzNbSubAreaSet1Master |  | Taskflow
46 | edm_processed_nb | NB - Agent Statement | Proj_nb | SSeqPzNbAgentStmt |  | Taskflow
47 | edm_processed_nb | NB - Contract Activity | Proj_nb | SSeqPzNbCaseRemarkPvt |  | Taskflow
48 | edm_processed_nb | NB - Contract Party Relationship | Proj_nb | SSeqPzNbPart1 |  | Taskflow
49 | edm_processed_nb | NB - Contract Alert | Proj_nb | SSeqPzNbSubAreaPvtSet1 |  | Taskflow
50 | edm_processed_nb | NB - Contract Change | Proj_nb | SSeqPzNbSubAreaSet1 |  | Taskflow
52 | edm_processed_nb | NB - Contract Party Relationship | Proj_nb | PzBrgNbCntPartyInsStmnt | m_RsBrgNbCntPartyInsStmnt |  | Rushil

## Sprint 12
S No | Project | Subject Area | BusinessProject | Job | Mapping | IDMCJobType | Assigned | Sprint Planning | Dev + UT | QA Recon | QA Validation | Stage | Prod | Prod Sign Off | UAT Sign Off | ETA | Remarks | Peer Review | Status
1 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbCntDclnReason |  | Advanced
2 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbCntExtraPremRate |  | Advanced
3 | edm_processed_nb | NB - Part1 | Proj_nb | PzBrgNbCntInsuredBnft |  | Advanced
4 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbCntOriginalOffer |  | Advanced
5 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbCntReinOffer |  | Advanced
6 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbCntUwRiskClass |  | Advanced
7 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbContractAmendment |  | Advanced
8 | edm_processed_nb | NB - Part1 | Proj_nb | PzBrgNbContractBeneficiary |  | Advanced
9 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbContractCorr |  | Advanced
10 | edm_processed_nb | NB - Part1 | Proj_nb | PzBrgNbContractEventSts |  | Advanced
11 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbContractExclusion |  | StandardPDO
12 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbContractimpairment |  | Advanced
13 | edm_processed_nb | NB - Part1 | Proj_nb | PzBrgNbInsuredOtherPolicy |  | Advanced
14 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbUwCntInsRating |  | Advanced
15 | edm_processed_nb | NB- Case Remark | Proj_nb | PzFactNbCaseRemark1 |  | StandardPDO
16 | edm_processed_nb | NB- Case Remark | Proj_nb | PzFactNbCaseRemark2 |  | StandardPDO
17 | edm_processed_nb | NB- Case Remark | Proj_nb | PzFactNbCaseRemark2Src |  | StandardPDO
18 | edm_processed_nb | NB- Case Remark | Proj_nb | PzFactNbCaseRemark2Union1Src |  | StandardPDO
19 | edm_processed_nb | NB- Case Remark | Proj_nb | PzFactNbCaseRemark2Union2Src |  | StandardPDO
20 | edm_processed_nb | NB- Case Remark | Proj_nb | PzFactNbCaseRemark2Union3Src |  | StandardPDO
21 | edm_processed_nb | NB- Case Remark | Proj_nb | PzFactNbCaseRemark3 |  | Advanced
22 | edm_processed_nb | NB- Case Remark | Proj_nb | PzFactNbCaseRemarkcdc |  | StandardPDO
23 | edm_processed_nb | NB - Part1 | Proj_nb | PzFactNbContractPart1 |  | Advanced
24 | edm_processed_nb | NB - Part1 | Proj_nb | PzFactNbContractPart1cdc |  | StandardPDO
25 | edm_processed_nb | NB - Part1 | Proj_nb | PzFactNbContractPart2 |  | Advanced
26 | edm_processed_nb |  | Proj_nb | PzFactNbContractQcReply1 |  | StandardPDO
27 | edm_processed_nb |  | Proj_nb | PzFactNbContractQcReply2 |  | Advanced
28 | edm_processed_nb |  | Proj_nb | PzFactNbContractQcReplyCDC |  | StandardPDO
29 | edm_processed_nb | NB - Part2-Medication | Proj_nb | PzFactNbMedication_1 |  | Advanced
30 | edm_processed_nb | NB - Part2-Medication | Proj_nb | PzFactNbMedication_2 |  | Advanced
31 | edm_processed_nb | NB - Part2-Medication | Proj_nb | PzFactNbMedication_3 |  | Advanced
32 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealth |  | Advanced
33 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealth204Trans |  | Advanced
34 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealth209Trans |  | Advanced
35 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealthTrans1 |  | StandardPDO
36 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealthTrans2 |  | Advanced
37 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealthTrans3 |  | StandardPDO
38 | edm_processed_nb | NB - Prescription | Proj_nb | PzFactNbPrescrDrugFill1 |  | StandardPDO
39 | edm_processed_nb | NB - Prescription | Proj_nb | PzFactNbPrescrDrugFill2 |  | StandardPDO
40 | edm_processed_nb | NB - Prescription | Proj_nb | PzFactNbPrescrDrugFill3 |  | StandardPDO
41 | edm_processed_nb | NB - Prescription | Proj_nb | PzFactNbPrescrDrugFill4 |  | StandardPDO
42 | edm_processed_nb | NB - Prescription | Proj_nb | PzFactNbPrescrDrugFillCDC |  | StandardPDO
43 | edm_processed_nb | NB - Prescription | Proj_nb | PzFactNbPrescrDrugFillSrc |  | StandardPDO
44 | edm_processed_nb | NB - Prescription ICD | Proj_nb | PzFactNbPrescriptionIcd1 |  | Advanced
45 | edm_processed_nb | NB - Prescription ICD | Proj_nb | PzFactNbPrescriptionIcd2 |  | StandardPDO
46 | edm_processed_nb | NB - Prescription ICD | Proj_nb | PzFactNbPrescriptionIcdCDC |  | StandardPDO
47 | edm_processed_nb | NB - Scheduled Work | Proj_nb | PzFactNbScheduledWork1 |  | StandardPDO
48 | edm_processed_nb | NB - Scheduled Work | Proj_nb | PzFactNbScheduledWork2 |  | Advanced
49 | edm_processed_nb | NB - Scheduled Work | Proj_nb | PzFactNbScheduledWorkArchivalProcess |  | StandardPDO
50 | edm_processed_nb | NB - Scheduled Work | Proj_nb | PzFactNbScheduledWorkCDC |  | Advanced
51 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzFactNbUwCntInsureBnft1 |  | StandardPDO
52 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzFactNbUwCntInsureBnft2 |  | Advanced
53 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzFactNbUwCntInsureBnft3 |  | Advanced
54 | edm_processed_nb |  | Proj_nb | SeqPzNbCommonStgTblCreationMaster |  | Taskflow
55 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | SeqPzNbContractInsuredBenefitMaster |  | Taskflow
56 | edm_processed_nb | NB - Person General Health | Proj_nb | SeqPzNbSubAreaPvtSet3Master |  | Taskflow
57 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | SSeqPzNbContractInsuredBenefit |  | Taskflow
58 | edm_processed_nb | NB - Person General Health | Proj_nb | SSeqPzNbSubAreaPvtSet3 |  | Taskflow
59 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealthCntr1
60 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealthCntr2
61 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealthCntr3
62 | edm_processed_nb | NB - Prescription ICD | Proj_nb | PzDS_FactNbPrescriptionIcd
63 | edm_processed_nb |  | Proj_nb | PzBrgNbCntBnftPartyInsStmnt
64 | edm_processed_nb |  | Proj_nb | SeqPzNbAgentStmtSet1_Master
65 | edm_processed_nb |  | Proj_nb | SSeqPzNbAgentStmtSet1

## Blocker's reso Confirmation
edm_processed_agency | m_RsFamilyBusinessLoad | Sakshi | Target Table ext_lake_oracle_orap10_ai0101.DH_AGENT_CASE_FAMILY_BUZ need to create in this schema as in DS it using Oracle as Target (asked to ignore that Peek target so took Oracle as Target)
adm | m_AgentContactFeeds_IncreLoad | Govind | Target Table AgencyDashboard_AgentContact_IAG_20240302102949 is not available on schema insurance_adm( in DS it's Sequential File)

## Team Velocity
Resource | 2024-05-09
Sridevi | 2days meduim with UT and complex 4 with UT
Smita | 2 days meduim with UT and complex 4 with UT | Mapping cleanup - RTR, JNR removal, Ref,Src rename,additional validation checkpoints, UT revised format was after the earlier estimate hence revised estimate is higher that before.
Rushil | 1 days meduim with UT and 3 complex with UT

## Blocker's Sheet
S.No | Folder Name | Mapping | Owner | Blocker Requested Date | Blocker updated Date | Blocker details | Schema | Table name | Resolved/Unresolved | Confirmed by Project Team
1 | edm_processed_agency | m_RsOpsEmBatchSeqRunDetailsLoad | Smita | 27-2-24 |  | Target connection and object - FF or table/ need clarification. DataStage has parameterized FF name whereas IDMC converted mapping has a table name which is present in Aurora connection with 2 fields extra and field names do not match with incoming fields Aurora Source - adv prop - fetch size to confirm
6 | edm_processed_agency | m_RsEMoneyEmd08BeneficiaryDataload | Govind | 2024-02-27 |  | SRC_hdfsExtractUniqueContract1(conversion brings as FF, we need to check with Rachit)DS File name ExtractUniqueContractData.txt
7 | edm_processed_agency | m_RsEMoneyEmd04ClientDataLoad | Yogeshwar | 2024-02-27 |  | Data Preview failed. Please verify connection, formatting options and object details. ([error [!Invalid Formatting options/Format type. Error: !No rows present in the selected file!!]])
8 | Compliance | m_RsEbossFinraAddress_lar2 | Yogeshwar | 2024-02-27 |  | Data Preview failed. Please verify connection, formatting options and object details. ([error [!Invalid Formatting options/Format type. Error: !No rows present in the selected file!!]])
9 | edm_processed_agency | m_RsEMoneyEmd01LifeDataPrep2 | Yogeshwar | 2024-02-27 |  | Data Preview failed. Please verify connection, formatting options and object details. ([error [!Invalid Formatting options/Format type. Error: !No rows present in the selected file!!]])
10 | edm_processed_agency | m_RsEMoneyEmd01DataLoad | Rajat | 2024-02-27 |  | Target Table does not exit. PzEmoneyInvestmentEmd01 PzEmoneyCalcemd01DataLoad PzEmoneyLifeEmd01 PzEmoneyLtcEmd01 PzEmoneyAnnuityEmd01 PzEmoneyOtherEmd01
11 | edm_processed_agency | m_RsEMoneyCalcExtractData | Sakshi | 2024-02-27 |  | 6 target table PzEmoneyCalcBAL,PzEmoneyCalcAnuity,PzEmoneyCalcemd01DataLoad,PzEmoneyCalcLyf2,PzEmoneyCalcLyf3,PzEmoneyCalcLyf4 not present in Schema insurance_emoney_agency_conv
12 | edm_processed_agency | m_RsEMoneyEmd01LifeDataPrep1 | Sakshi | 2024-02-27 |  | SRC_Copy_of_hdfsLifeContractData having FF in DS LdLifeContractData.txt not able to preview and check formating option(need to check with Rachit), Target Table Lifeextract01 not present in Schema insurance_emoney_agency_conv
13 | edm_processed_agency | m_RsEMoneyEmd03AnnuitiesDataPrep | Sakshi | 2024-02-27 |  | "SRC_hdfsAnnutiyContractData having FF in DS LdAnnutyContractData.txt not able to preview and check formating option(need to check with Rachit), Target Table PzEmoneyAnnuityEmd03 not present in Schema insurance_emoney_agency_conv"
14 | edm_processed_agency | m_RsEMoneyEmd02Marketersdataload | Kamlendu | 2024-02-27 |  | Source Table: Insurance_emoney_agency_conv.ExtractContractMarketerRel not present inDB | Insurance_emoney_agency_conv. | ExtractContractMarketerRel
15 | edm_processed_agency | m_RsEmExtractKeyColumns | Harsh | 2024-02-27 |  | tgt tables : MissingMarketer ExtractUniqueContractData ExtractContractMarketerRel ExtractUniqueClient ExtractContractClientRel needs to be created in db
16 | edm_processed_agency | m_RsEMoneyEmd01AnnuPayoutSeqEQ00 | Krishna | 2024-02-27 |  | Table missing : src - LdAnnutyContractData tgt -PzEmoneyAnnuitiesPayoutPart2
17 | edm_processed_agency | m_RsEMoneyEmd03LifeDataPrep | Krishna | 2024-02-27 |  | Table missing : src - LdLifeContractData tgt -emd03_Lifeextract03
18 | edm_processed_agency | m_RsEMoneyEmd07ClientInsuredrDataLoad | Krishna | 2024-02-27 |  | Table missing : src - ExtractContractClientRe
19 | edm_processed_agency | m_RsEMoneyEmd01AnnuitiesPayoutFinal | Kuldeep | 2024-02-27 |  | Source and Target Table does not exit. Source Table-PzEmoEmoneyAnnuitiesPayoutPart1 Source Table-PzEmoEmoneyAnnuitiesPayoutPart2 Target Table-PzEmoneyAnEmoneyAnnuitiesPayout
20 | edm_processed_agency | m_RsEMoneyEmd03InvestmentDataPrep | Kuldeep | 2024-02-27 |  | Source and Target Table does not exit. Source Table-LdInvstContractData Target Table -PzEmoneyInvestmentEmd03
21 | edm_processed_agency | m_RsEMoneyEmd07HistTblLoad | Kuldeep | 2024-02-27 |  | Target Table does not exit. Target Table -EMoney_ClientInsuredData_EMD07_count Target Table -EMoney_ClientInsuredData_EMD07
22 | edm_processed_agency | m_RsEMoneyEmd01AnnuPayoutSeqNE00 | Harsh | 2024-02-27 |  | src table:LdAnnutyContractData tgt table :PzEmoneyAnnuitiesPayoutPart1 needs to be created in db
23 | edm_processed_agency | m_RsEMoneyEmd01InvestmentDataPrep | Harsh | 2024-02-27 |  | Src table :LdInvstContractData PzEmoneyCalcBAL and tgt table:PzEmoneyInvestmentEmd01 needs to be created in db
24 | edm_processed_agency | m_RsEMoneyEmd04HistTblLoad | Rajat | 2024-02-27 |  | Target Table does not exit. EMoney_ClientData_EMD04__Count EMoney_ClientData_EMD04
25 | edm_processed_agency | PzEMoneyEmd09HistTblLoad | Rajat | 2024-02-27 |  | Target Table does not exit. EMoney_ControlData_EMD09
26 | edm_processed_agency | m_RsEMoneyEmd01AnnuitiesDataPrep1 | Farajiya | 2024-02-27 |  | Source and Target Table does not exit. SRC_hdfsAnnutiyPayoutData>>PzEmoneyAnnuitiesPayout SRC_hdfsAnnutiyData>>LdAnnutyContractData TGT_hdfsAnnutiyemd01Data>>PzEmoneyAnnuitiesDataprep1
27 | edm_processed_agency | m_RsEMoneyEmd03DataLoad | Farajiya | 2024-02-27 |  | Source Table does not exit. SRC_hdfsLifeContractEmd03>>emd03_Lifeextract03 SRC_hdfsInvestmentemd03Data>>PzEmoneyInvestmentEmd03 SRC_hdfsAnuityemd01Data>>PzEmoneyAnnuityEmd03
28 | edm_processed_agency | m_RsEMoneyEmd05HistTblLoad | Farajiya | 2024-02-27 |  | Target Table does not exit.
30 | edm_processed_agency | m_RsEmExtractKeyColumns | Harsh | 2024-02-28 |  | acc_id column is not available in ACCOUNT table - Rachit is looking into it
33 | edm_processed_agency | m_RsEmailCampaignSrcExtrct2 | Smita | 2024-03-06 | 03/07/2024 and 03/08/2024 | SRC_fchdfsEmailCampaignSrcExtract1 - Source table does not exist. Schemaname.Table name : insurance_agency_conv.EmailCampaignSrcExtract1(created on 03/07/24) SRC_hiveRcrCpSmy - Source table does not exist : ext_lake_oracle_orau10_ai0101.rcr_cp_smy. Query error : error [error [Provided Custom query is invalid due to:[[Amazon](500310) Invalid operation: AwsClientException: AccessDeniedException from glue - Resource does not exist or requester is not authorized to access requested permissions.;]]]. 03/08/2024 - Post Client discussion, table available in schema insurance_agency. But in order to parameterize this schema in source query, have defined an InOut parameter 'jpSchemaName_agency' with default value as 'insurance_agency ' schema in mapping but we need verify that this InOut paramter will be included in the updated parameter file as well. TGT_fchdfsEmailCampaignSrcExtract2 - Target table does not exist.Schemaname.Table name : insurance_agency_conv.EmailCampaignSrcExtract2 (created on 03/07/24)
35 | edm_processed_agency | m_RsFamilyBusinessLoad | Sakshi | 2024-03-08 |  | Target Table ext_lake_oracle_orap10_ai0101.DH_AGENT_CASE_FAMILY_BUZ need to create in this schema as in DS it using Oracle as Target (asked to ignore that Peek target so took Oracle as Target)
36 | adm | m_AgentContactFeeds_IncreLoad | Govind | 2024-03-08 |  | Target Table AgencyDashboard_AgentContact_IAG_20240302102949 is not available on schema insurance_adm( in DS it's Sequential File)
37 | edm_processed_agency | m_EmailCampaignOutbound | Krishna | 2024-03-08
38 | adm | m_AgentContactFeeds_Initial | Rushil | 2024-03-08 |  | SRC_OraDimOrgUnit and SRC_OraDimMktr queries in datastage and idmc do not match and expression not converted properly

## Sprint1&2
Sprint | Mapping | Owner | Asset Status | UT Status
Sprint 1 | m_RsInvAumIWS | Yogeshwar | Complete
| m_RsInvAumNFS | Monika | Complete | Done
| m_RsInvNewInvestorDonnelly | Ashwin | Complete | Done
| m_RsInvAumDST | Ashwin | Complete | Done
Sprint 2 | m_RsEMoneyEmd01AnnuPayoutSeqNE00 | Harsh | Complete | Done
| m_RsEMoneyEmd01InvestmentDataPrep | Harsh | Complete | Done
| m_RsEMoneyEmd01LifeDataPrep4 | Ashwin | Complete | Done
| m_RsEMoneyEmd08HistTblLoad | Ashwin | Complete | Done
| m_RsEbossFinraAddress_lar1 | Ashwin | Complete | Done
| m_RsEmExtractKeyColumns | Harsh | Complete | Done
| m_RsEMoneyEmd01AnnuitiesPayoutFinal | Kuldeep | Complete | Done
| m_RsEMoneyEmd01AnnuPayoutSeqEQ00 | Krishna | Complete | Done
| m_RsEMoneyEmd01DataLoad | Rajat | Complete | Done
| m_RsEMoneyEmd03LifeDataPrep | Krishna | Complete | Done
| m_RsEMoneyEmd04HistTblLoad | Rajat | Complete | Done
| m_RsEMoneyEmd05HistTblLoad | Farajiya | Complete | Done
| m_RsEMoneyEmd07ClientInsuredrDataLoad | Krishna | Complete | Done
| m_RsEMoneyEmd07HistTblLoad | Kuldeep | Complete | Done
| m_RsEMoneyEmd09HistTblLoad | Rajat | Complete | Done
| m_RsEbossFinraAddress_lar2 | Monika | In progress
| m_RsEbossFinraAddress_lar3 | Kamlendu | In progress |  | MCT done without Data need to do UAT
Sprint 1
m_RsInvAumIWS
m_RsInvNewInvestorDonnelly
Sprint 2
m_RsEbossFinraAddress_lar2
m_RsEbossFinraAddress_lar3
m_RsEMoneyEmd08HistTblLoad
m_RsEMoneyEmd01InvestmentDataPrep