## Sheet2
Master Tracker Statuses
Yet to Start
In Progress
Complete
On Hold
Column Wise Update
Sprint Planning | Indicates Sprint N-1 planning, Backlog Grooming, sprint planning, prioritizing, etc
Dev + UT | Indicates Analysis, Dev, UT, Code Review, Peer Review, Dry Run in QA
QA Recon | Indicates testing and Recon on QA env by dev team, with PBC data
QA Validation | Indicates Test case creation, test case execution/Testing, capture results in PT, etc on QA env
Stage | Indicates Deployment on Stage env, test
Prod | Indicates deployment on prod env, validate (fix) deliverables on prod env by Datanutts
prod sign off | Indicates Testing by Virtusa QA Team includes 3 rounds of recon, testing, etc
Hypercare | Indicates defect fixing in prod by Datanutts
UAT | Indicates UAT Defect fixing by Datanutts
Others | All other necessary Documentation and prod readiness by Datanutts

## Business_Project_POC
Business_Project | POC Member's | Email Id
edm_processed_agency-E-Money | Suraj Sharma | suraj_sharma@newyorklife.com
edm_processed_agency-LAR | Habeebur Rahmana | habeebur_rahmana@newyorklife.com
edm_processed_agency-EmailCampaign | Suraj Sharma | suraj_sharma@newyorklife.com
edm_processed_agency-DataObjectives | Siddarth Doon | siddarth_doon@newyorklife.com
edm_processed_agency-Amp | Vinayakkaparatti Basavanneppa | vinayakkaparatti_basavanneppa@newyorklife.com
edm_processed_agency-FamilyBusiness | Siddarth Doon | siddarth_doon@newyorklife.com | Project | Chunk | Tables | Slot
edm_processed_agency-ADM-Qualtrics | Pavithra Velayutham | pavithra_velayutham@newyorklife.com | NB21 | c2 | 92 tables | First Slot
edm_processed_agency-Producer2.0-CandidateDaily | Navin kumar kurapati | navinkumar_kurapati@newyorklife.com |  | c3
edm_processed_agency-FINRA | Navin kumar kurapati | navinkumar_kurapati@newyorklife.com |  | c4
edm_processed_agency-AMS EPM feeds | Navin kumar kurapati | navinkumar_kurapati@newyorklife.com |  | c10
edm_processed_agency-AMS LDAP feeds | Navin kumar kurapati | navinkumar_kurapati@newyorklife.com | ALIP | C3 | 23 tables | Second Slot
edm_processed_party-PDMParty | Manoj (Onsite): (Virtusa employee) | manojjh@virtusa.com
edm_processed_party-PDMParty | Manoj (Onsite): (Virtusa employee) | Manoj_juttu_Hariharan1@newyorklife.com
edm_processed_party-PDMParty | Shobhikala (Offshore): (Virtusa employee) | shobikalap@virtusa.com
edm_processed_party-PDMParty | Shobhikala (Offshore): (Virtusa employee) | Shobikala_Palanivelu1@newyorklife.com
edm_processed_party-PDMParty | Chandra (Onsite): (He is a NYL employee) | chandrashekharreddy_siddireddygari@newyorklife.com
edm_proccessed_nb-Proj_nb | Partha Pratim Mandal | pamandal@virtusa.com

## NYL Sprint plan 16
Squad | Team | NAME | Current assignment | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-15 | Number of leaves | Capacity | Number of jobs planned | Completed Jobs | Spill over | Stretch goals | Story Point Available
Squad11 | Project | Monika Joshi | Wave 3 & 4 | 2024-07-02: Technical calls + Code Review+Sprint Test planning+Prod roll out |  | 10 | 10
Squad11 | QA | Ashwin Kumar | Wave 3 & 4 | 2024-07-02: Prod Recon support , Data objectives seqDataObjAum Prod support Producer 2.0 PzCandidateDailyView seqCandidateDailyView; 2024-07-04: QA recon Poliocy PzFactContractPrimaryProducer; 2024-07-09: QA recon Poliocy PzFactInvestAccountPrimaryProducer |  | 10 | 2
Squad12 | QA | Muni Sankar | Wave 3 & 4 | 2024-07-02: Prod suppot Family business, emoney seqMasterPzEmoney PzAnnuityFamilyBusinessExtract PzFamilyBusinessLoad PzLifeFamilyBusinessExtract seqFamilyBusiness; 2024-07-04: QA recon Policy PzFactContractPartyRoleDerv |  | 9 | 1
Squad11 | QA | Yogeshwar Kudal | Wave 3 & 4 | 2024-07-02: Prod recon support - AMP PzAmpCntClientMktrIns PzAmpCntClientMktrReportBusinessGrp PzAmpCntClientMktrReportCompensationGrp PzAmpFamilyBusinessNB21Extract PzAmpFamilyBusinessRPYExtract PzAmpMentorMenteeExtract PzTraditionalAmpFullExtract seqAmpGenerateBusinessReport seqAmpGenerateCompensationReport; 2024-07-04: QA recon Policy PzFactContractCmpntInsuredDerv PzFactCtcpInvestmentBaseActvt |  | 10 | 2 |  |  | 1
Squad12 | QA | Harsh Panchal | Wave 3 & 4 | 2024-07-02: Prod support ADM Qualtrics PzAgentContactFeeds_IncreLoad PzAgentContactFeeds_Initial PzRecruiterContactFeeds_IncreLoad PzRecruiterContactFeeds_Initial seqPzMasterADMQualtricsFeed_Incr seqPzMasterADMQualtricsFeed_Initial; 2024-07-04: QA Recon party PzDimAgentCandRecrtmtStg PzDimAgentCandidateLead PzFactProducerGeneralOfficeComp |  | 10 | 2 |  |  | 1
Squad11 | QA | Mayank Kurkerja | Wave 3 & 4 | 2024-07-02: QA Recon party PzLkpAgentCandRecrtmtStg; 2024-07-08: QA recon party PzFactProducerGroupMembership |  | 10 | 2 |  |  | 1
Squad11 | QA | Kiruthika Rajamohan | Wave 3 & 4 | 2024-07-02: QA recon party PzFactFmisCntProducerPremShare; 2024-07-05: QA recon party PzFactProducerRecruitment; 2024-07-10: QA recon Party PzFactProducerAddtionalExpense |  | 10 | 4
Squad11 | Dev(n-1) | Sourabh Sharma | Wave 3 & 4 | 2024-07-02: Dev PzFactPsyclePartyReportGenerate; 2024-07-05: Dev PzFactNbCntInsuredReqrCDC; 2024-07-10: Dev PzFactNbCntPartyRelshp2 |  | 10 | 3
Squad11 | Dev(n-1) | Nisha Pursani | Wave 3 & 4 | 2024-07-02: Dev PzDimPsycleSegment; 2024-07-05: Dev PzBrgNbAgentStmntAgent; 2024-07-10: Dev PzFactNbCntInsuredReqr1 |  | 10 | 3
Squad11 | Dev(n-1) | Shreya Jain | Wave 3 & 4 | 2024-07-02: Dev PzDimPsycleSegmentInitLd; 2024-07-05: Dev PzFactNbCntInsuredReqr; 2024-07-10: Dev PzBrgNbContractOldCnt; 2024-07-15: Leave | 1 | 9 | 3 |  |  | 1
Squad11 | QA | Farajiya Khan | Wave 3 & 4 | 2024-07-02: QA recon Policy PzFactContractLowestPackage; 2024-07-08: QA recon party PzFactClientCommunication |  | 10 | 2
Squad11 | QA | Kamlendu Sarkar | Wave 3 & 4 | 2024-07-02: QA recon party - PzFactAgentAvisoryCouncil; 2024-07-08: QA recon Party - PzFactClientSubscription |  | 10 | 2
Squad12 | QA | Rajat Singh | Wave 3 & 4 | 2024-07-02: QA recon Party PzFactBookOfBusiness; 2024-07-08: QA recon party PzDimProducerType |  | 10 | 2 |  |  | 1
Squad11 | QA | Nikhil | Wave 3 & 4 | 2024-07-02: QA recon party PzLkpProducerCompensation; 2024-07-08: QA recon party PzFactProducerAddtionalExpense |  | 10 | 2
Squad12 | QA | Ankit Singh | Wave 3 & 4 | 2024-07-02: Prod recon support - LDAP PzLdapVueFieldOfficeSpecInsUpdDel PzLdapVueFieldOfficeTeamFileCsv Prod recon support - EPM feeds PzLdapEPMFieldOfficeSpecInsUpdDel PzLdapEPMFieldOfficeTeamFileUnqorkCsv PzLdapEPMFieldOfficeTeamInsUpdDel; 2024-07-04: QA recon PzFactCntProducerSalesAnnuity; 2024-07-10: QA recon Party PzFactAgentCandidateEmployment | 1 | 9 | 2
Squad12 | Dev | Kamakshi | Wave 3 & 4 | 2024-07-02: Dev PzPsyclePartyPublMonthlyTableLoad; 2024-07-05: Dev PzFactNbUwContractAlert; 2024-07-10: Dev PzFactNbUwMIB; 2024-07-12: Dev PzBrgNbCntDclnReason |  | 10 | 4
Squad12 | Dev | Wasi | Wave 3 & 4 | 2024-07-02: Dev PzFactNbCntInsuredReqrSrcCntr1; 2024-07-05: Dev PzFactNbCntInsuredReqrSrcCntr3; 2024-07-10: Dev PzFactNbCntInsuredReqrSrcCntr3; 2024-07-12: Dev PzBrgNbCntInsuredBnft |  | 10 | 4 |  |  | 1
Squad12 | Dev | Krishna K | Wave 3 & 4 | 2024-07-02: Dev PzFactNbAgentStatementTrans2; 2024-07-05: Dev PzFactNbMIB_1; 2024-07-09: Dev PzFactNbMIB_2; 2024-07-11: Dev PzBrgNbAgentStmntOldCnt |  | 10 | 4 |  |  | 1
Squad12 | Dev | Sakshi T | Wave 3 & 4 | Dev PzFactPsyclePartyInitLd |  | Dev PzFactNbCntInsuredPegaTrans |  | Leave | Leave | Dev PzFactNbUwContractAlertcdc |  | Dev PzBrgNbCntPartyRoleRelship |  | 2 | 8 | 4
Squad12 | Dev | Kuldeep Sharma | Wave 3 & 4 | 2024-07-02: Dev PzPsyclePartyPublYearlyTableLoad; 2024-07-05: Dev PzFactNbAgentStatementTrans1; 2024-07-10: PzFactNbContractChange; 2024-07-12: Dev PzFactNbContractChange |  | 10 | 4
Squad12 | Dev | Govind Gaurav | Wave 3 & 4 | Dev PzFactAgentStaffRelation |  | Dev PzBrgNbCntExtraPremRate |  | Leave | Leave | Leave | Leave | Leave | Dev PzBrgNbCntExtraPremRate | 5 | 5 | 2 |  |  | 1
Squad12 | Dev | Smita Rasal | Wave 3 & 4 | 2024-07-02: Dev SeqPzPartyFactFmisMaster; 2024-07-05: SSeqPzPartyFactFmis; 2024-07-10: Dev SeqPzPartyFactMaster |  | 10 | 3
Squad12 | Dev | Sridevi Kommera | Wave 3 & 4 | Dev PzFactNbCntPartyRelshp1 | Leave | Leave | Leave | Dev PzFactNbCntPartyRelshp1 |  | Dev PzBrgNbAgentStmntAgent |  |  |  | 3 | 7 | 2
Squad12 | Dev | Rushil Patel | Wave 3 & 4 | 2024-07-02: Leave; 2024-07-03: Leave; 2024-07-04: Leave; 2024-07-05: Dev PzFactNbCntPartyRelshp2; 2024-07-10: Dev PzBrgNbCntPartyInsStmnt | 3 | 7 | 2
Squad11 | Dev | Subakartika | Wave 3 & 4 | [10 empty] | 10 | 0 | 0 | bar: 2024-07-02 to 2024-07-15
Total: | [13 empty] | 26 | 224 | 71 |  | 0 | 8

## Sprint_5
S No | Project | Business Project | Job | Mapping/Tf | Assigned To | Sprint Planning | Dev + UT | QA Recon | QA Validation | Stage | Prod | Prod Sign Off | UAT Sign Off | Remarks | Peer-Review Owner
1 | edm_processed_agency | DataObjectives | PzClientBrinkerAddr | m_RsClientBrinkerAddr | Muni | Complete | Complete | Complete | Completed | Completed | Completed |  |  | Mocked up the data in source and UAT Done. | Kuldeep
2 | edm_processed_agency | DataObjectives | PzClientBrinkerAgent | m_RsClientBrinkerAgent | Smita | Complete | Complete | Complete | Completed | Completed | Completed |  |  | Mocked up the data in source and UAT Done. | Rajat
3 | edm_processed_agency | DataObjectives | PzClientBrinkerInitial | m_RsClientBrinkerInitial | Sridevi | Complete | Complete | Complete | Completed | Completed | Completed |  |  | Mocked up the data in source and UAT Done,documentation in progress. Rachit needs to give confirmation for two extra columns in target table | Farajiya
4 | edm_processed_agency | DataObjectives | PzClientInitialL10 | m_RsClientInitialL10 | Harsh | Complete | Complete | Complete | Completed | Completed | Completed |  |  | Mocked up the data in source data and UAT Done. | Govind
5 | edm_processed_agency | DataObjectives | PzClientInvLkpRoleTranslation | m_RsClientInvLkpRoleTranslation | Sridevi | Complete | Complete | Complete | Completed | Completed | Completed |  |  | Mocked up the data in source and UAT Done. | Sakshi
6 | edm_processed_agency | DataObjectives | PzClientL10Addr | m_RsClientL10Addr | Farajiya | Complete | Complete | Complete | Completed | Completed | Completed |  |  | Mocked up the data in source and UAT Done. | Krishna
7 | edm_processed_agency | DataObjectives | PzClientL10Agent | m_RsClientL10Agent | Kamlendu | Complete | Complete | Complete | Completed | Completed | Completed |  |  | Mocked up the data in source and UAT Done. | Kuldeep
8 | edm_processed_agency | DataObjectives | PzClientL10BrinkerLoad | m_RsClientL10BrinkerLoad | Kuldeep | Complete | Complete | Complete | Completed | Completed | Completed |  |  | Mocked up the data in source and UAT Done. | Rajat
9 | edm_processed_agency | DataObjectives | PzClientOutboundFeed | m_RsClientOutboundFeed | Krishna | Complete | Complete | Complete | Completed | Completed | Completed |  |  | Mocked up the data in source and UAT Done. | Farajiya
10 | edm_processed_agency | DataObjectives | PzInvAum529 | m_RsInvAum529 | Yogeshwar | Complete | Complete | Complete | Completed | Completed | Completed |  |  |  | Govind
11 | edm_processed_agency | DataObjectives | PzInvAumAGENT | m_RsInvAumAGENT | Rajat | Complete | Complete | Complete | Completed | Completed | Completed |  |  | Mocked up the data in source and UAT Done. | Sakshi
12 | edm_processed_agency | DataObjectives | PzInvAumDST | m_RsInvAumDST | Kiruthika | Complete | Complete | Complete | Completed | Completed | Completed |  |  |  | Krishna
13 | edm_processed_agency | DataObjectives | PzInvAumIWS | m_RsInvAumIWS | Sourabh | Complete | Complete | Complete | Completed | Completed | Completed |  |  | UT pending and has no data for testing | Harsh
14 | edm_processed_agency | DataObjectives | PzInvAumNFS | m_RsInvAumNFS | Shreya / Farajiya | Complete | Complete | Complete | Completed | Completed | Completed |  |  | Mocked up the data in source and UAT Done. | Rajat
15 | edm_processed_agency | DataObjectives | PzInvHouseholdLdap | m_RsInvHouseholdLdap | Nisha | Complete | Complete | Complete | Completed | Completed | Completed |  |  |  | Farajiya
16 | edm_processed_agency | DataObjectives | PzInvNewInvestorDonnelly | m_RsInvNewInvestorDonnelly | Govind | Complete | Complete | Complete | Completed | Completed | Completed |  |  |  | Harsh
17 | edm_processed_agency | DataObjectives | seqDataObjAum | tf_seqDataObjAum | Muni | Complete | Complete | Complete | Completed | Completed | Completed
18 | edm_processed_agency | DataObjectives | seqDataObjBrinkerInitialfeed | tf_seqDataObjBrinkerInitialfeed | Muni | Complete | Complete | Complete | Completed | Completed | Completed
19 | edm_processed_agency | DataObjectives | seqDataObjClientfeed | tf_seqDataObjClientfeed | Muni | Complete | Complete | Complete | Completed | Completed | Completed |  |  | Validated , need to run with default values if no data in the tables
20 | edm_processed_agency | DataObjectives | seqInvAum529 | tf_seqInvAum529 | Muni | Complete | Complete | Complete | Completed | Completed | Completed |  |  | failed with Permisson issue - Operation failed: error [error [An error occured while executing the custom query: [select COALESCE(max(max(edm_file_last_received_date)::varchar),'19000101')::VARCHAR(2000) jpoutValue from ext_lake_int_agency_lookup.inv_aum where edm_src_cd='529plans'] due to: [[Amazon](500310) Invalid operation: AwsClientException: AccessDeniedException from glue - Resource does not exist or requester is not authorized to access requested permissions.;]. Please check the custom query ]].
21 | edm_processed_agency | DataObjectives | seqInvAumAGENT | tf_seqInvAumAGENT | Muni | Complete | Complete | Complete | Completed | Completed | Completed
22 | edm_processed_agency | DataObjectives | seqInvAumDST | tf_seqInvAumDST | Muni | Complete | Complete | Complete | Completed | Completed | Completed
23 | edm_processed_agency | DataObjectives | seqInvAumIWS | tf_seqInvAumIWS | Muni | Complete | Complete | Complete | Completed | Completed | Completed
24 | edm_processed_agency | DataObjectives | seqInvAumNFS | tf_seqInvAumNFS | Muni | Complete | Complete | Complete | Completed | Completed | Completed
25 | edm_processed_agency | DataObjectives | seqInvHouseHoldLdap | tf_seqInvHouseHoldLdap | Muni | Complete | Complete | Complete | Completed | Completed | Completed
26 | edm_processed_agency | DataObjectives | SeqInvNewInvestorDonnelly | tf_seqInvNewInvestorDonnelly | Muni | Complete | Complete | Complete | Completed | Completed | Completed |  |  | MCT Query issue

## Sprint_6
S No | Project | BusinessProject | Job Name(OnPrem) | Mapping/Tf | Assigned To | Sprint Planning | Dev + UT | QA Recon | QA Validation | Stage | Prod | Prod Sign Off | UAT Sign Off | Remarks | Peer-Review Owner | Status | DS Target Load
1 | edm_processed_agency | eMoney | OpsEmBatchJobRunDetailsLoad | m_RsEmBatchJobRunDetailsLoad | Krishna | Complete | on hold | [6 empty] | Conversion not pulled all sources, need to check with DataSwitch team/xml parser Need to check rachit on logic for Heirachy parser 03/05 - need a sample XML file name and directory - file need be available on agent
2 | edm_processed_agency | eMoney | OpsEmBatchSeqRunDetailsLoad | m_RsOpsEmBatchSeqRunDetailsLoad | Harsh | Complete | on hold | [6 empty] | Source and Target is Aurora need confirmation from suraj
3 | edm_processed_agency | eMoney | PzEmContractProductSplit | m_RsEmContractProductSplit | Sridevi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Dry Run Completed, UT complete,document in progress | Krishna | Done
4 | edm_processed_agency | eMoney | PzEmExtractKeyColumns | m_RsEmExtractKeyColumns | Harsh | Complete | Complete | Complete | Complete | Complete | Complete |  |  | acc_id column is not available in ACCOUNT table | Rajat | Done
5 | edm_processed_agency | eMoney | PzEMoneyCalcExtractData | m_RsEMoneyCalcExtractData | Sakshi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with data UT Complete | Yogeshwar | Done
6 | edm_processed_agency | eMoney | PzEMoneyEmd01AnnuitiesDataPrep1 | m_RsEMoneyEmd01AnnuitiesDataPrep1 | Farajiya | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with Data, need to prepare UT doc - Rushil - UT Completed | Rajat | Done
7 | edm_processed_agency | eMoney | PzEMoneyEmd01AnnuitiesDataPrep2 | m_RsEMoneyEmd01AnnuitiesDataPrep2 | Kamlendu | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked up the data in source and UAT Done. | Farajiya | Done
8 | edm_processed_agency | eMoney | PzEMoneyEmd01AnnuitiesPayoutFinal | m_RsEMoneyEmd01AnnuitiesPayoutFinal | Kuldeep | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked up the data in source and UAT Done. | Krishna | Done
9 | edm_processed_agency | eMoney | PzEMoneyEmd01AnnuPayoutSeqEQ00 | m_RsEMoneyEmd01AnnuPayoutSeqEQ00 | Krishna | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Dry run completed need to tested with data | Sridevi | Done
10 | edm_processed_agency | eMoney | PzEMoneyEmd01AnnuPayoutSeqNE00 | m_RsEMoneyEmd01AnnuPayoutSeqNE00 | Harsh | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Ran with dummy data enterd using hardcoded select query | Smita | Done
11 | edm_processed_agency | eMoney | PzEMoneyEmd01DataLoad | m_RsEMoneyEmd01DataLoad | Rajat | Complete | Complete | Complete | Complete | Complete | Complete |  |  | UT Done | Rushil | Done
12 | edm_processed_agency | eMoney | PzEMoneyEmd01HistTblLoad | m_RsEMoneyEmd01HistTblLoad | Smita | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success without data, UT completed | Govind | Done
13 | edm_processed_agency | eMoney | PzEMoneyEmd01InvestmentDataPrep | m_RsEMoneyEmd01InvestmentDataPrep | Harsh | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Ran with dummy data enterd using hardcoded select query | Sakshi | Done
14 | edm_processed_agency | eMoney | PzEMoneyEmd01LifeDataPrep1 | m_RsEMoneyEmd01LifeDataPrep1 | Sakshi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with Data UT Completed with Mocked up Data | Rajat | Done
15 | edm_processed_agency | eMoney | PzEMoneyEmd01LifeDataPrep2 | m_RsEMoneyEmd01LifeDataPrep2 | Yogeshwar | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Dry run completed - Rushil - UT Completed | Krishna | Done
16 | edm_processed_agency | eMoney | PzEMoneyEmd01LifeDataPrep3 | m_RsEMoneyEmd01LifeDataPrep3 | Govind | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with data, UT Complete | Yogeshwar | Done
17 | edm_processed_agency | eMoney | PzEMoneyEmd01LifeDataPrep4 | m_RsEMoneyEmd01LifeDataPrep4 |  | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | Rajat | Done
18 | edm_processed_agency | eMoney | PzEMoneyEmd01LtcDataPrep | m_RsEMoneyEmd01LtcDataPrep | Rushil | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with data, UT Complete | Farajiya | Done
19 | edm_processed_agency | eMoney | PzEMoneyEmd01OtherDataPrep | m_RsEMoneyEmd01OtherDataPrep | Smita | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with data, UT completed | Krishna | Done
20 | edm_processed_agency | eMoney | PzEMoneyEmd02HistTblLoad | m_RsEMoneyEmd02HistTblLoad | Kamlendu | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked up the data in source and UAT Done. | Sridevi | Done
21 | edm_processed_agency | eMoney | PzEMoneyEmd02Marketersdataload | m_RsEMoneyEmd02Marketersdataload | Kamlendu | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked up the data in source and UAT Done. | Smita | Done
22 | edm_processed_agency | eMoney | PzEMoneyEmd03AnnuitiesDataPrep | m_RsEMoneyEmd03AnnuitiesDataPrep | Sakshi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success Without Data UT Completed with Mocked up Data | Rushil | Done
23 | edm_processed_agency | eMoney | PzEMoneyEmd03DataLoad | m_RsEMoneyEmd03DataLoad | Farajiya | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked up the data in source and UAT Done. | Govind | Done
24 | edm_processed_agency | eMoney | PzEMoneyEmd03HistTblLoad | m_RsEMoneyEmd03HistTblLoad | Kamlendu | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked up the data in source and UAT Done. | Sakshi | Done
25 | edm_processed_agency | eMoney | PzEMoneyEmd03InvestmentDataPrep | m_RsEMoneyEmd03InvestmentDataPrep | Kuldeep | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with Data | Sridevi
26 | edm_processed_agency | eMoney | PzEMoneyEmd03LifeDataPrep | m_RsEMoneyEmd03LifeDataPrep | Krishna | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Dry run completed need to tested with data | Kamlendu | Done
27 | edm_processed_agency | eMoney | PzEMoneyEmd04ClientDataLoad | m_RsEMoneyEmd04ClientDataLoad | Yogeshwar | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Completed with Data, UT completed | Kamlendu | Done
28 | edm_processed_agency | eMoney | PzEMoneyEmd04HistTblLoad | m_RsEMoneyEmd04HistTblLoad | Rajat | Complete | Complete | Complete | Complete | Complete | Complete |  |  | UT Done | Farajiya | Done
29 | edm_processed_agency | eMoney | PzEMoneyEmd05ClientOwnerDataLoad | m_RsEMoneyEmd05ClientOwnerDataLoad | Sridevi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Dry Run Completed, UT complete,document done | Yogeshwar | Done
30 | edm_processed_agency | eMoney | PzEMoneyEmd05HistTblLoad | m_RsEMoneyEmd05HistTblLoad | Farajiya | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked up the data in source and UT Completed. | Kamlendu | Done
31 | m_RsEbossFinraAddress_lar1 | eMoney | PzEMoneyEmd07ClientInsuredrDataLoad | m_RsEMoneyEmd07ClientInsuredrDataLoad | Krishna | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Dry run completed need to tested with data | Sridevi | Done
32 | edm_processed_agency | eMoney | PzEMoneyEmd07HistTblLoad | m_RsEMoneyEmd07HistTblLoad | Kuldeep | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked up the data in source and UAT Done. | Smita | Done
33 | edm_processed_agency | eMoney | PzEMoneyEmd08BeneficiaryDataload | m_RsEMoneyEmd08BeneficiaryDataload | Govind | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with data, UT Complete | Rushil | Done
34 | edm_processed_agency | eMoney | PzEMoneyEmd08HistTblLoad | m_RsEMoneyEmd08HistTblLoad |  | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | Rushil | Done
35 | edm_processed_agency | eMoney | PzEMoneyEmd09HistTblLoad | m_RsEMoneyEmd09HistTblLoad | Rajat | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mocked Up the data/UT Done | Yogeshwar | Done
36 | edm_processed_agency | eMoney | seqMasterPzEmoney | tf_seqMasterPzEmoney | Harsh | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mapping on hold dependency
37 | Compliance | LAR | PzEbossFinraAddress_lar1 | m_RsEbossFinraAddress_lar1 | Ashwin | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | Smita | Done
38 | Compliance | LAR | PzEbossFinraAddress_lar2 | m_RsEbossFinraAddress_lar2 | Yogeshwar | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | Harsh/Krishna | Done
39 | Compliance | LAR | PzEbossFinraAddress_lar3 | m_RsEbossFinraAddress_lar3 | Harsh | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | Sridevi | Done
40 | Compliance | LAR | seqMasterFinraAddressEboss_lar | tf_seqMasterFinraAddressEboss_lar | Yogeshwar | Complete | Complete | Complete | Complete | Complete | Complete
41 | Compliance | LAR | SseqFinraAddressEboss_lar | tf_SseqFinraAddressEboss_lar | Yogeshwar | Complete | Complete | Complete | Complete | Complete | Complete

## Sprint_8
S No | Project | Business Project | Job | Mapping | Assigned To | Sprint Planning | Dev + UT | QA Recon | QA Validation | Stage | Prod | Prod Sign Off | UAT Sign Off | Remarks | Peer Review | Status
1 | edm_processed_agency | Producer2.0-CandidateDaily | PzCandidateDailyView | m_RsCandidateDailyView | Kuldeep | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success without Data,source table does not have any Data | Sridevi | Done
2 | edm_processed_agency | Producer2.0-CandidateDaily | seqCandidateDailyView | TF_seqCandidateDailyView | Kuldeep | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Complated without Ops job confirmation is pending.
3 | edm_processed_agency | FINRA | PzAmsFinraInfoLoad | m_RsAmsFinraInfoLoad | Kamlendu | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Completed with Data & UT done | Smita | Done
4 | edm_processed_agency | FINRA | seqAmsFinraInfoLoad | TF_seqAmsFinraInfoLoad | Kamlendu/Kuldeep | Complete | Complete | Complete | Complete | Complete | Complete
5 | edm_processed_agency | AMS EPM feeds | PzLdapEPMFieldOfficeSpecInsUpdDel | m_RsLdapEPMFieldOfficeSpecInsUpdDel | Sakshi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Completed with Data UT done ,CDC-logic | Kuldeep
6 | edm_processed_agency | AMS EPM feeds | PzLdapEPMFieldOfficeTeamFileUnqorkCsv | m_RsLdapEPMFieldOfficeTeamFileUnqorkCsv | Govind | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success without Data, UT Done | Rajat | Done
7 | edm_processed_agency | AMS EPM feeds | PzLdapEPMFieldOfficeTeamInsUpdDel | m_RsLdapEPMFieldOfficeTeamInsUpdDel | Krishna | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mapping is validated and CDC-logic ,need to confirm with Saranya | Kamlendu
8 | edm_processed_agency | AMS EPM feeds | PzLdapEPMStandardUserInsUpdDel | m_RSLdapEPMStandardUserInsUpdDel | Rajat | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | Farajiya | Done
9 | edm_processed_agency | AMS EPM feeds | seqLdapVueFileUnqorkFeed | tf_seqLdapVueFileUnqorkFeed | Krishna | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Tf is completed.Need confirmation one cmd which mct we need to use in idmc Ds CMD Task : "select max(edh_updated_batch_key) from #LdapHierarchyHiveDBConnectionString.$EDM_HUB_PZ_AGENCY_SCHEMA#.ldap_epm_field_office_team union select max(edh_created_batch_key) from #LdapHierarchyHiveDBConnectionString.$EDM_HUB_PZ_AGENCY_SCHEMA#.ldap_epm_field_office_team";
10 | edm_processed_agency | AMS LDAP feeds | PzLdapVueFieldOfficeSpecInsUpdDel | m_RsLdapVueFieldOfficeSpecInsUpdDel | Smita | Complete | Complete | Complete | Complete | Complete | Complete |  |  | CDC logic. MCT run success. UT Complete | Krishna | Done | 5/2/2024 - Cleaned up and revalidated as per revised validation document
11 | edm_processed_agency | AMS LDAP feeds | PzLdapVueFieldOfficeTeamFileCsv | m_RsLdapVueFieldOfficeTeamFileCsv | Sridevi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Source SRC_hiveLdapStandardUserSpec: has'Is_external' field datatype as integer but IDMC conversion pulled as string 100. Added Exp before tgt and fixed the logic. MCT success with no data. UT doc provided with no data in targets. Source tables does not have any data. 3/27/2024 MCT success with data. updated the UT document with data screen shots. | Harsh
12 | edm_processed_agency | AMS LDAP feeds | PzLdapVueFieldOfficeTeamFileUnqorkCsv | m_RsLdapVueFieldOfficeTeamFileUnqorkCsv |  | Complete |  | Descoped
13 | edm_processed_agency | AMS LDAP feeds | PzLdapVueFieldOfficeTeamInsUpdDel | m_RsLdapVueFieldOfficeTeamInsUpdDel | Smita | Complete | Complete | Complete | Complete | Complete | Complete |  |  | CDC logic. MCT run success.UT Complete | Sakshi | Done | 5/2/2024 - Cleaned up and revalidated as per revised validation document
14 | edm_processed_agency | AMS LDAP feeds | PzLdapVueStandardUserInsUpdDel | m_RsLdapVueStandardUserInsUpdDel | Sridevi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | CDC job. MCT success. Needto check with Harsh.UT done. | Govind | Done | 5/2/2024 - Cleaned up mapping revalidated as per the validation document.
15 | edm_processed_agency | AMS LDAP feeds | seqLdapVueFileFeed | tf_seqLdapVueFileFeed | Sakshi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Depends on mct_RsLdapVueFieldOfficeSpecInsUpdDel, mct_RsLdapVueFieldOfficeTeamInsUpdDel, mct_RsLdapVueStandardUserInsUpdDel, mct_RsLdapVueFieldOfficeTeamFileCsv

## EDM_Policy
Datastage2IDMC | [7 empty] | Standard Mappings |  |  |  | Advanced Mappings
Priority | Folder | Job | Mapping | Target Table | Mentor | Owner | Conversion status | Mapping Validation | MCT Run Status | Review Status | Unit Testing / All Flows | Switched to Advance | MCT Status | UT Documentation Status | DN Recon status | QA Deployment | MCT Status ( QA ) | Development Status | ETA | Peer Review
1.1 | Proj_policy | PzFactCntProducerSalesAnnuity | m_RsFactCntProducerSalesAnnuity m_RsFactCntProducerSalesAnnuity_adv | fact_cnt_producer_sales_annuity | Muni | Rushil | Yes | Validated | Success | Need to be peer reviewed Long running ,tuned as much as possible DS run time is 1hr 23 min in PROD ADV mapping runs for 1hr 5min pdm_conv.fact_cnt_producer_sales_annuity_max_prevtransdt need confirmation if this is truncate and load as no dates in table | UT Completed | Yes | Success |  |  |  |  | original mapping validation is done - need to be optimized tuned as much as possible, converted to adv standard mct ran with filter in source. Adv mct ran with full load |  | Smita | Paused, Muni will get back on optimization that was done using Union to replace all Joiners
1.1 | Proj_policy | PzFactContractMoodyBondYield | m_RsFactContractMoodyBondYield | Fact_Contract_Moody_Bond_Yield | Muni | Sridevi | Yes | Validated | Dry Run Completed | MCT success with no data. Completed | UT Completed | Yes | Success-old status Success |  |  |  |  | Advanced : success but standard mapping is not optimized |  | Rushil
1.1 | Proj_policy | PzFactContractOrgUnitRelation | m_RsFactContractOrgUnitRelation | fact_contract_org_unit_relation | Monika | Govind | Yes | Validated | Success | MCT Completed, UT Completed | UT Completed | [8 empty] | Sakshi | done
1.1 | Proj_policy | PzFactContractPayeeContact | m_RsFactContractPayeeContact | fact_contract_payee_contact | Muni | Smita | Yes | Validated | Success | MCT success. Standard mode session run completed in 2min 14sec.Hence as confirmed by Muni, did not switch to Advanced mode | UT Completed | No | [7 empty] | Sridevi | Sridevi completed peer reviewing of Adv asset and uploaded the document on 4/9/2024. Shailja assigned this to Sridevi. | done
1.1 | Proj_policy | PzFactContractPolicyNotes | m_RsFactContractPolicyNotes | fact_contract_policy_notes | Ashwin | Kamlendu | Yes | Validated | Success | MCT success with data and UT Completed | UT Completed | Yes | Success |  |  |  |  | Changes are not done suggested by Subu |  | Sakshi | done
1.1 | Proj_policy | PzFactContractReinsurance | m_RsFactContractReinsurance | fact_contract_reinsurance | Monika | Rajat | Yes | Validated | Success | Success, UT Completed | UT Completed | [8 empty] | Govind
1.1 | Proj_policy | PzFactContractTax | m_RsFactContractTax | fact_contract_tax | Yogeshwar | Rajat | Yes | Validated | Success | Success, UT Completed | UT Completed | Yes | Success | [6 empty] | Krishna
1.1 | Proj_policy | PzFactCtcpCpiSkip | m_RsFactCtcpCpiSkip | fact_ctcp_cpi_skip | Ashwin | Kuldeep | Yes | Validated | Success | Completed.UT Completed | UT Completed | [8 empty] | Govind
1.1 | Proj_policy | PzFactCtcpOppFinActivityHist | m_RsFactCtcpOppFinActivityHist | fact_ctcp_opp_fin_activty_hist | Ashwin | Farajiya | Yes | Validated | Dry Run Completed | 17 apr: Standard/Advanced mapping completed and UT completed. | UT Completed | Yes | Success | [6 empty] | Sridevi
1.1 | Proj_policy | PzFactFinInstitutionAcct | m_RsFactFinInstitutionAcct | fact_fin_institution_acct | Ashwin | Farajiya | Yes | Validated | Success | Completed.UT Completed | UT Completed | Yes | Success | [6 empty] | Rushil
1.1 | Proj_policy | PzFactInvestmentBaseShareValue | m_RsFactInvestmentBaseShareValue | fact_investment_base_share_value | Monika | Krishna | Yes | Validated | Success | Completed.UT Completed | UT Completed | Yes | [5 empty] | Advanced mapping is failed |  | Farajiya | 22 april: review completed
1.1 | Proj_policy | PzFactRelatedContracts | m_RsFactRelatedContracts | fact_related_contracts | Yogeshwar | Kamlendu | Yes | Validated | Success | MCT success with data and UT Completed | UT Completed | [8 empty] | Kuldeep
1.1 | Proj_policy | PzFactContractCmpntInsuredDerv | m_RsFactContractCmpntInsuredDerv | fact_contract_cmpnt_insured_derv | Yogeshwar | Krishna | Yes | Validated | old - Success/On Hold | 1.MCT ran Successfully.All UT scenario tested, except Full load taking time. Fullload is stopped because running continous more than 1 hrs(As suggest by mam) so i have tested 51000 records inserted for full load . Other UT scenrios working fine. 2.Switich to ad. but it will take 1 hour to complete the mct | UT Completed | Yes | Success | [6 empty] | Rajat
1.1 | Proj_policy | PzFactContractLowestPackage | m_RsFactContractLowestPackage | fact_contract_lowest_package | Harsh | Kuldeep | Yes | Validated | Success | Success, UT Completed | UT Completed | Yes | Success | [6 empty] | Rajat
1.1 | Proj_policy | PzFactContractLTC | m_RsFactContractLTC | fact_contract_ltc | Harsh | Smita | Yes | Validated | Success | Optimised 4 sources in to one combined query. Removed one JoinerKeyCols and RTR logic and optimized mapping. Session success - 17 min(Prod run is 14 min, hence as confirmed by Muni since delta is 3, hence no need to switch to Advance mode) | UT Completed | No | [7 empty] | Sridevi | Shailja has assigned this asset for peer review to Sridevi. Started on 4/9/2024.
1.1 - High | Proj_policy | PzFactContractPrimaryProducer | m_RsFactContractPrimaryProducer | fact_contract_primary_producer | Monika | Sridevi/Kamlendu | Yes | Validated | Success-old status | MCT success with data. Limited rows in source. Long running(47 minutes without limit) Assigned to Kamlendu after tuninig,good candidate for ADV mapping | UT Completed | [6 empty] | In standard mapping limited data in source query MCT got success.Long running(47 minutes) Note: SRT_sortproduceridnk ---- DS: producer_id_nk is also in sort keys under partition tab. Ascending ,Nulls last. But IDMC not. need to veriywith someone. EXP_xfmproduceridnk ----verify DS has a constraint keychange = 1 but IDMC not. ----- but it is not going forward. |  | Rushil
1.1 - High | Proj_policy | PzFactCtcpInvestmentBaseActvt | m_RsFactCtcpInvestmentBaseActvt | fact_ctcp_investment_base_actvt | Ashwin | Rushil | Yes | Validated | Success | Success | UT Completed | Yes | Success | [6 empty] | Smita | Completed on 04/30/2024 after mapping was revalidated as per Validation doc and suggestions from offshore
1.1 | Proj_policy | PzFactInvestAccountPrimaryProducer | m_RsFactInvestAccountPrimaryProducer | fact_invest_account_primary_producer | Harsh | Sakshi | Yes | Validated | Success | Success with data , STM Checked,UT completed | UT Completed | Yes | Success |  |  |  |  | Changes are not done suggested by Subu |  | Krishna
1.1 - High | Proj_policy | PzFactContractPartyRoleDerv | m_RsFactContractPartyRoleDerv | fact_contract_party_role_derv | Muni | Kamlendu | Yes | Validated | Success | Success with data , STM Checked,UT completed | UT Completed | Yes | Success | [6 empty] | Sridevi
`

## Sprint_7
S No | Project | Business Project | Job | Mapping | Assigned To | Sprint Planning | Dev + UT | QA Recon | QA Validation | Stage | Prod | Prod Sign Off | UAT Sign Off | Remarks | Peer Review | Status
1 | edm_processed_agency | Family Business | PzAnnuityFamilyBusinessExtract | m_RsAnnuityFamilyBusinessExtract | Kamlendu | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success without Data and UT complete | Govind | Done
2 | edm_processed_agency | Family Business | PzFamilyBusinessLoad | m_RsFamilyBusinessLoad | Sakshi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success Without Data and UT completed (Target Table Schema provided By Rachit On 8/3/2024 ) (asked to ignore that Peek target so took Oracle as Target) | Kamlendu | Done
3 | edm_processed_agency | Family Business | PzLifeFamilyBusinessExtract | m_RsLifeFamilyBusinessExtract | Rajat | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Fixed and Modified query on own/UT DOC uploaded | Smita | Done
4 | edm_processed_agency | Family Business | seqFamilyBusiness | tf_seqFamilyBusiness | Kamlendu | Complete | Complete | Complete | Complete | Complete | Complete
5 | adm | ADM-Qualtrics | PzAgentContactFeeds_IncreLoad | m_AgentContactFeeds_IncreLoad | Govind | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success without Data and UT complete | Kuldeep | Done
6 | adm | ADM-Qualtrics | PzAgentContactFeeds_Initial | m_AgentContactFeeds_Initial | Rushil | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | Muni
7 | adm | ADM-Qualtrics | PzRecruiterContactFeeds_IncreLoad | m_RecruiterContactFeeds_IncreLoad | Farajiya | Complete | Complete | Complete | Complete | Complete | Complete |  |  | CDC-logic ,need to confirm with Saranya ( to confirm if Dataswitch will fix it)--15/03- manually fixed Another issue is with src query-subquery is causing issue-Waiting for project team confirmation 22/03- Mapping ran without data, UT is done 26/03-Data is not loading to target because change code is not generated. It is coming as 0 and record is getting loaded into router default output group. Which is causing issue to load the data into target, Hence data is not loading to target in this scenario. | Rajat | Done
8 | adm | ADM-Qualtrics | PzRecruiterContactFeeds_Initial | m_RecruiterContactFeeds_Initial | Govind | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Success with Data, UT Done | Farajiya | Done
9 | adm | ADM-Qualtrics | seqPzMasterADMQualtricsFeed_Incr | tf_seqPzMasterADMQualtricsFeed_Incr | Govind | Complete | Complete | Complete | Complete | Complete | Complete |  |  | CMD regarding confirmation needed by project team | Sakshi
10 | adm | ADM-Qualtrics | seqPzMasterADMQualtricsFeed_Initial | tf_seqPzMasterADMQualtricsFeed_Initial | Sakshi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | CMD regarding confirmation needed by project team
11 | edm_processed_agency | AMP | PzAmpCntClientMktrIns | m_RsAmpCntClientMktrIns | Farajiya | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mct success with Data, UT document done. | Rajat | Done
12 | edm_processed_agency | AMP | PzAmpCntClientMktrReportBusinessGrp | m_RsAmpCntClientMktrReportBusinessGrp | Kuldeep | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | Krishna | Done
13 | edm_processed_agency | AMP | PzAmpCntClientMktrReportCompensationGrp | m_AmpCntClientMktrReportCompensationGrp | Sridevi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mapping and mct success without data. UT document done. Target preSQL provided. | Smita | Done
14 | edm_processed_agency | AMP | PzAmpFamilyBusinessNB21Extract | m_RsAmpFamilyBusinessNB21Extract | Smita | Complete | Complete | Complete | Complete | Complete | Complete |  |  | UT document complete with mock data. Session success without data | Sridevi | Done
15 | edm_processed_agency | AMP | PzAmpFamilyBusinessRPYExtract | m_RsAmpFamilyBusinessRPYExtract | Smita | Complete | Complete | Complete | Complete | Complete | Complete |  |  | UT document complete Session success with data | Sridevi | Done
16 | edm_processed_agency | AMP | PzAmpMentorMenteeExtract | m_RsAmpMentorMenteeExtract | Sridevi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Peer review - EXP_XfmDerived_OpsOutputStage - constraint logic seen in DS but not in IDMC / verify with offshore UT document done. Datastage has this target 'idms_mentor_mentee_dtls.txt' and load is overwrite file . mapping and mct got success with data. Datastage, IDMC target fields have datatype mismatch. idms_mentor_mentee_dtls: recrtr_agt_relatnsp_eff_dt: IDMC:str 10 but DS bigint, recrtr_agt_relatnsp_exprtn_dt: IDMC:str 10 but DS bigint, recrtr_shr_pct:IDMC:bigint but DS decimal 7,2 | Smita | Done
17 | edm_processed_agency | AMP | PzTraditionalAmpFullExtract | m_RsTraditionalAmpFullExtract | Rushil | Complete | Complete | Complete | Complete | Complete | Complete |  |  | UT document completed TGT_hdfsValidMentor>>>ValidMentors table created | Muni/ Smita | Done
18 | edm_processed_agency | AMP | seqAmpGenerateBusinessReport | tf_seqAmpGenerateBusinessReport | Farajiya | Complete | Complete | Complete | Complete | Complete | Complete
19 | edm_processed_agency | AMP | seqAmpGenerateCompensationReport | tf_seqAmpGenerateCompensationReport | Kamlendu | Complete | Complete | Complete | Complete | Complete | Complete
20 | edm_processed_agency | Email Campaign | PzEmailCampaignInsUpdDel | m_RsEmailCampaignInsUpdDel | Harsh/Krishna | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | Krishna
21 | edm_processed_agency | Email Campaign | PzEmailCampaignOutbound | m_EmailCampaignOutbound | Krishna | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | Kuldeep | Done
22 | edm_processed_agency | Email Campaign | PzEmailCampaignSrcExtrct1 | m_RsEmailCampaignSrcExtrct1 | Sakshi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | UT document complete. Session success with data | Kamlendu | Done
23 | edm_processed_agency | Email Campaign | PzEmailCampaignSrcExtrct2 | m_RsEmailCampaignSrcExtrct2 | Smita | Complete | Complete | Complete | Complete | Complete | Complete |  |  | UT document complete. Session success with data 1 Source and 1 Target table were created on 3/7/24. Other source table was created on 3/8/2024. Issue / concern - table 'rcr_cp_smy ' available in schema insurance_agency as created by Client on 03/08/2024. As of now, have defined an InOut parameter 'jpSchemaName_agency' with default value as 'insurance_agency ' schema in mapping but we need verify that this InOut paramter will be included in the updated parameter file as well. | Sridevi | Done
24 | edm_processed_agency | Email Campaign | PzEmailCampaignSrcExtrct3 | m_RsEmailCampaignSrcExtrct3 | Rajat | Complete | Complete | Complete | Complete | Complete | Complete |  |  | UT Document uploaded | Farajiya | Done
25 | edm_processed_agency | Email Campaign | PzEmailCampaignSrcExtrct4 | m_RsEmailCampaignSrcExtrct4 | Rushil | Complete | Complete | Complete | Complete | Complete | Complete |  |  | UT document completed SRC_fchdfsEmailCampaignSrcExtract2>>>EmailCampaignSrcExtract2 (table available in 3/7/24) | Muni/Sridevi | Done
26 | edm_processed_agency | Email Campaign | PzEmailCampaignSrcExtrct5 | m_RSEmailCampaignSrcExtrct5 | Sridevi | Complete | Complete | Complete | Complete | Complete | Complete |  |  | Mapping and mct success with data. UT document done. Target preSQL provided. | Smita | Done
27 | edm_processed_agency | Email Campaign | seqEmailCampaign | tf_seqEmailCampaign | Krishna | Complete | Complete | Complete | Complete | Complete | Complete

## Sprint _9
| Project | BusinessProject | Job | Mapping | IDMC Job Type | Owner | Sprint Planning | Dev + UT | QA Recon | QA Validation | Stage | Prod | Prod Sign Off | UAT Sign Off | ETA | Remarks | Peer Review | Status
1 | edm_processed_party | PDMParty | SeqPzPartyDimMaster | tf_RsPartyDimMaster | Taskflow | Kamlendu | Complete | OnHold | [7 empty] | This is master sequence, depends on 5 sub sequences and need to check for cmd,how to handle it.
2 | edm_processed_party | PDMParty | SSeqPzPartyDim1 | tf_RsPartyDim1 | Taskflow | Kamlendu | Complete | In Progress | [6 empty] | 2024-05-31 | Only Editing ETA because In this seq, having 10+ cmd's, need to check for cmd.
3 | edm_processed_party | PDMParty | PzDimBeneficiary | m_RsDimBeneficiary | Advanced | Kamlendu | Complete | Completed | [7 empty] | Considered bene_id_nk as Varchar and Completed the Mapping with UT Complete |  |  | 2024-08-05
4 | edm_processed_party | PDMParty | PzDimContractPartyRole | m_RsDimContractPartyRole | StandardPDO | Kuldeep | Complete | Completed | [7 empty] | UT Completed
5 | edm_processed_party | PDMParty | PzDimAgentCandRecrtmtStg | m_RsDimAgentCandRecrtmtStg | StandardPDO | Krishna | Complete | Completed | [7 empty] | UT Completed
6 | edm_processed_party | PDMParty | PzLkpAgentCandRecrtmtStg | m_RsLkpAgentCandRecrtmtStg | StandardPDO | Sakshi | Complete | Completed | [7 empty] | Mapping Success with data , UT Complete
7 | edm_processed_party | PDMParty | SSeqPzPartyDim2 | tf_Rs_PartyDim2 | Taskflow | Farajiya | Complete | On Hold | [7 empty] | In this seq, having 14 cmd's, need to check for cmd.
8 | edm_processed_party | PDMParty | PzDimClient | m_RsDimClient | Advanced | Wasi | Complete | In Progress | [7 empty] | Ashwin is working on query optimization.Mapping is complex. 03/06: Waiting for Ashwin to complete query optimization. 6/25/2024: long running m_RsDimClient_NJ_DND Tunning pending Missing peek_552 table.(used temp table :pdm_conv/peek_624) Dups logic 2 places ,Need to be advanced |  | Fixing Joinners
9 | edm_processed_party | PDMParty | PzDimFund | m_RsDimFund | Advanced | Rushil | Complete | Completed | [7 empty] | converted to adv - 6/27
10 | edm_processed_party | PDMParty | SSeqPzPartyDim3 | tf_RsPartyDim3 | Taskflow | Kamlendu | Complete | [7 empty] | 2024-06-05 | Only Editing ETA because In this seq, having 10+ cmd's, need to check for cmd.
11 | edm_processed_party | PDMParty | PzDimName | m_RsDimName | Advanced | Rajat | Complete | Completed | [7 empty] | UT Complete
12 | edm_processed_party | PDMParty | PzDimAgentCandidateLead | m_RsDimAgentCandidateLead | StandardPDO | Govind | Complete | Completed | [7 empty] | MCT & UT completed.
13 | edm_processed_party | PDMParty | PzDimProducerLicenseLOB | m_RsDimProducerLicenseLOB | Advanced | Smita | Complete | Completed | [7 empty] | MCT & UT complete. Advanced job complete. UT done -Sridevi - July1st
14 | edm_processed_party | PDMParty | PzLkpProducerLicenseLob | m_RsLkpProducerLicenseLob | Advanced | Sridevi | Complete | Completed | [7 empty] | MCT success. UT Completed. validated as per revised validation document.
15 | edm_processed_party | PDMParty | SSeqPzPartyDim4 | tf_RsPartyDim4 | Taskflow | Kamlendu | Complete | [7 empty] | 2024-06-06 | Only Editing ETA because In this seq, having 10+ cmd's, need to check for cmd.
16 | edm_processed_party | PDMParty | PzLkpProducerType | m_RsLkpProducerType | Advanced | Farajiya | Complete | Completed | [7 empty] | Mapping is success, UT completed
17 | edm_processed_party | PDMParty | PzDimProducerType | m_RsDimProducerType | Advanced | Rajat | Complete | Completed | [7 empty] | UT Complete
18 | edm_processed_party | PDMParty | PzDimProducerCompensation | m_RsDimProducerCompensation | Advanced | Krishna | Complete | Completed | [7 empty] | UT Completed and switich to adv. mode
19 | edm_processed_party | PDMParty | PzLkpProducerCompensation | m_RsLkpProducerCompensation | Advanced | Sakshi | Complete | Completed | [6 empty] | 21-05 | MCT & UT completed. DS having 4 src while in IDMC 3 src are present , Conversion Issue
20 | edm_processed_party | PDMParty | SSeqPzPartyDim5 | tf_RsPartyDim5 | Taskflow | Kamlendu | Complete | [7 empty] | 2024-06-07 | Only Editing ETA because In this seq, having 10+ cmd's, need to check for cmd.
21 | edm_processed_party | PDMParty | DimIncomeExpense | m_RsDimIncomeExpense | StandardPDO | Kuldeep | Complete | Completed | [7 empty] | UT Completed
22 | edm_processed_party | PDMParty | PzLkpIncomeExpense | m_RsLkpIncomeExpense | Advanced | Govind | Complete | Completed | [7 empty] | MCT & UT completed.
23 | edm_processed_party | PDMParty | PzDimProducerContractType | m_RsDimProducerContractType | Advanced | Nisha | Complete | Completed | [7 empty] | Mapping Success with data , UT Complete
24 | edm_processed_party | PDMParty | PzLkpProducerContractType | m_RsLkpProducerContractType | Advanced | Shreya | Complete | Completed | [7 empty] | Mapping Success with data , UT Complete
25 | edm_processed_party | PDMParty | SeqPzDimClientCombClientRel2 | tf_Rs_DimClientCombClientRel2 | Taskflow | Farajiya | Complete | Edited | [7 empty] | 15 May-Working on cmd,once mct will complete,will test seq
27 | edm_processed_party | PDMParty | SeqPzPartyDimClientCombRelMaster | tf_SeqPzPartyDimClientCombRelMaster | Taskflow | Kamlendu | Complete | [7 empty] | 2024-06-07 | Only Editing ETA because In this seq, having 10+ cmd's, need to check for cmd.
28 | edm_processed_party | PDMParty | SSeqPzPartyDimClientCombRel | tf_SSeqPzPartyDimClientCombRel | Taskflow | Kamlendu | Complete | [7 empty] | 2024-06-07 | Only Editing ETA because In this seq, having 10+ cmd's, need to check for cmd.
29 | edm_processed_party | PDMParty | PzDimClientCombClientRel1 | m_RsDimClientCombClientRel1 | StandardPDO | Krishna | Complete | Completed | [7 empty] | 26-06: UT completed and data is loaded into all 3 pipeline (matched or unmatched are separate tgt's) STM is matched with tgt clm and fields are using in rel 3 as src after that used for alias check with sana verified. Source: ext_lake_oracle_orap03_co0101.client Targets: pdm_conv.dim_client_comb_client_rel_full pdm_conv.dim_client_comb_client_rel_matched pdm_conv.dim_client_comb_client_rel_Nonmatched Please followup with Sana on pdm_conv.dim_client_comb_client_rel_Nonmatched MCT Success. UT on hold. Waiting on confirmation from client. Smita has fixed joiners and was missing one joiner also. Same source table and 3 target for Fulll,NotMultipleMatch and Match records,email sent to client Still waiting on client. Issue is escalated. last follow up with Sana/Farajiya is : 6/12/2024
26 | edm_processed_party | PDMParty | PzDimClientCombClientRel2 | m_RsDimClientCombClientRel2 | StandardPDO | Sakshi | Complete | [7 empty] | 18-05 | This dependent on Rel1 Source : pdm_conv.dim_client_comb_client_rel_matched pdm_conv.dim_client_comb_client_rel_full Target : pdm_conv.dim_client_comb_client_rel_matched_trg pdm_conv.dim_client_comb_client_rel_Nonmatched_inbatch_key Please followup with Sana on pdm_conv.dim_client_comb_client_rel_Nonmatched_inbatch_key --- 05/20 - provided src and tgt table connections. Mapping is valid. Session is running > 30 min. Need to review / run with limit - WIP. Shailja asked to hold until Client confirms. UT pending. 05/10-Need confirmation from Client on source and target tables - both are same in pre req document. 05/20 - Client asked to provide table names as per DataStage, all 4 table connections are provided in mapping Still waiting on client. Issue is escalated. last follow up with Sana/Farajiya is : 6/12/2024
30 | edm_processed_party | PDMParty | PzDimClientCombClientRel3 | m_RsDimClientCombClientRel3 | Advanced | Rushil | Complete | Completed | [7 empty] | converted to adv - 6/28 Dependency on Rel1 Mapping Success with data , UT Complete rel3: Source pdm_conv.dim_client_comb_client_rel_Nonmatched ext_lake_oracle_orap03_co0101.client pdm_conv.dim_client_comb_client_rel Target pdm_conv.etl_party_reject_table pdm_conv.ops_etl_config_batch_key pdm_conv.dim_client_comb_client_rel pdm_conv.dim_client_comb_client_rel Please followup with Sana on pdm_conv.dim_client_comb_client_rel_Nonmatched -- need to ask sana about fields not match ds--fixed
31 | edm_processed_party | PDMParty | SeqPzPartyFactAgentCandRecrtmtFunnelMaster | tf_Rs_PartyFactAgentCandRecrtmtFunnelMaster | Taskflow | Farajiya | Complete | Edited | [7 empty] | This is master sequence, depends on two sub sequences and need to check for cmd,how to handle it.
32 | edm_processed_party | PDMParty | SSeqPzPartyFactAgentCandRecrtmtFunnel | tf_Rs_SPzPartyFactAgentCandRecrtmtFunnel | Taskflow | Kuldeep | Complete | [8 empty] | Dependent MCt is on hold due to Conversion Issue
33 | edm_processed_party | PDMParty | PzFactAgentCandRecrtmtFunnel | m_RsFactAgentCandRecrtmtFunnel | Advanced | Kuldeep | Complete | In Progress | [7 empty] | 1. Optimization is done and validation was in WIP But project team made some changes in flow now it become complex need new converted code to re-optimize with new flow. 2. Now it have new 5 duplicate logic,2 router,2 aggergator,2 lookup, 2 peek targets. 3.Connected with Ma'am regarding further optimization.The latest STM is required for validation.
34 | edm_processed_party | PDMParty | PzFactAgentAvisoryCouncil | m_RsFactAgentAvisoryCouncil | StandardPDO | Govind | Complete | Completed | [6 empty] | 2024-06-06 | MCT & UT completed.
35 | edm_processed_party | PDMParty | PzFactBookOfBusiness | m_RsFactBookOfBusiness | Advanced | Rajat | Complete | Completed | [7 empty] | UT Complete
36 | edm_processed_party | PDMParty | PzFactClientCommunication | m_RsFactClientCommunication | StandardPDO | Krishna | Complete | Completed | [7 empty] | UT Completed
37 | edm_processed_party | PDMParty | PzFactClientSubscription | m_RsFactClientSubscription | StandardPDO | Sakshi | Complete | Completed | [7 empty] | Mapping Success with data , UT Complete , update flow is not working because chksum key is included in main joiner 20/06 - As per discussion with Manoj proceeding as per datastage , ignoring update ,it will only insert data¦ deleted inactive target
38 | edm_processed_party | PDMParty | PzFactFatca | m_RsFactFatca | Advanced | Govind | Complete | Completed | [6 empty] | 21-05 | MCT & UT completed.
39 | edm_processed_party | PDMParty | PzFactProducerAddtionalExpense | m_RsFactProducerAddtionalExpense | StandardPDO | Smita | Complete | Completed | [7 empty] | MCT Successwith data. UT Complete
40 | edm_processed_party | PDMParty | PzFactProducerAdvisoryBoardDirector | m_RsFactProducerAdvisoryBoardDirector | Advanced | Sridevi | Complete | Completed | [7 empty] | MCT Success, UT completed
41 | edm_processed_party | PDMParty | PzFactProducerCertification | m_RsFactProducerCertification | Advanced | Rushil | Complete | Completed | [7 empty] | Mapping Success with data , UT Complete converted to adv - 6/27
42 | edm_processed_party | PDMParty | PzFactProducerCompensation | m_RsFactProducerCompensation | Advanced | Farajiya | Complete | Completed | [7 empty] | Got confirmation with project team as it is SCD-1 but in the DS description, mentioned as SCD-2. 30 April: Proceeding with SCD-1 as confirmed by poc, working for scd1 flow. Mapping success with Data and UT Completed
43 | edm_processed_party | PDMParty | PzFactProducerDebitArrangement | m_RsFactProducerDebitArrangement | StandardPDO | Kamlendu | Complete | Completed | [7 empty] | MCT success with data and UT completed
44 | edm_processed_party | PDMParty | PzFactProducerEdLicCmplnc | m_RsFactProducerEdLicCmplnc | Advanced | Sakshi | Complete | Completed | [7 empty] | Mapping Success with data , UT Complete
45 | edm_processed_party | PDMParty | PzFactProducerFinancialInstitution | m_RsFactProducerFinancialInstitution | StandardPDO | Govind | Complete | Completed | [7 empty] | MCT & UT completed.
46 | edm_processed_party | PDMParty | PzFactProducerFinra | m_RsFactProducerFinra | Advanced | Farajiya | Complete | Completed | [6 empty] | 15-05 | MCT & UT Completed
47 | edm_processed_party | PDMParty | PzFactProducerGeneralOfficeComp | m_RsFactProducerGeneralOfficeComp | StandardPDO | Sridevi | Complete | Completed | [6 empty] | 16-05 | MCT success. UT Completed.
48 | edm_processed_party | PDMParty | PzFactProducerGroupMembership | m_RsFactProducerGroupMembership | Advanced | Rushil | Complete | Completed | [7 empty] | Mapping success. UT Complete converted to adv 6/28 Data switch team will reconvert mapping - 5/13 Sent message on 6/17 to sana to follow up on it again
49 | edm_processed_party | PDMParty | PzFactProducerIncomeExpense | m_RsFactProducerIncomeExpense | Advanced | Krishna | Complete | Completed | [6 empty] | 23-05 | Clubbed query getting error out of memory issue checking with harsh & mam so i have tested all scercnio expect full load bcz of long running so i have tested 100 record it working fine Filter :- producer_id_nk='0351106' and src_sk='92477364' Revised ETA - 29/05
50 | edm_processed_party | PDMParty | PzFactProducerLedger | m_RsFactProducerLedger | Advanced | Rajat | Complete | Completed | [7 empty] | UT Complete
51 | edm_processed_party | PDMParty | PzFactProducerLtcTraining | m_RsFactProducerLtcTraining | Advanced | Rajat | Complete | Completed | [7 empty] | UT Complete
52 | edm_processed_party | PDMParty | PzFactProducerMdrtMembership | m_RsFactProducerMdrtMembership | Advanced | Krishna | Complete | Completed | [7 empty] | UT Completed
53 | edm_processed_party | PDMParty | PzFactProducerPartnerCompensation | m_RsFactProducerPartnerCompensation | StandardPDO | Kiruthika | Complete | Completed | [7 empty] | UT Completed
54 | edm_processed_party | PDMParty | PzFactProducerPartnerRole | m_RsFactProducerPartnerRole | StandardPDO | Sakshi | Complete | Completed | [6 empty] | 29-05 | Mapping Success with data , UT Complete
55 | edm_processed_party | PDMParty | PzFactProducerProducerRel | m_RsFactProducerProducerRel | Advanced | Kuldeep | Complete | Completed | [7 empty] | UT Completed
56 | edm_processed_party | PDMParty | PzFactProducerStCntyReqr | m_RsFactProducerStCntyReqr | Advanced | Nisha | Complete | Completed | [7 empty] | Mapping Success with data,UT Completed
57 | edm_processed_party | PDMParty | PzFactProducerSubsidiaryCnt | m_RsFactProducerSubsidiaryCnt | Advanced | Govind | Complete | Completed | [7 empty] | MCT & UT completed.
58 | edm_processed_party | PDMParty | PzFactAgentCandidateEducation | m_RsFactAgentCandidateEducation | Advanced | Kamlendu | Complete | Completed | [6 empty] | 16-05 | UT -WIP
59 | edm_processed_party | PDMParty | PzFactAgentCandidateEmployment | m_RsFactAgentCandidateEmployment | StandardPDO | Smita | Complete | Completed | [6 empty] | 16-05 | UT Complete MCT success.
60 | edm_processed_party | PDMParty | PzFactAgentCandidateExperience | m_RsFactAgentCandidateExperience | StandardPDO | Sourabh | Complete | Completed | [7 empty] | Mapping is success with data, UT Complete
61 | edm_processed_party | PDMParty | PzFactAgentCandidateLead | m_RsFactAgentCandidateLead | Advanced | Shreya | Complete | Completed | [7 empty] | Mapping is success with data, UT Complete
62 | edm_processed_party | PDMParty | PzFactAgentCandidateRecrtmt | m_RsFactAgentCandidateRecrtmt | Advanced | Shreya | Complete | Completed | [6 empty] | 16-05 | Mapping is success with data, UT Complete
63 | edm_processed_party | PDMParty | PzFactProducerActivity | m_RsFactProducerActivity | Advanced | Nisha | Complete | Completed | [7 empty] | Mapping is success with data, UT Complete,Converted in Advance mode
64 | edm_processed_party | PDMParty | PzFactProducerLicense | m_RsFactProducerLicense | StandardPDO | Rushil | Complete | Completed | [6 empty] | 2024-05-29 | Mapping Success with data , UT Complete runs longer than production time is DS --- converted to adv mapping after truncating target and running adv mapping it finished in 5 min and when reran it took 12 min converted to adv - 5/29
Note on Q14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Converted DataSwitch mapping - few expressions were incorrect in Expression tab. Fixed as per DataStage
Note on Q60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 05/10 - Awaiting confirmation from Client for - Issue : SRC_hiveTableSrc - Query has missing field - DataSwitch original mapping has hardcoded the field vs DataStage it is not . 'a.addl_rmrk_txt' addl_rmrk_free_txt . Without single quotes, query error : error [error [Provided Custom query is invalid due to:[[Amazon](500310) Invalid operation: column a.addl_rmrk_txt does not exist;]]]

## Sprint 10
S No | Project | BusinessProject | Job | Mapping | IDMC Job type | Assigned To | Sprint Planning | Dev + UT | QA Recon | QA Validation | Stage | Prod | Prod Sign Off | UAT Sign Off | ETA | Remarks | Peer Review | Status
1 | edm_processed_party | PDMParty | PzFactAgentCandidateLeadScore | m_RsFactAgentCandidateLeadScore | Advanced | Rajat | Complete | Completed | [6 empty] | 17-05 |  |  | UT Complete
2 | edm_processed_party | PDMParty | PzFactAgentCandidateLeadScreen | m_RsFactAgentCandidateLeadScreen | Advanced | Sourabh | Complete | Completed | [6 empty] | 17-05 |  |  | MCT success with data and UT completed
3 | edm_processed_party | PDMParty | PzFactProducer | m_RsFactProducer | Advanced | Smita/Rushil | Complete | Blocked | [7 empty] | working on STM of other assets |  | Julian day/date logic is there in expression is not supported in Informatica EXP_xfmActiveRecs --Datastage ----JulianDayFromDate(lnkActiveRecs.rec_exp_dt) integer EXP_XfmMaxDate--Datastage logic DateFromJulianDay(lnkMaxDate.max_date_aggr+1) datetime Mapping is tuned by combining queries where ever applicable :15 min runtime Waiting for confirmation from project team
4 | edm_processed_party | PDMParty | PzFactProducerAddlDtls | m_RSFactProducerAddlDtls | Advanced | Shivangi | Complete | Completed | [9 empty] | MCT success with data and UT completed
5 | edm_processed_party | PDMParty | PzFactProducerCouncil | m_RsFactProducerCouncil | Advanced | Shivangi | Complete | Completed | [6 empty] | 16-05 |  |  | MCT success with data and UT completed
6 | edm_processed_party | PDMParty | PzFactProducerDerv | m_RsFactProducerDerv | Advanced | Sonveer | Complete | Completed | [6 empty] | 20-05 |  |  | MCT success with data and UT completed
7 | edm_processed_party | PDMParty | PzFactProducerFldSuprtEnroll | m_RSFactProducerFldSuprtEnroll | Advanced | Krishna | Complete | Completed | [6 empty] | 22-05 |  |  | Working on docu ETA by :22/05/
8 | edm_processed_party | PDMParty | PzFactProducerRecruitment | m_RSFactProducerRecruitment | Advanced | Farajiya | Complete | Completed | [6 empty] | 2024-06-12 |  |  | Half query part optimization completed , need help in other part Informed to Thomas. Proceeding with half part query optimization, verified query with harsh, working on mapping optimization. 07/06: Still in progress bcz code is not proper in sync with DS. 10/06: validation is complete, mapping is failing on preview. working on it. 12/06: MCT success with data and UT completed
9 | edm_processed_party | PDMParty | PzFactProducerStSolicElg | m_RsFactProducerStSolicElg | Advanced | Kuldeep/Nikhil | Complete | In Progress | [9 empty] | 1.Node count: 180 ,Source 13,Sorter 52,Joiner 27 2. 95% optimization done, need help to clubbed one of the Exp inside source Query. 3. Mapping flows is complex. but it can be redesign but first need to discuss STM with Harsh and than need confimation with project team.
10 | edm_processed_party | PDMParty | PzFactAgentStaffRelation | m_RsFactAgentStaffRelation |  | Govind | Complete | Success | [6 empty] | 2024-07-04 |  |  | MCT success with data and UT completed
11 | edm_processed_party | PDMParty | SeqPzPartyFactFmisMaster | tf_RsPartyFactFmisMaster | Taskflow | Kamlendu | Complete | On Hold | [6 empty] | 2024-06-11 | It's Master Tasflow were to 2 Subtasflow is used tf_RsSSeqPzPartyFactFmis and tf_SubSeqPzParty_Recon. tf_SubSeqPzParty_Recon is not in our Tracker need to confirm who will provide the validated Subtaskflow.
12 | edm_processed_party | PDMParty | SSeqPzPartyFactFmis | tf_RsSSeqPzPartyFactFmis | Taskflow | Govind | Complete | On Hold | [6 empty] | 2024-06-11 |  |  | For this TF, MCT mct_RsFactFmisCntProducerPremShare Full Load is taking too much time for running.(TF not edited yet)
13 | edm_processed_party | PDMParty | PzFactFmisCntProducerPremShare | m_RsFactFmisCntProducerPremShare | Advanced | Nikhil | Complete | Completed | [6 empty] | 17-05 |  |  | 1.MCT ran Successfully.All UT scenario tested, except Full load taking time. Fullload is stopped because running continous more than 2 hrs(As suggest by mam) . Other UT scenrios working fine. This condition 'where A.cnt_id_nk=39710540 and A.mkshr_totcpn_prmam=402 and F.ent_plan_cd='UNK' ' used for testing UT scenarios.(QA team will take care of this job for Full Load). 2. in HiveLkpProduct src duplicate records is present. With this condition 'edh_record_end_ts='9999-12-31'' duplicate can be removed. But this need to be confirm from project team.
14 | edm_processed_party | PDMParty | PzFactProducerNasdExam |  | Advanced |  | Complete | Out of Scope
15 | edm_processed_party | PDMParty | SeqPzPartyFactMaster | tf_RsPartyFactMaster | Taskflow | Sakshi | Complete | On Hold | [9 empty] | Dependent on SSeqPzPartyFact
16 | edm_processed_party | PDMParty | SSeqPzPartyFact |  | Taskflow |  | Complete | On Hold | [9 empty] | It's Master Tasflow were to 2 Subtasflow is used tf_RsSSeqPzPartyFact and tf_SubSeqPzParty_Recon. tf_SubSeqPzParty_Recon is not in our Tracker .
17 | edm_processed_party | PDMParty | PzDimPsycleSegmentInitLd | m_RsDimPsycleSegmentInitLd |  | Shreya | Complete | Success | [6 empty] | 2024-07-03 |  |  | MCT success with data and UT completed
18 | edm_processed_party | PDMParty | SSeqPzPartyDimPsycleSegmentInitLd |  |  |  | Complete
19 | edm_processed_party | PDMParty | SeqPzPartyDimPsycleSegmentInitLdMaster |  |  |  | Complete
20 | edm_processed_party | PDMParty | PzDimPsycleSegment | m_RsDimPsycleSegment |  | Nisha | Complete | Success | [6 empty] | 2024-04-07 |  |  | MCT success with data and UT completed
21 | edm_processed_party | PDMParty | PzFactPsyclePartyInitLd | m_RsFactPsyclePartyInitLd |  | Sakshi | Complete | Inprogress | [6 empty] | 2024-07-05 |  |  | job is long running ,as per discussed in call (04/07)UT done with limited data
22 | edm_processed_party | PDMParty | PzDimCycleSegmentInitLd |  |  | Wasi
22 | edm_processed_party | PDMParty | SSeqPzFactPsyclePartyInitLd |  |  |  | Complete
23 | edm_processed_party | PDMParty | SeqPzFactPsyclePartyInitLdMaster |  |  |  | Complete
24 | edm_processed_party | PDMParty | PzFactPsycleParty |  |  | Krishna | Complete | Blocked | [9 empty] | Miss match in src query and seq tble not exist in mapping need confirmation
25 | edm_processed_party | PDMParty | PzFactPsyclePartyReportGenerate | m_RsFactPsyclePartyReportGenerate |  | Sourabh | Complete | Blocked | [6 empty] | 2024-04-07 |  |  | Confirmation is required from POC for the target as a Sequential File in DataStage.
26 | edm_processed_party | PDMParty | SeqPzFactPsyclePartyMaster
27 | edm_processed_party | PDMParty | SSeqPzFactPsycleParty
28 | edm_processed_party | PDMParty | SeqPzFactPsyclePartyYearlyMaster
29 | edm_processed_party | PDMParty | SSeqPzFactPsyclePartyYearly
30 | edm_processed_party | PDMParty | PzPsyclePartyPublMonthlyTableLoad | m_RsPsyclePartyPublMonthlyTableLoad |  | Kamakshi | Complete | Blocked | [6 empty] | 2024-07-03 | Validation in progress (Waiting for trgt table confirmation (trgt is sequential file in DS)
31 | edm_processed_party | PDMParty | PzPsyclePartyPublYearlyTableLoad | m_RsPsyclePartyPublYearlyTableLoad |  | Kuldeep | Complete | Blocked | [6 empty] | 2024-03-07 |  |  | Confirmation is required from POC for the target as a Sequential File in DataStage. working on validation
32 | edm_processed_party | PDMParty | SeqPzPsyclePartyMonthlyPublishingMaster
33 | edm_processed_party | PDMParty | SSeqPzPsyclePartyMonthlyPublishing
34 | edm_processed_party | PDMParty | SeqPzPsyclePartyYearlyPublishingMaster
35 | edm_processed_party | PDMParty | SSeqPzPsyclePartyYearlyPublishing
Note on S4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6/6/2024 - MCT success , EXP_xfmIndFldUpd and EXP_xfmReject - IDMC mapping DataSwitch code for expression fields does not match DataStge code for many fields RTR_fltrCult_Mktr_cd - DataSwitch conversion has incorrect FIELD RENAME and 1 other field renaming is missed, 2 more discrepancies fixed. Sources - 18, Targets - 4, Joiners -37, Sorters - 74 approx

## Sprint 11
S No | Project | Subject Area | BusinessProject | Job | Mapping | IDMCJobType | Assigned | Sprint Planning | Dev + UT | QA Recon | QA Validation | Stage | Prod | Prod Sign Off | UAT Sign Off | ETA | Remarks | Peer Review | Status
1 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzBrgNbAgentStAddlDtlTp | m_RsBrgNbAgentStAddlDtlTp | Advanced | Sakshi | Completed | Success | [6 empty] | 2024-07-04 | Mapping Success with data in Advance , UT Complete
2 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzBrgNbAgentStmntAgent | m_RsBrgNbAgentStmntAgent | Advanced | Nisha | Completed | InProgress | [6 empty] | 2024-07-05 | Validation done,UT Done,switching to advance
3 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzBrgNbAgentStmntDpndnt | m_RsBrgNbAgentStmntDpndnt | StandardPDO | Kuldeep | Completed | Success | [6 empty] | 25-06-2024
4 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzBrgNbAgentStmntFundSrc | m_RsBrgNbAgentStmntFundSrc | StandardPDO | Shreya | Completed | Success | [6 empty] | 26-06-2024 | Mapping Success with data , UT Complete
5 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzBrgNbAgentStmntOldCnt | m_RsBrgNbAgentStmntOldCnt | StandardPDO | Krishna | Completed | Success | [6 empty] | 25-06-2024 | Mapping Success with data , UT Complete
6 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzBrgNbAgntStmntInsPrps | m_RsBrgNbAgntStmntInsPrps | Advanced | Govind | Completed | Success | [6 empty] | 26-06-2024 | MCT Completed with UT in both mode
7 | edm_processed_nb | NB - Contract Party Relationship | Proj_nb | PzBrgNbCntPartyRoleRelship | m_RsBrgNbCntPartyRoleRelship | Advanced | Sakshi | Completed | InProgress | [6 empty] | 2024-07-05 | Validation is Done,STM Validation in-progress, UT inProgress
8 | edm_processed_nb | NB - Contract Party Relationship | Proj_nb | PzBrgNbContractOldCnt | m_RsBrgNbContractOldCnt | Advanced | Shreya | Completed | InProgress
9 | edm_processed_nb | NB - Contract Alert | Proj_nb | PzBrgNbUwContractAlert | m_RsBrgNbUwContractAlert | StandardPDO | Kamakshi | Completed | Inprogress | [6 empty] | 2024-07-05 | Validation in progress
10 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementCdc | m_RsFactNbAgentStatementCdc | Advanced | Sourabh | Completed | InProgress | [6 empty] | 27-06-2024 | Dependent on Trans 3.Validation complete
11 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo1 | m_RsFactNbAgentStatementDimGeo1 | StandardPDO | Govind | Completed | Success | [6 empty] | 25-06-2024 | MCT Completed with UT
12 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo2 | m_RsFactNbAgentStatementDimGeo2 | StandardPDO | Wasi | Completed | Success | [6 empty] | 25/06/2024 | MCT Completed with UT
13 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo3 | m_RsFactNbAgentStatementDimGeo3 | StandardPDO | Kamakshi | Completed | Success | [6 empty] | 2024-06-26 | MCT Completed with UT
14 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo4 | m_RsFactNbAgentStatementDimGeo4 | StandardPDO | Wasi | Completed | Success | [6 empty] | 24/06/2024 | MCT Completed with UT
15 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo5 | m_RsFactNbAgentStatementDimGeo5 | StandardPDO | Sridevi | Completed | Success | [6 empty] | 2024-06-21 | MCT success, UTcompleted sent to sana to verify
16 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo6 | m_RsFactNbAgentStatementDimGeo6 | StandardPDO | Rushil | Completed | Success | [7 empty] | Mapping Success. UT Completed. Stm done |  |  | Waiting on client on target table name
17 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo7 | m_RsFactNbAgentStatementDimGeo7 | StandardPDO | Sakshi | Completed | Success | [6 empty] | 26/06/2024 | MCT Completed with UT
18 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo8 | m_RsFactNbAgentStatementDimGeo8 | StandardPDO | Krishna | Completed | Success | [6 empty] | 2024-06-24 | 25-06 : Check with vir team not in issue it has depency on other mapping UT completed and discrepancy found in stm reported to sana --fixed and check with poc Gokul
19 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementDimGeo9 | m_RsFactNbAgentStatementDimGeo9 | StandardPDO | Kuldeep | Completed | Success | [6 empty] | 26-06-2024
20 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementTrans1 | m_RsFactNbAgentStatementTrans1 | StandardPDO | Kuldeep | Completed | Success | [6 empty] | 2024-06-04 | MCT Completed with UT
21 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementTrans2 | m_RsFactNbAgentStatementTrans2 | StandardPDO | Krishna | Completed | Success | [6 empty] | 2024-02-07 | UT completed
22 | edm_processed_nb | NB - Agent Statement | Proj_nb | PzFactNbAgentStatementTrans3 | m_RsFactNbAgentStatementTrans3 | Advanced | Krishna | Completed | In progress | [7 empty] | standard MCT success. UT pending. Note:Only for this field primary_insured_src_cl_id in EXP_xfm I did not change the LTRIMRTRIM expression. I need help on that. Rest all fields I have changed. src_cl_id, cl_id_nk fixed LTRIMRTRIM with the help of Muni--7/2/2024 fact_nb_agent_statement_trans2 this target table is one of the source in this mapping.All 9 geo tables are sources in this mapping. Note: DS Mapping has 9 remove duplicates. Note: target table in DS datatype is bigint 18 but IDMC table has bigint 19.
23 | edm_processed_nb | NB - Contract Insured Pega Transaction | Proj_nb | PzFactNbCntInsuredPegaTrans | m_RsFactNbCntInsuredPegaTrans | Advanced | Sakshi | Completed
24 | edm_processed_nb | NB - Contract Insured Requirement | Proj_nb | PzFactNbCntInsuredReqr | m_RsFactNbCntInsuredReqr | StandardPDO | Shreya | Completed | InProgress | [6 empty] | 2024-07-04 | Validations is Completed --UT Inprogress dependent on this job PzFactNbCntInsuredReqrSrc
25 | edm_processed_nb | NB - Contract Insured Requirement | Proj_nb | PzFactNbCntInsuredReqr1 | m_RsFactNbCntInsuredReqr1 | Advanced | Nisha | Completed
26 | edm_processed_nb | NB - Contract Insured Requirement | Proj_nb | PzFactNbCntInsuredReqrCDC | m_RsFactNbCntInsuredReqrCDC | StandardPDO | Sourabh | Completed | InProgress | [6 empty] | 2024-07-05 | Dependent on PzFactNbCntInsuredReqr1.Validation complete
27 | edm_processed_nb | NB - Contract Insured Requirement | Proj_nb | PzFactNbCntInsuredReqrSrc | m_RsFactNbCntInsuredReqrSrc | StandardPDO | Sakshi | Completed
28 | edm_processed_nb | NB - Contract Insured Requirement | Proj_nb | PzFactNbCntInsuredReqrSrcCntr1 | m_RsFactNbCntInsuredReqrSrcCntr1 | StandardPDO | Wasi | Completed | Success | [6 empty] | 2024-07-04 | MCT Completed with UT
29 | edm_processed_nb | NB - Contract Insured Requirement | Proj_nb | PzFactNbCntInsuredReqrSrcCntr2 | m_RsFactNbCntInsuredReqrSrcCntr2 | StandardPDO | Kamakshi | Completed | Success | [6 empty] | 29/6/24 | MCT Completed with UT
30 | edm_processed_nb | NB - Contract Insured Requirement | Proj_nb | PzFactNbCntInsuredReqrSrcCntr3 | m_RsFactNbCntInsuredReqrSrcCntr3 | StandardPDO | Wasi | Completed | Success | [6 empty] | 2024-07-04 | MCT Completed with UT
31 | edm_processed_nb | NB - Contract Party Relationship | Proj_nb | PzFactNbCntPartyRelshp1 | m_RsFactNbCntPartyRelshp1 | Advanced | Nisha | Completed
32 | edm_processed_nb | NB - Contract Party Relationship | Proj_nb | PzFactNbCntPartyRelshp2 | m_RsFactNbCntPartyRelshp2 | Advanced | Sourabh | Completed
33 | edm_processed_nb | NB - Contract Party Relationship | Proj_nb | PzFactNbCntPartyRelshpCDC | m_RsFactNbCntPartyRelshpCDC | StandardPDO | Shreya | Completed
34 | edm_processed_nb | NB - Contract Activity | Proj_nb | PzFactNbContractActivity | m_RsFactNbContractActivity | Advanced | Shailja | Completed
35 | edm_processed_nb | NB - Contract Change | Proj_nb | PzFactNbContractChange | m_RsFactNbContractChange | Advanced | Kuldeep | Completed
36 | edm_processed_nb | NB - MIB | Proj_nb | PzFactNbMIB_1 | m_RsFactNbMIB_1 | Advanced | Krishna | Completed | Success | [6 empty] | 2024-07-04 | Validation and UT Completed and stm need to check Switich to adv. also
37 | edm_processed_nb | NB - MIB | Proj_nb | PzFactNbMIB_2 | m_RsFactNbMIB_2 | Advanced | Krishna | Completed
38 | edm_processed_nb | NB - Contract Alert | Proj_nb | PzFactNbUwContractAlert | m_RsFactNbUwContractAlert | StandardPDO | Shailja | Completed
39 | edm_processed_nb | NB - Contract Alert | Proj_nb | PzFactNbUwContractAlertcdc | m_RsFactNbUwContractAlertcdc | StandardPDO | Sakshi | Completed
40 | edm_processed_nb | NB - MIB Underwriting | Proj_nb | PzFactNbUwMIB | m_RsFactNbUwMIB | Advanced | Shreya | Completed
41 | edm_processed_nb | NB - Agent Statement | Proj_nb | SeqPzNbAgentStmt_Master |  | Taskflow |  | Completed
42 | edm_processed_nb | NB - Contract Activity | Proj_nb | SeqPzNbCaseRemarkPvtMaster |  | Taskflow |  | Completed
43 | edm_processed_nb | NB - Contract Party Relationship | Proj_nb |  |  | Taskflow |  | Completed
44 | edm_processed_nb | NB - Contract Alert | Proj_nb | SeqPzNbSubAreaPvtSet1Master |  | Taskflow |  | Completed
45 | edm_processed_nb | NB - Contract Change | Proj_nb | SeqPzNbSubAreaSet1Master |  | Taskflow |  | Completed
46 | edm_processed_nb | NB - Agent Statement | Proj_nb | SSeqPzNbAgentStmt |  | Taskflow |  | Completed
47 | edm_processed_nb | NB - Contract Activity | Proj_nb | SSeqPzNbCaseRemarkPvt |  | Taskflow |  | Completed
48 | edm_processed_nb | NB - Contract Party Relationship | Proj_nb | SSeqPzNbPart1 |  | Taskflow |  | Completed
49 | edm_processed_nb | NB - Contract Alert | Proj_nb | SSeqPzNbSubAreaPvtSet1 |  | Taskflow |  | Completed
50 | edm_processed_nb | NB - Contract Change | Proj_nb | SSeqPzNbSubAreaSet1 |  | Taskflow |  | Completed
52 | edm_processed_nb | NB - Contract Party Relationship | Proj_nb | PzBrgNbCntPartyInsStmnt | m_RsBrgNbCntPartyInsStmnt |  |  | Completed

## Sprint 12
S No | Project | Subject Area | BusinessProject | Job | Mapping | IDMCJobType | Assigned | Sprint Planning | Dev + UT | QA Recon | QA Validation | Stage | Prod | Prod Sign Off | UAT Sign Off | ETA | Remarks | Peer Review | Status
1 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbCntDclnReason |  | Advanced | Kamakshi | Completed
2 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbCntExtraPremRate |  | Advanced | Govind | Completed
3 | edm_processed_nb | NB - Part1 | Proj_nb | PzBrgNbCntInsuredBnft |  | Advanced | Wasi | Completed
4 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbCntOriginalOffer |  | Advanced | Shailja | Completed
5 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbCntReinOffer |  | Advanced | Shailja | Completed
6 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbCntUwRiskClass |  | Advanced |  | Completed
7 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbContractAmendment |  | Advanced |  | Completed
8 | edm_processed_nb | NB - Part1 | Proj_nb | PzBrgNbContractBeneficiary |  | Advanced |  | Completed
9 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbContractCorr |  | Advanced |  | Completed
10 | edm_processed_nb | NB - Part1 | Proj_nb | PzBrgNbContractEventSts |  | Advanced |  | Completed
11 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbContractExclusion |  | StandardPDO |  | Completed
12 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbContractimpairment |  | Advanced |  | Completed
13 | edm_processed_nb | NB - Part1 | Proj_nb | PzBrgNbInsuredOtherPolicy |  | Advanced |  | Completed
14 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzBrgNbUwCntInsRating |  | Advanced |  | Completed
15 | edm_processed_nb | NB- Case Remark | Proj_nb | PzFactNbCaseRemark1 |  | StandardPDO | Govind | Completed
16 | edm_processed_nb | NB- Case Remark | Proj_nb | PzFactNbCaseRemark2 |  | StandardPDO |  | Completed
17 | edm_processed_nb | NB- Case Remark | Proj_nb | PzFactNbCaseRemark2Src |  | StandardPDO |  | Completed
18 | edm_processed_nb | NB- Case Remark | Proj_nb | PzFactNbCaseRemark2Union1Src |  | StandardPDO |  | Completed
19 | edm_processed_nb | NB- Case Remark | Proj_nb | PzFactNbCaseRemark2Union2Src |  | StandardPDO |  | Completed
20 | edm_processed_nb | NB- Case Remark | Proj_nb | PzFactNbCaseRemark2Union3Src |  | StandardPDO |  | Completed
21 | edm_processed_nb | NB- Case Remark | Proj_nb | PzFactNbCaseRemark3 |  | Advanced |  | Completed
22 | edm_processed_nb | NB- Case Remark | Proj_nb | PzFactNbCaseRemarkcdc |  | StandardPDO |  | Completed
23 | edm_processed_nb | NB - Part1 | Proj_nb | PzFactNbContractPart1 |  | Advanced |  | Completed
24 | edm_processed_nb | NB - Part1 | Proj_nb | PzFactNbContractPart1cdc |  | StandardPDO |  | Completed
25 | edm_processed_nb | NB - Part1 | Proj_nb | PzFactNbContractPart2 |  | Advanced |  | Completed
26 | edm_processed_nb |  | Proj_nb | PzFactNbContractQcReply1 |  | StandardPDO |  | Completed
27 | edm_processed_nb |  | Proj_nb | PzFactNbContractQcReply2 |  | Advanced |  | Completed
28 | edm_processed_nb |  | Proj_nb | PzFactNbContractQcReplyCDC |  | StandardPDO |  | Completed
29 | edm_processed_nb | NB - Part2-Medication | Proj_nb | PzFactNbMedication_1 |  | Advanced |  | Completed
30 | edm_processed_nb | NB - Part2-Medication | Proj_nb | PzFactNbMedication_2 |  | Advanced |  | Completed
31 | edm_processed_nb | NB - Part2-Medication | Proj_nb | PzFactNbMedication_3 |  | Advanced |  | Completed
32 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealth |  | Advanced |  | Completed
33 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealth204Trans |  | Advanced |  | Completed
34 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealth209Trans |  | Advanced |  | Completed
35 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealthTrans1 |  | StandardPDO |  | Completed
36 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealthTrans2 |  | Advanced |  | Completed
37 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealthTrans3 |  | StandardPDO |  | Completed
38 | edm_processed_nb | NB - Prescription | Proj_nb | PzFactNbPrescrDrugFill1 |  | StandardPDO |  | Completed
39 | edm_processed_nb | NB - Prescription | Proj_nb | PzFactNbPrescrDrugFill2 |  | StandardPDO |  | Completed
40 | edm_processed_nb | NB - Prescription | Proj_nb | PzFactNbPrescrDrugFill3 |  | StandardPDO |  | Completed
41 | edm_processed_nb | NB - Prescription | Proj_nb | PzFactNbPrescrDrugFill4 |  | StandardPDO |  | Completed
42 | edm_processed_nb | NB - Prescription | Proj_nb | PzFactNbPrescrDrugFillCDC |  | StandardPDO |  | Completed
43 | edm_processed_nb | NB - Prescription | Proj_nb | PzFactNbPrescrDrugFillSrc |  | StandardPDO |  | Completed
44 | edm_processed_nb | NB - Prescription ICD | Proj_nb | PzFactNbPrescriptionIcd1 |  | Advanced |  | Completed
45 | edm_processed_nb | NB - Prescription ICD | Proj_nb | PzFactNbPrescriptionIcd2 |  | StandardPDO |  | Completed
46 | edm_processed_nb | NB - Prescription ICD | Proj_nb | PzFactNbPrescriptionIcdCDC |  | StandardPDO |  | Completed
47 | edm_processed_nb | NB - Scheduled Work | Proj_nb | PzFactNbScheduledWork1 |  | StandardPDO |  | Completed
48 | edm_processed_nb | NB - Scheduled Work | Proj_nb | PzFactNbScheduledWork2 |  | Advanced |  | Completed
49 | edm_processed_nb | NB - Scheduled Work | Proj_nb | PzFactNbScheduledWorkArchivalProcess |  | StandardPDO |  | Completed
50 | edm_processed_nb | NB - Scheduled Work | Proj_nb | PzFactNbScheduledWorkCDC |  | Advanced |  | Completed
51 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzFactNbUwCntInsureBnft1 |  | StandardPDO |  | Completed
52 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzFactNbUwCntInsureBnft2 |  | Advanced |  | Completed
53 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | PzFactNbUwCntInsureBnft3 |  | Advanced |  | Completed
54 | edm_processed_nb |  | Proj_nb | SeqPzNbCommonStgTblCreationMaster |  | Taskflow |  | Completed
55 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | SeqPzNbContractInsuredBenefitMaster |  | Taskflow |  | Completed
56 | edm_processed_nb | NB - Person General Health | Proj_nb | SeqPzNbSubAreaPvtSet3Master |  | Taskflow |  | Completed
57 | edm_processed_nb | NB - UW - Contract Insured Benefit | Proj_nb | SSeqPzNbContractInsuredBenefit |  | Taskflow |  | Completed
58 | edm_processed_nb | NB - Person General Health | Proj_nb | SSeqPzNbSubAreaPvtSet3 |  | Taskflow |  | Completed
59 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealthCntr1 |  |  |  | Completed
60 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealthCntr2 |  |  |  | Completed
61 | edm_processed_nb | NB - Person General Health | Proj_nb | PzFactNbPersonGenrlHealthCntr3 |  |  |  | Completed
62 | edm_processed_nb | NB - Prescription ICD | Proj_nb | PzDS_FactNbPrescriptionIcd |  |  |  | Completed
63 | edm_processed_nb |  | Proj_nb | PzBrgNbCntBnftPartyInsStmnt |  |  |  | Completed
64 | edm_processed_nb |  | Proj_nb | SeqPzNbAgentStmtSet1_Master |  | Taskflow |  | Completed
65 | edm_processed_nb |  | Proj_nb | SSeqPzNbAgentStmtSet1 |  | Taskflow |  | Completed

## Blocker's reso Confirmation
edm_processed_agency | m_RsFamilyBusinessLoad | Sakshi | Target Table ext_lake_oracle_orap10_ai0101.DH_AGENT_CASE_FAMILY_BUZ need to create in this schema as in DS it using Oracle as Target (asked to ignore that Peek target so took Oracle as Target)
adm | m_AgentContactFeeds_IncreLoad | Govind | Target Table AgencyDashboard_AgentContact_IAG_20240302102949 is not available on schema insurance_adm( in DS it's Sequential File)

## Team Velocity
Resource | 2024-05-09
Sridevi | 2days meduim with UT and complex 4 with UT
Smita | 2 days meduim with UT and complex 4 with UT | Mapping cleanup - RTR, JNR removal, Ref,Src rename,additional validation checkpoints, UT revised format was after the earlier estimate hence revised estimate is higher that before.
Rushil | 1 days meduim with UT and 3 complex with UT

## Blocker's Sheet
S.No | Folder Name | Mapping | Owner | Blocker Requested Date | Blocker updated Date | Blocker details | Schema | Table name | Resolved/Unresolved | Confirmed by Project Team
1 | edm_processed_agency | m_RsOpsEmBatchSeqRunDetailsLoad | Smita | 27-2-24 |  | Target connection and object - FF or table/ need clarification. DataStage has parameterized FF name whereas IDMC converted mapping has a table name which is present in Aurora connection with 2 fields extra and field names do not match with incoming fields Aurora Source - adv prop - fetch size to confirm
6 | edm_processed_agency | m_RsEMoneyEmd08BeneficiaryDataload | Govind | 2024-02-27 |  | SRC_hdfsExtractUniqueContract1(conversion brings as FF, we need to check with Rachit)DS File name ExtractUniqueContractData.txt
7 | edm_processed_agency | m_RsEMoneyEmd04ClientDataLoad | Yogeshwar | 2024-02-27 |  | Data Preview failed. Please verify connection, formatting options and object details. ([error [!Invalid Formatting options/Format type. Error: !No rows present in the selected file!!]])
8 | Compliance | m_RsEbossFinraAddress_lar2 | Yogeshwar | 2024-02-27 |  | Data Preview failed. Please verify connection, formatting options and object details. ([error [!Invalid Formatting options/Format type. Error: !No rows present in the selected file!!]])
9 | edm_processed_agency | m_RsEMoneyEmd01LifeDataPrep2 | Yogeshwar | 2024-02-27 |  | Data Preview failed. Please verify connection, formatting options and object details. ([error [!Invalid Formatting options/Format type. Error: !No rows present in the selected file!!]])
10 | edm_processed_agency | m_RsEMoneyEmd01DataLoad | Rajat | 2024-02-27 |  | Target Table does not exit. PzEmoneyInvestmentEmd01 PzEmoneyCalcemd01DataLoad PzEmoneyLifeEmd01 PzEmoneyLtcEmd01 PzEmoneyAnnuityEmd01 PzEmoneyOtherEmd01
11 | edm_processed_agency | m_RsEMoneyCalcExtractData | Sakshi | 2024-02-27 |  | 6 target table PzEmoneyCalcBAL,PzEmoneyCalcAnuity,PzEmoneyCalcemd01DataLoad,PzEmoneyCalcLyf2,PzEmoneyCalcLyf3,PzEmoneyCalcLyf4 not present in Schema insurance_emoney_agency_conv
12 | edm_processed_agency | m_RsEMoneyEmd01LifeDataPrep1 | Sakshi | 2024-02-27 |  | SRC_Copy_of_hdfsLifeContractData having FF in DS LdLifeContractData.txt not able to preview and check formating option(need to check with Rachit), Target Table Lifeextract01 not present in Schema insurance_emoney_agency_conv
13 | edm_processed_agency | m_RsEMoneyEmd03AnnuitiesDataPrep | Sakshi | 2024-02-27 |  | "SRC_hdfsAnnutiyContractData having FF in DS LdAnnutyContractData.txt not able to preview and check formating option(need to check with Rachit), Target Table PzEmoneyAnnuityEmd03 not present in Schema insurance_emoney_agency_conv"
14 | edm_processed_agency | m_RsEMoneyEmd02Marketersdataload | Kamlendu | 2024-02-27 |  | Source Table: Insurance_emoney_agency_conv.ExtractContractMarketerRel not present inDB | Insurance_emoney_agency_conv. | ExtractContractMarketerRel
15 | edm_processed_agency | m_RsEmExtractKeyColumns | Harsh | 2024-02-27 |  | tgt tables : MissingMarketer ExtractUniqueContractData ExtractContractMarketerRel ExtractUniqueClient ExtractContractClientRel needs to be created in db
16 | edm_processed_agency | m_RsEMoneyEmd01AnnuPayoutSeqEQ00 | Krishna | 2024-02-27 |  | Table missing : src - LdAnnutyContractData tgt -PzEmoneyAnnuitiesPayoutPart2
17 | edm_processed_agency | m_RsEMoneyEmd03LifeDataPrep | Krishna | 2024-02-27 |  | Table missing : src - LdLifeContractData tgt -emd03_Lifeextract03
18 | edm_processed_agency | m_RsEMoneyEmd07ClientInsuredrDataLoad | Krishna | 2024-02-27 |  | Table missing : src - ExtractContractClientRe
19 | edm_processed_agency | m_RsEMoneyEmd01AnnuitiesPayoutFinal | Kuldeep | 2024-02-27 |  | Source and Target Table does not exit. Source Table-PzEmoEmoneyAnnuitiesPayoutPart1 Source Table-PzEmoEmoneyAnnuitiesPayoutPart2 Target Table-PzEmoneyAnEmoneyAnnuitiesPayout
20 | edm_processed_agency | m_RsEMoneyEmd03InvestmentDataPrep | Kuldeep | 2024-02-27 |  | Source and Target Table does not exit. Source Table-LdInvstContractData Target Table -PzEmoneyInvestmentEmd03
21 | edm_processed_agency | m_RsEMoneyEmd07HistTblLoad | Kuldeep | 2024-02-27 |  | Target Table does not exit. Target Table -EMoney_ClientInsuredData_EMD07_count Target Table -EMoney_ClientInsuredData_EMD07
22 | edm_processed_agency | m_RsEMoneyEmd01AnnuPayoutSeqNE00 | Harsh | 2024-02-27 |  | src table:LdAnnutyContractData tgt table :PzEmoneyAnnuitiesPayoutPart1 needs to be created in db
23 | edm_processed_agency | m_RsEMoneyEmd01InvestmentDataPrep | Harsh | 2024-02-27 |  | Src table :LdInvstContractData PzEmoneyCalcBAL and tgt table:PzEmoneyInvestmentEmd01 needs to be created in db
24 | edm_processed_agency | m_RsEMoneyEmd04HistTblLoad | Rajat | 2024-02-27 |  | Target Table does not exit. EMoney_ClientData_EMD04__Count EMoney_ClientData_EMD04
25 | edm_processed_agency | PzEMoneyEmd09HistTblLoad | Rajat | 2024-02-27 |  | Target Table does not exit. EMoney_ControlData_EMD09
26 | edm_processed_agency | m_RsEMoneyEmd01AnnuitiesDataPrep1 | Farajiya | 2024-02-27 |  | Source and Target Table does not exit. SRC_hdfsAnnutiyPayoutData>>PzEmoneyAnnuitiesPayout SRC_hdfsAnnutiyData>>LdAnnutyContractData TGT_hdfsAnnutiyemd01Data>>PzEmoneyAnnuitiesDataprep1
27 | edm_processed_agency | m_RsEMoneyEmd03DataLoad | Farajiya | 2024-02-27 |  | Source Table does not exit. SRC_hdfsLifeContractEmd03>>emd03_Lifeextract03 SRC_hdfsInvestmentemd03Data>>PzEmoneyInvestmentEmd03 SRC_hdfsAnuityemd01Data>>PzEmoneyAnnuityEmd03
28 | edm_processed_agency | m_RsEMoneyEmd05HistTblLoad | Farajiya | 2024-02-27 |  | Target Table does not exit.
30 | edm_processed_agency | m_RsEmExtractKeyColumns | Harsh | 2024-02-28 |  | acc_id column is not available in ACCOUNT table - Rachit is looking into it
33 | edm_processed_agency | m_RsEmailCampaignSrcExtrct2 | Smita | 2024-03-06 | 03/07/2024 and 03/08/2024 | SRC_fchdfsEmailCampaignSrcExtract1 - Source table does not exist. Schemaname.Table name : insurance_agency_conv.EmailCampaignSrcExtract1(created on 03/07/24) SRC_hiveRcrCpSmy - Source table does not exist : ext_lake_oracle_orau10_ai0101.rcr_cp_smy. Query error : error [error [Provided Custom query is invalid due to:[[Amazon](500310) Invalid operation: AwsClientException: AccessDeniedException from glue - Resource does not exist or requester is not authorized to access requested permissions.;]]]. 03/08/2024 - Post Client discussion, table available in schema insurance_agency. But in order to parameterize this schema in source query, have defined an InOut parameter 'jpSchemaName_agency' with default value as 'insurance_agency ' schema in mapping but we need verify that this InOut paramter will be included in the updated parameter file as well. TGT_fchdfsEmailCampaignSrcExtract2 - Target table does not exist.Schemaname.Table name : insurance_agency_conv.EmailCampaignSrcExtract2 (created on 03/07/24)
35 | edm_processed_agency | m_RsFamilyBusinessLoad | Sakshi | 2024-03-08 |  | Target Table ext_lake_oracle_orap10_ai0101.DH_AGENT_CASE_FAMILY_BUZ need to create in this schema as in DS it using Oracle as Target (asked to ignore that Peek target so took Oracle as Target)
36 | adm | m_AgentContactFeeds_IncreLoad | Govind | 2024-03-08 |  | Target Table AgencyDashboard_AgentContact_IAG_20240302102949 is not available on schema insurance_adm( in DS it's Sequential File)
37 | edm_processed_agency | m_EmailCampaignOutbound | Krishna | 2024-03-08
38 | adm | m_AgentContactFeeds_Initial | Rushil | 2024-03-08 |  | SRC_OraDimOrgUnit and SRC_OraDimMktr queries in datastage and idmc do not match and expression not converted properly

## Sprint1&2
Sprint | Mapping | Owner | Asset Status | UT Status
Sprint 1 | m_RsInvAumIWS | Yogeshwar | Complete
| m_RsInvAumNFS | Monika | Complete | Done
| m_RsInvNewInvestorDonnelly | Ashwin | Complete | Done
| m_RsInvAumDST | Ashwin | Complete | Done
Sprint 2 | m_RsEMoneyEmd01AnnuPayoutSeqNE00 | Harsh | Complete | Done
| m_RsEMoneyEmd01InvestmentDataPrep | Harsh | Complete | Done
| m_RsEMoneyEmd01LifeDataPrep4 | Ashwin | Complete | Done
| m_RsEMoneyEmd08HistTblLoad | Ashwin | Complete | Done
| m_RsEbossFinraAddress_lar1 | Ashwin | Complete | Done
| m_RsEmExtractKeyColumns | Harsh | Complete | Done
| m_RsEMoneyEmd01AnnuitiesPayoutFinal | Kuldeep | Complete | Done
| m_RsEMoneyEmd01AnnuPayoutSeqEQ00 | Krishna | Complete | Done
| m_RsEMoneyEmd01DataLoad | Rajat | Complete | Done
| m_RsEMoneyEmd03LifeDataPrep | Krishna | Complete | Done
| m_RsEMoneyEmd04HistTblLoad | Rajat | Complete | Done
| m_RsEMoneyEmd05HistTblLoad | Farajiya | Complete | Done
| m_RsEMoneyEmd07ClientInsuredrDataLoad | Krishna | Complete | Done
| m_RsEMoneyEmd07HistTblLoad | Kuldeep | Complete | Done
| m_RsEMoneyEmd09HistTblLoad | Rajat | Complete | Done
| m_RsEbossFinraAddress_lar2 | Monika | In progress
| m_RsEbossFinraAddress_lar3 | Kamlendu | In progress |  | MCT done without Data need to do UAT
Sprint 1
m_RsInvAumIWS
m_RsInvNewInvestorDonnelly
Sprint 2
m_RsEbossFinraAddress_lar2
m_RsEbossFinraAddress_lar3
m_RsEMoneyEmd08HistTblLoad
m_RsEMoneyEmd01InvestmentDataPrep